# Minutes & Actions

# UBS Start Up Project

Kick-Off Meeting, 1/29/02, Room ECS: 06106, 10:00am to 11:00am

Attendees:

Bailey, Debra; Steffes, James D.; Will, Lloyd; Baughman Jr., Don; Bentley, Corry; Donovan, Terry W.; Abler, Bill; Rorschach, Reagan; Day, Smith; Choate, Jason; Hanse, Patrick; Furrow, Dale; Valderrama, Larry

Meeting Summary:

Lloyd Will outlined the many tasks required as part of the UBS start_up project.  We created the following list of actions requiring immediate attention over the next 60 days during the period UBS will be waiting to receive a FERC Power Marketing License.

Jim Steffes will be joining UBS for a meeting with FERC on February 5th .  The plan is to file for a Marketing License on February 6th  (this would start the 60 day licensing process).

It was agreed by the team to meet regularly (daily/weekly) to ensure the following tasks are completed in time to begin trading once we receive our Marketing License.

|  | Action | Responsible | Notes |
| --- | --- | --- | --- |
| 1 | Provide proper language “template” to utilize while discussing the new UBS trading organization with counter parties, TP’s, etc. | Jim Steffes | Jim will provide template to Debra to forward to group |
| 2 | Determine plan for storing and backing up documentation created with the start-up of UBS trading | Debra Bailey | Goal to eventually store all info online for easy access |
| 3 | Finalize Company information required for business. Info. Includes: company name, company contacts, fax #’s, routing #’s, new desk #’s, NERC TSIN identity, etc. | Jim Steffes | Debra will ensure Jim has complete list of required information |
| 4 | Determine if a new DUNS number will be created or if we will use the current UBS DUNS number | Jim Steffes |  |
| 5 | Train, coordinate and transfer the Enron scheduling to Enron Estate personnel | Corry Bentley, Bob Hall, Tom May |  |
| 6 | Ensure all proper data is transferred successfully to UBS. Potentially set up a team to manage the transfer and implement the agreement | Lloyd Will, Dale Furrrow, Jim Steffes | Debra will set up a meeting to discuss the plan, asap |
| 7 | Coordinate credit requirements from the TP’s with Bill Bradford | Jim Steffes, Debra Bailey | Bill would like final TP list and individual TP credit requirements |
| 8 | Create a spreadsheet listing all pools, contacts, and required paperwork | Jim Steffes | Debra will assist |
| 9 | Review Master Agreements and ensure all required TP’s are included | Lloyd Will, Reagan Rorschach |  |
| 10 | Form team to ensure all physical scheduling tools are available and maintained (ETAG, Tradewave) | Corry Bentley, Smith Day, Debra Bailey, Lloyd Will |  |
| 11 | Create a project spreadsheet that correlates dependencies | Debra Bailey |  |