# Estimate

Project Description: One-sheet ad slick, copy provided.

Schedule:

Layout to Enron					10/02

Comments from Enron to Creative Center	10/03

Revisions to Enron				10/04

Final comments/approval to Creative Center	10/05

Disk and Release				10/05

Prints deliver					10/08

|  | Qty 250 | Qty 500 |
| --- | --- | --- |
| Design (9 hours @ $60/hr) *includes one round of changes | $360 | $360 |
| Printing (on 100# cover) | $947.50 | $979.61 |
| Printing (on 80# cover) | $839.27 | $879.33 |
| Totals (100#) | $1307.50 | $1339.61 |
| Totals (80#) | $1199.27 | $1239.33 |

### Print Specifications

QUANTITY: 			250, 500

SIZE AND FORMAT: 		8.5 x 11

STOCK: 			A) 100# gloss cover

B)	80# gloss cover

INK: 				4cp/4cp

PRELIMINARY:	Disk furnished, output film provide proofs

FINISHING:	Trim

PACKING:	Box

SHIPPING/HANDLING:	1 Local Delivery

PRICE:			A)	250 = 947.63

500 = 979.61

B)	250 = 839.27

500 = 879.33