SOLID FUEL INITIATIVE

MEMORANDUM OF UNDERSTANDING

This MEMORANDUM OF UNDERSTANDING (“MOU”) is made as of October 17, 2001 by and between ALSTOM POWER INC., a Delaware corporation with its principal offices at 2000 Day Hill Road, Windsor, CT, 06095 (“Consultant”) and Enron North America Corp., a Delaware corporation with its principal office at 1400 Smith Street, Houston, Texas 77251-1188 (“Company”) (individually each Consultant and Company are a “Party” and collectively they are the “Parties”).

WHEREAS, Company is presently evaluating the development of certain selected solid fuel power plant facilities in the United States to be identified by Company (the “Solid-Fuel Projects”);

WHEREAS, Consultant has experience and expertise in developing facilities comparable to the Solid-Fuel Projects;

WHEREAS, Company desires to enter into a strategic relationship with Consultant in order to assist Company in the development of the Solid-Fuel Projects and Consultant desires to enter into such a relationship with Company; and

WHEREAS, this MOU is intended to set forth certain basic terms of the understanding reached to date between the Parties and serve as a basis for further discussions and negotiations among the Parties, including the fundamental principles upon which the Parties, or their respective designees, will collaborate with each other in connection with the Solid-Fuel Projects, and the negotiation of project specific mutually acceptable definitive turnkey agreements for engineering, procurement, and construction services (“EPC Contracts”) in connection with Conceptual Projects (as defined below in Article 2.3).

NOW, THEREFORE, in consideration of the foregoing premises, the rights and obligations of the Parties hereunder, and other good and valuable consideration, the receipt and sufficiency of which being hereby acknowledged by the Parties, the Parties hereby agree as follows:

##### ARTICLE I

#### Purpose

1.1	Cooperation of the Parties.  The Parties agree this MOU sets forth the basis on which they will cooperate with each other in connection with the Solid-Fuel Projects.  Presently, it is the intent of the Parties that: (i) Company, or its designee, will have the sole right to and responsibility for the identifying, selecting and developing the Solid-Fuel Projects (each a “Project”); and (ii) to the extent of the terms as outlined herein, Consultant, or a wholly-owned direct or indirect subsidiary of Alstom Holdings, will have the responsibility for the provision of information pursuant to Article 2.2 and technical consulting services pursuant to the Consulting Services Agreement ("CSA") entered into contemporaneously with this MOU, including having the opportunity to negotiate with Company or its designee EPC Contracts in connection with certain of the Conceptual Projects, which negotiations shall be exclusive to the extent and in accordance with the procedures more specifically set forth in Article II herein.

1.2	Negotiation of Other Definitive Agreements.  In connection with the foregoing purposes, the Parties agree that they will conduct meetings on a mutually acceptable and convenient basis to discuss and negotiate subsequent mutually acceptable definitive agreements including, but not limited to EPC Contracts for Conceptual Projects selected by Company pursuant to Article 2.3 hereof  (collectively all such agreements constitute the “Definitive Agreements”).

ARTICLE II

FRAMEWORK FOR EXCLUSIVE

EPC CONTRACT NEGOTIATIONS

2.1	Overview of Article II.  The Parties agree that Article II of this MOU establishes the framework pursuant to which they shall initiate and conduct EPC Contract negotiations in connection with each Conceptual Project (as defined below).

2.2	Provision of Target Pricing for a Project.  Exhibit A sets forth certain plant configurations and basic  scope descriptions for such plants along with associated target pricing.  Company will notify Consultant when Company desires Consultant to provide Company with additional written target price ranges for various plant configurations and basic scope descriptions in connection with any Project which configuration and basic scope may not be listed in Exhibit A.  Such additional target price ranges shall be provided in accordance with the parameters set forth in Exhibit A and will be subject to the mutual agreement of the Parties and provided by Consultant at no cost to Company.  Any such additional agreed target pricing and the target pricing listed in Exhibit A shall collectively be referred to as  (“Target Pricing”). The provision of Target Pricing by Consultant and Company’s receipt thereof shall in no way obligate Company to issue, nor obligate Consultant to accept, a Notification Letter (as defined below).

2.3	Company Identification of Conceptual Projects.  At any point in time during the term of this MOU (as specified in Article 3.2), Company or its designee may, in its sole discretion, issue a notification letter (a “Notification Letter”) to Consultant in the form attached as Exhibit B indicating that Company or its designee desires to initiate and conduct EPC Contract negotiations with Consultant in connection such Conceptual Project in accordance with the provisions of Article 2.4 below. Upon the issuance of a Notification Letter, each Project referenced therein shall hereinafter be referred to as a “Conceptual Project”.  Included within such Notification Letter shall be the Target Pricing established under Article 2.2 for the applicable plant configuration and scope.

2.4	Framework for Exclusive EPC Contract Negotiations.  Upon the issuance of a Notification Letter, the Parties agree that they shall use commercially reasonable efforts to initiate and conduct EPC Contract negotiations for the Conceptual Project in accordance with the following framework:

- Exclusivity Obligations of the Parties. Unless terminated earlier pursuant to Article 2.4(e), the Parties agree that upon the issuance of a Notification Letter by Company and acceptance by Consultant (as evidenced by Consultant’s return of the fully executed Notification Letter to Company), each Party shall be obligated to exercise commercially reasonable efforts to conduct EPC Contract negotiations with respect to the Conceptual Project covered in the Notification Letter for a period of twelve (12) months from the date of such Notification Letter, (provided however, that should Company notify Consultant in writing that work on a Conceptual Project is being suspended and shall so notify Consultant upon resumption of work, such period shall be extended for the time equal to such suspension, provided any such extension period shall not exceed twelve (12) months)  in connection with each such Conceptual Project (the “Exclusivity Period”).  During the Exclusivity Period, the Company shall be prohibited from soliciting offers from or engaging in negotiations with other third parties for (i) EPC Contracts or (ii) the supply of major equipment, in connection with the Conceptual Project covered in the Notification Letter and Consultant shall be prohibited from proposing, offering or engaging in negotiations with participants in the Conceptual Project other than Company or with third parties regarding the provision of consulting, engineering, procurement, or construction services for the Conceptual Project, or any projects that are substantially similar to each such Conceptual Project and would be located within 250 miles of each such Conceptual Project (a "Substantially Similar Project"). Notwithstanding the foregoing sentence, nothing contained herein shall prevent (x) Company from soliciting, during the Exclusivity Period, pricing information from third parties for use by Company in reviewing and analyzing the equipment prices provided by Consultant, or (y) Consultant from offering to supply or from supplying, during the Exclusivity Period, equipment to any third party, provided however, that Consultant shall notify Company prior to making any offer to supply a boiler to a Substantially Similar Project.

b.	Negotiation of EPC Contract based on Term Sheet.  The Parties agree and acknowledge that the generalized EPC term sheet, initialed by each of them and attached hereto as Exhibit C (the “Term Sheet”), shall serve as the baseline for the EPC Contract negotiations for each specific Conceptual Project.  Notwithstanding the foregoing, the Parties agree and acknowledge that individual specific requirements of each Project may drive deviations from the Term Sheet and that these requirements will surface during the development of each Conceptual Project; however, the Parties agree to use reasonable efforts to adhere to the Term Sheet in the negotiation of EPC Contracts for any individual Conceptual Projects.

c.	Provision of Order of Magnitude Estimates for Conceptual Projects.  Upon the issuance of a Tasking Letter by Company under the CSA and acceptance thereof by Consultant (as evidenced by Consultant’s return of the fully executed Tasking Letter Release to Company), Consultant will provide such conceptual engineering, estimating, and development support, including an order of magnitude estimate (“OOM Estimate”) in connection with each Conceptual Project as shall be specified in the Tasking Letter Release.  Consultant shall provide the OOM to Company within thirty (30) days of the issuance of the Tasking Letter Release, or other period of time as may mutually be agreed. The Parties agree and acknowledge that the OOM Estimate shall be reviewed with Company on an open book basis and based on the Term Sheet and the Baseline Criteria (defined below).  The initiation and performance of such activities shall be according to the schedule and terms outlined under a specific Tasking Letter Release issued to Consultant by Company under the CSA.  The Parties acknowledge that the detailed level of estimate support documentation reviewed while developing the OOM Estimate will not be as detailed or complete as will be when developing the LSTK Price as certain specific cost elements for manufactured equipment may be derived from Consultant’s other similar projects.  In cases where such estimating information has been confirmed to be derived from Consultant’s other similar projects, Company shall be afforded a reasonable review of supporting estimating documentation necessary for Company to understand the basis and justification of estimate composition, however, Consultant shall not be obligated to disclose its confidential equipment pricing information of such other similar projects to Company.  Company will provide Consultant with any site information in its possession relating to or reasonably necessary for the Conceptual Project and requested by Consultant.  Such site information provided by Company, as well as professional assumptions made by Consultant regarding information not provided by Company that are clearly identified in writing by Consultant in the OOM provided to Company shall constitute the “Baseline Criteria”.

d.	Provision of Lump Sum Turn Key Pricing for Conceptual Projects.  Company may, in its sole discretion at any time after the provision of the OOM Estimate by Consultant, direct Consultant via the issuance of a Tasking Letter by Company under the CSA and acceptance thereof by Consultant (as evidenced by Consultant’s return of the fully executed Tasking Letter Release to Company), to prepare and provide to Company, in writing, a lump sum turn key EPC open book price (the “LSTK Price”) for a Conceptual Project.  The LSTK Price will be based upon a detailed scope book that fully describes the agreed Conceptual Project scope, receipt of bids for major equipment and agreed terms and conditions for an EPC contract for the Conceptual Project, and shall be the price at which Consultant shall offer to enter into such EPC Contract for such Conceptual Project.   Development of the LSTK Price will be performed on an open book basis, and Consultant will provide to Company on an open book basis, a written break down of all pricing information particular to the specific Conceptual Project or project segments, which disclosure shall be in accordance with the provisions of Exhibit D, including the examples set forth therein.  The intent of the foregoing is that, Company shall be afforded a reasonable review of estimate details, pricing, and quotes received, and a reasonable opportunity to review and approve all LSTK Price components, including but not limited to major equipment quotations utilized in preparing the LSTK Price.  Such approval rights shall be timely exercised by Company.  In performing its review as above, Company shall not have the right to retain photo copies of all Consultants estimate details, pricing components, equipment quotations or supporting estimating material, but may take and retain its notes and Consultant provided summary documents.  Supporting estimate documents may be retained by Company as mutually agreed between Parties.  Notwithstanding such limitation on the retention of copies, Company’s project technical director shall be allowed to retain a complete copy of the baseline estimate (including all revisions and updates) for his use in connection with the Conceptual Project. Consultant shall bear its costs of negotiating the EPC Contract for such Conceptual Projects.  Consultant shall be reimbursed, pursuant to and as authorized under the CSA, for preparing and reviewing the open book price estimate and determining the LSTK Price with Company.

e.	Expiration and/or Termination of Exclusive EPC Contract Negotiations.  The Exclusivity Period and the obligations of the Parties with respect thereto in connection with each such Conceptual Project shall expire as set forth in Article 2.4 (a) unless terminated earlier as set forth below:

(i)	by Company effective upon the issuance of written termination notice to Consultant, if with respect to such Conceptual Project (a) the OOM Estimate exceeds the Target Pricing by greater than five percent (5%) (excluding any mutually agreed percentage variance(s) resulting from either requests by Company for changes to the Baseline Criteria or differences that are found to exist between assumed and actual site conditions (hereinafter “Variances”)) or (b) the LSTK Price exceeds the OOM Estimate by greater than five percent (5%) (excluding any agreed Variances); or

- by Company or Consultant, in the event that the Parties are unable to reach agreement on a mutually acceptable EPC Contract (including, but not limited to schedule, guarantees, terms and LSTK Price) for a Conceptual Project, in which case the Party seeking to terminate the exclusive EPC Contract negotiations shall provide written notice to the other with an explanation of the reasons for such termination.  The termination of the Exclusivity Period and release of the exclusivity obligations as set forth in this Article 2.4 (e)(ii) shall become effective thirty (30) days after the date of such notice; provided, however, that upon the issuance or receipt of the foregoing notice, as the case may be, either Party may request that nominated executive officer level representatives from the Parties meet during such thirty (30) day period and attempt to resolve the causes of the termination notice; or

- by Company effective upon the issuance of written notice to Consultant if Company elects to cancel the Conceptual Project.

The expiration or termination of each such Exclusivity Period as set forth above in connection with a Conceptual Project shall in no way impact the obligations of the parties under the CSA. Upon the expiration or termination of any Exclusivity Period under (i) or (ii) above, and subject to the provisions of Article 3.5, Company shall be freely entitled to solicit EPC Contract offers from and engage in EPC Contract negotiations with other third Parties in connection with such Conceptual Project without penalty, further recourse or obligation to Consultant.  Upon the expiration or termination of any Exclusivity Period under (i), (ii), or (iii) above, and subject to the provisions of Article 3.5,  Consultant shall be freely entitled to propose, offer or engage in negotiations with other third parties for EPC Contracts for any Substantially Similar Project.

Article 3

GENERAL TERMS AND CONDITIONS

3.1	Adequacy of Consideration.  Both Parties acknowledge the adequacy and sufficiency of consideration of this MOU.

3.2	Term and Termination.  This MOU shall remain in force and effect until the earliest to occur of the following events: (a) December 31, 2002 (the “Expiration Date”), provided that the Expiration Date shall be automatically extended by one six (6) month period following December 31, 2002, unless either Party provides written notification thirty (30) days prior to December 31, 2002 of its desire not to extend the term of the MOU, or (b) written agreement by the Parties to terminate this MOU prior to the Expiration Date.

3.3	Representations and Warranties.  Each Party hereby represents and warrants to the other Party that this MOU (a) has been validly executed and delivered, (b) has been duly authorized by all action necessary for the authorization hereof, and (c) is the legal, valid and binding obligation of such Party, enforceable in accordance with its terms.

3.4	Approval.  No Party shall be bound by any Definitive Agreement until (a) such Party shall have agreed to and executed a Definitive Agreement, and (b) all conditions precedent to the effectiveness of any such Definitive Agreement shall have been satisfied.

3.5	Confidentiality. Reference is made to that certain confidentiality agreement entered into between the Parties as of March 19, 2001 (the “Confidentiality Agreement”), which the Parties do hereby agree is cancelled. Notwithstanding the foregoing, the Parties agree and acknowledge that “Confidential Information” (as defined in the terms of the Confidentiality Agreement) which was exchanged between the Parties under the Confidentiality Agreement shall be deemed to constitute Confidential Information under this MOU and shall be afforded the protections of this Article 3.5.  In connection with the activities and discussions that the Parties will have in connection with the matters addressed by this MOU, the Parties are prepared to furnish one another with information (whether written, oral or electronically-generated and including this MOU) which is confidential, proprietary or generally not available to the public (the "Confidential Information").  The Parties each agree that during the term of this MOU and for a period two (2) years from the date of the termination of this MOU neither Party shall disclose the other Party’s Confidential Information without the other Party’s prior written consent; provided, however, a Party may disclose:

(a) the other Party’s Confidential Information to the Party’s affiliates, representatives, directors, employees, advisors, lawyers, accountants,  lenders and potential lenders, investors, equity participants, partners, co-venturers, or other participants in a Project or Conceptual Project, and their respective governing leaders, representatives, affiliates, directors, officers, employees, advisors, lawyers, accountants, lenders and potential lenders, investors, equity participants, partners or co-venturers in a Project or Conceptual Project (collectively, "Representatives"), who agree to maintain the confidentiality of such Confidential Information in accordance with the terms hereof, and;

(b) any of the other Party’s Confidential Information that: (i) becomes generally available to the public; (ii) is already known to the Party at the time of disclosure by the other Party; or (iii) is acquired from a third party not known to the receiving Party to be prohibited from making disclosure.

### Consultant and Company further agree that neither Party shall use the other Party’s Confidential Information other than for the purpose of evaluating, negotiating and consummating Conceptual Projects in connection with this MOU.  Upon a Party’s request, the other Party shall return all written Confidential Information of the requesting Party, except for that portion of such Confidential Information that may be found in analyses, compilations, studies or other documents prepared by, or for, the returning Party, and the returning Party and its Representatives shall not retain any copies of such written Confidential Information.  The portion of written Confidential Information that may be found in analyses, compilations, studies or other documents prepared by, or for, the returning Party, any Confidential Information furnished by the requesting Party not so requested or returned, will be held by the returning Party and kept subject to the terms of this MOU, or destroyed.

### Notwithstanding anything contained in this MOU:

### (1)	Confidential Information may be disclosed to any governmental, judicial or regulatory or exchange authority requiring such Confidential Information, or to comply with any applicable law, order, regulation or ruling provided that: (a) each Party shall promptly inform the other Party of the substance of any inquiries received by such Party from any governmental, judicial or regulatory or exchange authority in connection with attempts to gain access to Confidential Information concerning the proposed transaction; (b) prior to such disclosure, the Party who originally supplied the Confidential Information is given the earliest practicable notice of any disclosure requirement so that it may take whatever action it deems appropriate, at its sole expense, including intervention in any proceeding and the seeking of an injunction to prohibit such disclosure; (c) such Confidential Information is submitted under applicable provisions in the jurisdiction in which disclosure is sought for confidential treatment by such governmental, judicial or regulatory authority; and (d) the Party subject to the governmental, judicial or regulatory or exchange authority endeavors to protect the confidentiality of any Confidential Information to the extent reasonable under the circumstances and to use its good faith efforts to prevent the further disclosure of any Confidential Information provided to any governmental, judicial or regulatory authority.  If any court or other tribunal having jurisdiction orders that a Party is obligated to disclose any documents containing Confidential Information, then the Party shall first request from the other Party a “Public Disclosure Copy” in which the Confidential Information has been redacted at the other Party’s discretion to the extent that such redaction is permitted by the applicable court or tribunal requiring disclosure, as the case may be, and

### The provisions of this Article 3.5 shall not prevent Company from using the information contained within Exhibit A, including without limitation the Target Prices or any additional information prepared by Consultant and provided to Company pursuant to Article 2.2 hereof, and the EPC Agreement including its attachments or exhibits either prepared or being prepared (collectively, the "MOU Work Product") to proceed with any Conceptual Project, including with any 3rd Party EPC Contractor, if this MOU or the Exclusivity Period with respect to such Conceptual Project terminates or expires; however such use shall be at Company's risk and without any warranty whatsoever, either express or implied, by Consultant.  For the avoidance of doubt, upon the termination or expiration of this MOU or the Exclusivity Period with respect to the subject Conceptual Project, Company shall be permitted to freely disclose any such MOU Work Product other than the Target Prices to third parties in connection with any Conceptual Project, it being agreed and understood that the Target Prices shall continue to be subject to the non-disclosure obligations of this Article 3.5 in accordance with its terms. Company’s right to use the open book estimating information obtained in reviewing and preparing the LSTK Price shall not extend to pricing information provided by Consultant pursuant to Article 2.4(d) and Exhibit D, which shall remain Consultants Confidential Information and which open book pricing estimating information Company may disclose  only to its employees having a reasonable need to know.

### Nothing in this MOU shall obligate Consultant to disclose to Company any of Consultant’s Confidential Information which discloses its manufacturing drawings, manufacturing practices or processes of manufacturing operations related to the equipment manufactured by Consultant.

### Although a Party furnishing Confidential Information has endeavored to include materials which the furnishing Party believes to be reliable and relevant for the receiving Party's evaluation, the furnishing Party makes no representation or warranty as to the accuracy or completeness of any such provided information.  Furthermore, neither the furnishing Party nor its Representatives shall have any liability to either the receiving Party or its Representatives resulting from the use of any such information by the receiving Party or its Representatives in accordance with the terms, and for the purpose set forth in this MOU.  Notwithstanding the foregoing sentence, a Party shall be liable for any breach of the other provisions of this Article 3.5  by such Party or any of its representatives.

3.6	Entire Agreement.  As of the date of this MOU, this MOU constitutes the entire agreement of the Parties relating to the subject matter hereof and supersedes all prior discussions, agreements or understandings, whether oral or written, relating to such subject matter other than the CSA.  There are no other written or oral agreements or understandings among the Parties regarding the subject matter of this MOU.  Any amendment of this MOU must be written and signed by both Parties.  Waivers of rights under this MOU must be in writing and signed by the Party to be bound thereby. No failure to exercise, no delay in exercising, and no course of dealing or trade custom with respect to, any provision of this MOU shall waive such provision.

3.7	Governing Law and Dispute Resolution.  This MOU shall be governed by and construed in accordance with the laws of the State of New York, without giving reference to its conflicts of laws principles.  All claims and matters in question arising out of this MOU or the relationship between the Parties created by this MOU, whether sounding in contract, tort or otherwise, shall be resolved by binding arbitration pursuant to the Federal Arbitration Act.  The arbitration shall be administered by the American Arbitration Association ("AAA").  There shall be three arbitrators.  Each Party shall designate an arbitrator, who need not be neutral, within thirty (30) days of receiving notification of the filing with the AAA of a demand for arbitration.  The two arbitrators so designated shall elect a third arbitrator.  If either Party fails to designate an arbitrator within the time specified or the two Parties' arbitrators fail to designate a third arbitrator within thirty (30) days of their appointments, the third arbitrator shall be appointed by the AAA.  The location of any arbitration shall be New York City, New York.

3.8	NON-INCLUSIVE; NON-BINDING.  THIS MOU DOES NOT CONTAIN ALL MATTERS UPON WHICH AGREEMENT MUST BE REACHED IN ORDER FOR THE CONSUMMATION OF ANY DEFINITIVE AGREEMENT TO BE NEGOTIATED PURSUANT TO THIS MOU.  THIS MOU, ANY TARGET PRICING, OOM ESTIMATES, TERM SHEETS OR DRAFT EPC AGREEMENT: (1) ONLY EXPRESS THE INTEREST OF THE PARTIES TO NEGOTIATE A TRANSACTION THAT WILL BE FINALIZED IN A DEFINITIVE AGREEMENT AT A FUTURE TIME; (2) DO NOT CREATE AND ARE NOT INTENDED TO CREATE A BINDING AND ENFORCEABLE CSA OR EPC CONTRACT BETWEEN THE PARTIES OR ANY AGREEMENT OR OBLIGATIONS TO ENTER INTO ANY CSA OR EPC CONTRACT; AND (3) MAY NOT BE RELIED UPON BY A PARTY AS THE BASIS FOR A CSA OR EPC CONTRACT BY ESTOPPEL IMPLICATION, OR OTHERWISE. A BINDING CSA OR EPC CONTRACT COMMITMENT WITH RESPECT TO THE SOLID-FUEL PROJECTS OR ANY OTHER SUBJECT MATTER IN CONNECTION WITH THE SOLID-FUEL PROJECTS CAN ONLY RESULT FROM THE EXECUTION AND DELIVERY OF DEFINITIVE AGREEMENTS.  THE PARTIES AGREE THAT THEY HAVE HAD THE BENEFIT OF COUNSEL IN PREPARING THIS MOU, AND THEY FURTHER AGREE THAT NO ACTIONS ON THE PART OF EITHER PARTY SHALL BE DEEMED TO RENDER THIS MOU A BINDING OBLIGATION WITH RESPECT TO THE EXECUTION OF A CSA OR AN EPC CONTRACT FOR ANY SOLID-FUEL PROJECT(S).

3.9	Relationship of the Parties.  The Parties are not and shall not be deemed in a relationship of partners or joint venturers by virtue of this MOU, nor shall either Party be an agent, representative, trustee or fiduciary of the other.  Neither Party shall have any authority to bind the other to any agreement.

3.10	LIMITATION OF LIABILITY.  NOTWITHSTANDING ANYTHING HEREIN TO THE CONTRARY, NEITHER COMPANY NOR CONSULTANT, NOR ANY OF THEIR RESPECTIVE ELECTED OR APPOINTED OFFICIALS, DIRECTORS, OFFICERS, SHAREHOLDERS, MANAGERS, OR EMPLOYEES WILL BE LIABLE TO ANY OTHER PARTY, OR ITS DIRECTORS, OFFICERS, SHAREHOLDERS, MANAGERS OR EMPLOYEES, WHETHER UNDER BREACH OF CONTRACT, BREACH OF WARRANTY, GUARANTEE, INDEMNITY, TORT LIABILITY (INCLUDING WITHOUT LIMITATION BOTH NEGLIGENCE AND STRICT LIABILITY), STRICT LIABILITY OR OTHERWISE, FOR ANY INCIDENTAL, SPECIAL, INDIRECT, EXEMPLARY, PUNITIVE OR CONSEQUENTIAL DAMAGES WHATSOEVER (INCLUDING WITHOUT LIMITATION LOST PROFITS OR REVENUE) OF ANY NATURE CONNECTED WITH OR RESULTING FROM PERFORMANCE OF THIS MOU, BUT SHALL BE LIABLE TO THE OTHER PARTY ONLY FOR DIRECT ACTUAL DAMAGES ARISING FROM WILLFUL BREACH OF THIS MOU, SOLE, JOINT OR CONCURRENT NEGLIGENCE, MISCONDUCT OR FRAUD.

3.11	Assignment.  Neither Party may assign this MOU without the prior written approval of the other Party, which approval shall not be unreasonably withheld or delayed.  Notwithstanding the foregoing, however, either Party may freely assign its obligations hereunder to any of its affiliates and any non-affiliated entity in connection with the financing or accounting structure of the Project, provided that the Party making such assignment notifies the other Party in writing of such assignment.

3.12	Notices:  All notices required or permitted by the terms hereof shall be sent by Certified Mail or facsimile (with written confirmation, generated by the transmitting fax machine, of successful transmission to the recipient’s fax number indicated below) to the following addresses if sent to Consultant or Company:

To Company:			To Consultant:

Enron North America Corp.		Alstom Power Inc.

1400 Smith Street 				2000 Day Hill Road

Houston, Texas 77002			Windsor, CT 06095

Attention:  General Counsel		Attention:  General Counsel

Fax: (713) 646-6280			Fax: (860) 285-9790

3.13	Survival.  Notwithstanding anything to the contrary contained in this MOU, the confidentiality obligations contained in Article 3.5 and the provisions of Article 2.4, including but not limited to the expiration of the respective Exclusivity Period in connection with each Conceptual Project, shall survive termination of this MOU, and shall expire only as provided in such Articles.

  - No Third Party Beneficiaries.  Except with respect to any permitted assignees of this MOU as set forth above in Article 3.11, no other parties shall be deemed to be third party beneficiaries of this MOU.

[Signatures follow on next page.]

IN WITNESS WHEREOF, each of the undersigned Parties has caused this Memorandum of Understanding to be executed and delivered in counterparts, including by facsimile or otherwise, each of which shall be deemed an original but which together shall constitute one and the same instrument, its duly authorized officer as of the date first written above.

ALSTOM POWER INC.

## By:		___________________________________________

Name:		___________________________________________

Title: 		___________________________________________

ENRON NORTH AMERICA CORP.

## By:		___________________________________________

Name:		___________________________________________

Title: 		___________________________________________

EXHIBIT A

TARGET PRICING

|  | Units Per Site | Configuration B T NET OUTPUT | Target Price/Net MW PETCOKE / PRB | Schedule from NTP Months | Validity Period |
| --- | --- | --- | --- | --- | --- |
| A | 2 | 1x1 250 MW CFB | 1100 1250 | 40 | 12/31/2001 |
| B | 2 | 1x1 800 MW PC | N/A 950 | 50 | 12/31/2002 |
| C |  | Later |  |  |  |
| D |  | Later |  |  |  |
| E |  | Later |  |  |  |

The Target Price set forth above for each configuration reflects the scope for such configuration as outlined in the applicable Schedule (A, B, C, etc.)  to this Exhibit A, and is valid for the  period indicated above (the “Validity Period”).  If the Parties agree to add additional configurations pursuant to Article 2.2, then this Exhibit A shall be amended in writing to incorporate the Parties’ agreement with respect to the above information for each such additional configuration, and a Schedule shall be added hereto for each such additional configuration, which describes the scope thereof.

If any Validity Period should expire during the term of this MOU (including any extension pursuant to Article 3.2), the Parties will mutually agree (on or before the fifth  day prior to such expiration), upon a written amendment of this Exhibit A to either extend such Validity Period; revise the subject Target Pricing and applicable Validity Period, or delete the subject configuration.

EXHIBIT A

SCHEDULE [A],

Scope Description for Plant Configuration [A]

EXHIBIT A

SCHEDULE [B],

Scope Description for Plant Configuration [B]

(Scope Document to be inserted when agreed)

Exhibit B

Form of Notification Letter of a Conceptual Project

Date:	_________

Alstom Power Inc.

2000 Day Hill Road

Windsor, CT 06095

Subject:	Notification of Conceptual Project under the Memorandum of Understanding dated as of [________], 2001

Dear Sir,

Reference is made to that certain Memorandum of Understanding entered into between Alstom Power Inc., and Enron North America Corp. dated as of [________], 2001 (the “MOU”).  Pursuant to Article 2.3 of the MOU, please be advised that we hereby notify you that [insert project description] is hereby categorized as a Conceptual Project under the terms of the MOU and that our future negotiations in connection therewith shall be on an exclusive basis in accordance with Article 2.4 of the MOU.  Please be further advised that pursuant to Exhibit A, the Target Pricing for such opportunity is [_________].

Sincerely,

ENRON NORTH AMERICA CORP.

By:

Name:

Title:

AGREED AND ACCEPTED

AS OF THE DATE SET FORTH ABOVE:

ALSTOM POWER INC.

By:

Name:

Title:

EXHIBIT C

EPC TERM SHEET

(ARTICLE 2.4(b))

Use of defined terms of this Term Sheet:

“EPC Agreement”	The Lump-sum EPC turnkey contract between Contractor and Company (or their delegated entities) for a Project.

“Company”	(TBD)

“Equipment”	All equipment comprising the Facility.

### “Facility”		The agreed nominal MW power plant including all Contractors Work inside the site fence and comprised of all Plant and Unit(s).

### “Plant”		All Unit(s) comprising a Facility.

### “Unit”	Electrical power generating unit containing one turbine, one or more boilers and a proportionate share of Facility infrastructure.

“Work”	All work provided by Contractor under the EPC Agreement.

The summary statements listed herein represent the principles of understanding between the Parties for the respective terms and do not necessarily set forth the exact wording to be used in the EPC Agreement.

| Term | Summary of EPC Agreement |
| --- | --- |
| - Contracting Approach | Lump-sum turnkey (“LSTK”) pricing, inclusive of all labor, material, equipment, and services, with guaranteed performance and Substantial Completion Dates. |
| - Contractors Scope | Contractor shall provide turnkey engineering, procurement, construction and training (“EPC”) services for the complete Facility including power Units, all materials handling systems, tank facility, switchyard, and other Plant systems described in an agreed scope document to be attached as an exhibit to the EPC Agreement, including such other obligations as are typical of EPC contractors building non recourse project financed power projects. Contractor shall warrant compliance with portions of the Project off take agreements and similar Project documents that will be identified in the EPC Agreement. |
| - Basic Design / Detailed Eng. | Contractor shall be responsible for all basic design and all detailed engineering. |
| - CSA Merger | All Services provided under the CSA and used for the Project shall be deemed to have been performed under the EPC Agreement for all purposes other than the Contract Price. |
| - Codes and Standards | Contractor shall engineer and construct the Facility using all applicable, U.S. codes and standards (industry, local, state and federal). |
| - Notice To Proceed (“NTP”) | Contractor shall not initiate activities and Company shall have no obligations to Contractor until such time Company has issued NTP to Contractor. The following shall be a condition precedent to Company’s issuance of NTP; - Financial closing. - The necessary permits required to start construction and which are required to be issued in the name of Company shall be in place. - Company shall be in a position to give possession and full access of the site to Contractor. - The required insurances shall be in place. - Contractor shall have received the agreed advanced payment. - Contractor shall have received the written verification from Company’s third party financial advisor or Project lender confirming that adequate funding is available. |
| - Price | Fixed price Contract (“Contract Price”). The EPC Agreement may also contain a per Unit price, depending on Plant configuration, being the Contract Price apportioned on a per Unit basis (“Unit Contract Price”) which aggregated sum shall equal the Contract Price. |
| - Taxes | The Contract Price includes, but is not limited to all taxes on Equipment and materials necessary to complete the Facility but excluding tax on real property and on Contractors income. The Parties shall reasonably cooperate to maximize the tax efficiencies of the Project. These provisions may be otherwise mutually agreed on a Project-by-Project basis pending the Project tax structure. |
| - Duties | All import duties; custom clearance charges and similar costs are the responsibility of Contractor and shall be included in the Contract Price. The Parties shall reasonably cooperate to minimize duty expenses. |
| - Company Obligations | Company shall be obligated to obtain the following; - Project financing. - Permits which are required to be obtained in Company name. - The site with lay-down area and full access for Contractor. - Fuel and sorbent supply (i.e. coal, coke, sorbent, sand) for operating the Facility during commissioning, testing, start-up and commercial operation. - Water for construction use to within (250ft.) of site boundary. To be ready in accordance with each agreed Project schedule. - Interconnect for power supply and off-take for operating the Facility during commissioning, testing, start-up and commercial operation. - Waste water discharge/disposal for operating the Facility during commissioning, testing, start-up and commercial operation. |
| - Payment | - An advance payment shall be agreed on a Project-by-Project basis. - Predetermined milestones, invoiced monthly. - Withholdings may be made for deficient progress as measured against the agreed Project Milestone Schedule. Such withholding, if any, shall not preclude subsequent payment of non-disputed milestones properly completed and due. - Non-disputed payments will be made (30) days after receipt of invoice. - (90%) paid / (10%) retainage on each non-disputed invoice. - Late payments by either Party shall bear interest at a rate to be agreed on a Project-by-Project basis. - Contractor may suspend for late payment of non-disputed amounts which are beyond (45) days past due, provided (10) day notice of intent to suspend has been received by Company. - Contractor may terminate for late payment of non-disputed amounts which are beyond (75) days past due, provided (10) day notice of intent to terminate has been received by Company. |
| - Retention | Retention shall be withheld from each invoice; however, Contractor may post security in the form of an unconditional and irrevocable letter of credit (or other security acceptable to Company), in the amount of such withholding, in a form and issued by a financial institution acceptable to Company and Lenders. Such retention, or security will be released upon Final Completion (“FC”). |
| - Parent Guaranty | As a condition precedent to Notice To Proceed (“NTP”), Contractor shall provide Company an unconditional and irrevocable parent guaranty of its obligations under the EPC Agreement from its ultimate parent company (Alstom Holdings) in a format to be mutually agreed. An alternate form of security (i.e. bond) in a form and content acceptable to Company may otherwise be agreed. |
| - Security for Payment | As a condition precedent to NTP, Contractor shall be provided written verification from Company’s third party financial advisor or Project lender confirming that funding in amounts adequate to cover the Contract Price is available to Company and the conditions precedent to draw such funds have been satisfied. The payment milestones will be based on maintaining Contractor in a neutral cash flow position. |
| - Operational Spare Parts | Contractor shall provide recommended operational spare parts listings and associated fixed prices with the LSTK Price. Such pricing shall be valid for (24) months after NTP. The cost for Contractors services for purchasing, administration, expediting, receiving and storage of such spares through Substantial Completion (“SC”) shall be to the account of Contractor. The cost of such operational spares shall be to the account of Company. |
| - Subcontracts | The EPC Agreement will include an agreed Approved Vendor List (“AVL”) for subcontractors, vendors and suppliers. Contractor will be responsible as a LSTK contractor for all Equipment, Work and materials comprising its scope of work and shall be responsible for its subcontractors, vendors and suppliers to the same extent as if provided by Contractor. Provisions for flow down of certain Company and Owner terms and conditions shall also be included. |
| - Purchase Order Assignment | If Contractor is required to purchase Equipment prior to NTP, the Parties shall mutually agree on the format of, and security for, Contractor’s purchase (i.e. as Company’s agent with full assignment at NTP, option agreement, or direct purchase by Contractor). |
| - Permits | Contractor shall be responsible for permits required to be taken in its name. Company shall be responsible for permits required to be in the name of Owner. The Parties shall reasonably cooperate with each other in the application and maintenance of such permits. |
| - Key Personnel | Contractor’s key personnel shall be approved by Company. |
| - Mechanical Completion | “Mechanical Completion” shall mean, with respect to each Unit, system, or component of the Facility, the completion of the Work relating thereto, including flushing and purging of systems; setting of the Equipment on foundations; connecting Equipment to other applicable equipment with piping, wiring, controls, and safety systems; ensuring that such Equipment and such related operating systems are individually cleaned, leak-checked, lubricated, and point-to-point checked to verify that such Equipment and such related operating systems have been correctly installed so as to respond to simulated test signals equivalent to actual signals received during operation; and ensuring that such Equipment and related operating systems are ready for initial operation, adjustment and testing and may be so operated, adjusted and tested safely and without damage thereto or to any other property and without injury to any person. Mechanical Completion shall also include but not be limited to the following pre-commissioning activities with respect to the applicable unit, system, or component: stroking of all control valves, phase rotation of electrical equipment, and continuity of other electrical circuits (including loop checks) and response of controls and control equipment. It is intended that the above statement as written in this section 20, will be the definition of Mechanical Completion in the EPC Agreement. |
| - Completion Guarantees | Contractor guarantees that it will (i) cause the Facility to achieve Mechanical Completion (“MC”), (ii) achieve Substantial Completion (“SC”) by the Guaranteed SC Date(s) and (iii) achieve Final Completion (“FC”) by the Guaranteed FC Date. |
| - Performance Guarantees | Contractor shall guarantee the following on either a Facility or on a per Unit basis as determined by Facility layout, while meeting Sound Level Guarantees and Emissions Guarantees in order to achieve SC (the “Performance Guarantees”): - Net Electrical Output Guarantee (TBD) - Net Heat Rate Guarantee (TBD) - Reliability (TBD) - Lime/Limestone Consumption (TBD) “(TBD)” to be agreed on a project-by-project basis. |
| - Anticipated Capacity Margin | Base design to include an eight (8%) percent additional capacity design margin. |
| - Specific Performance Guarantees | The following comprise Contractors “Specific Performance Guarantees”: - Minimum (TBD%) Net Electrical Output Guarantee (100hr. test)* - Maximum (TBD%) Net Heat Rate Guarantee (2, 4hr tests)* - Sound Level Guarantees - Emissions Guarantee * each while meeting the Sound Level Guarantee and the Emissions Guarantee. “(TBD%)” to be agreed on a project-by-project basis. |
| - Substantial Completion | Completion of the following minimum acceptance criteria will constitute Substantial Completion: - Mechanical Completion has been achieved. - The Facility can be safely and reliably operated for its specified purpose. - The Parties have mutually agreed the Punch List. - All Work is properly incorporated into the Facility so that it is capable of commercial operation. - Performance Tests have been completed. - The Facility meets all the Specific Performance Guarantees. ### The Facility has (i) met all of the Performance Guarantees or (ii) the Facility has met the Specific Performance Guarantees but not the Performance Guarantees, and Contractor has paid all Performance LD’s and notified Company that it will not exercise its rights to retest and improve performance levels or (iii) the Facility has met the Specific Performance Guarantees but not the Performance Guarantees, and Contractor has notified Company that it will exercise its right to improve performance levels and retest. - Operations personnel have received the agreed training from Contractor. Unless and to the extent agreed between the Parties, Company shall not have the right to operate the Unit(s) prior to SC. |
| - Improving Performance Levels and Payment of LD’s | Contractor shall have the right to undertake at its cost Work to improve the performance of the Facility during a one hundred and eighty (180) day period after the date of SC. Contractor shall provide notice of the exercise of such right to Company in its certificate of SC and shall coordinate with Company the scheduling, nature and scope of the proposed plan of improvement of Facility performance and the performance of the Work. Company shall provide Contractor with reasonable access to the Facility for the purposes of such Work and retesting, provided that such Work and retesting shall be subject to the requirements of the EPC Agreement and shall not unreasonably adversely affect the Facility or its operations or the ability of Owner to perform its obligations under agreements with others. Contractor's plan and conduct of Work related thereto shall be subject to the prior consent of Company. The results of such Work shall be delivered to Company within the earlier of (i) five (5) days after completion of the Work or (ii) the end of the one hundred and eighty (180) day period (the “Cure Period Expiration Date”). Payment of LD’s for shortfall in performance shall be made to Company within (15) days of the Cure Period Expiration Date. |
| - Final Completion | Completion of the following minimum acceptance criteria will constitute Final Completion: - Substantial Completion has been achieved. - All Punch List Items have been completed. - Performance Guarantees have been achieved or payment of LDs, has been received by Company. - Completion of a (21) day Reliability Test (CFB)/(PC). - Delivery of final lien waivers. - Delivery of final as-builts and documentation. - The Contractor has left the Site free from waste materials or rubbish caused by it, or its Subcontractors activities. - Contractor has met all its obligations under the EPC Agreement, other than warranty. |
| - Schedule LD’s | Contractor shall pay Schedule LD’s for late achievement of the Guaranteed SC Date(s) at the rate of (0.6%) of the respective Unit Contract Price per week, (prorated for each day of delay) up to a cap of (15%) of the respective Unit Contract Price. Contractor shall make payment of Schedule LD’s upon the last day of each month Contractor is in delay of achieving SC. |
| - “Performance LD’s” | Performance LD’s shall be as follows: - Unit Electrical Output: (2%) of respective Unit Contract Price per (1%) less than Guarantee. - Unit Heat Rate: (1%)* of respective Unit Contract Price per (1%) greater than Guarantee. - Limestone Consumption Guarantee (CFB): $(TBD)/Btu/kWh. - Reliability: $(TBD)/percent. * May be modified on a project-by-project basis. |
| - LD’s Cap | - Schedule LD cap of (15%) of respective Unit Contract Price. - Performance LD cap for Net Capacity of (5%) of the respective Unit Contract Price. - Performance LD cap for Net Heat Rate of (5%) of the respective Unit Contract Price. - Aggregate LD cap for Net Capacity, Net Heat Rate, Limestome Consumption and Reliability of (15%) of the Unit Contract Price. - Aggregate LD cap: of (25%) of the Unit Contract Price. |
| - Liability Limitations | Contractors Total Aggregate Liability Cap for damages shall be: One hundred percent (100%) of the Contract Price excluding; (i) liability associated with third party personal injury and property damage caused by Contractor’s fault or negligence, (ii) Patent Infringement, (iii) proceeds of Project specific insurance, and (iv) liability arising from gross negligence or willful misconduct of Contractor, Subcontractors, or others Contractor is responsible for. |
| - Consequential Damages | Mutual waiver from consequential, incidental, special or indirect damages. |
| - Incentive Bonus | An incentive bonus for Heat Rate, Capacity and early SC may be agreed on a Project-by-Project basis. |
| - Indemnities | Contractor shall indemnify and hold harmless Company from: - Third party personal injury caused by its fault or negligence or that of its Subcontractors, or others Contractor is responsible for. - Third party property damage caused by its fault or negligence. - Patent Infringement. - Taxes that it is responsible for under the EPC Agreement. - Provided Contractor has acknowledged its obligation to indemnify Company regarding such claims and the defense and settlement thereof, Contractor shall have the right to defend and settle such claims. |
| - Warranty | Contractor warrants; (i) it will at all times be fully qualified and capable of performing the Work to complete the Facility according with the terms of the EPC Agreement and all Work shall be in accordance with the manufacturer or vendor’s warranty requirements, (ii) the design, engineering, construction and commissioning of the Facility has and will be; (a) carried out using skill, care and diligence expected of experienced professional engineers and constructors in the independent power production industry, (b) in accordance with good modern engineering principles and practices of a standard equivalent to similar US independent power projects and all codes and standards of the EPC Agreement, (iii) the Facility including Equipment and other items furnished by Contractor shall be new, of good quality, free from defects and shall conform with all applicable laws and governmental authorizations in effect at SC and, (iv) the operators training program prepared by Contractor shall comply with industry standards and applicable laws and will contain sufficient information and will be presented such that reasonably educated operations and maintenance personnel trained by Contractor under the training program are capable of adequately operating the Facility. The warranty shall extend for a period of eighteen (18) months from SC (“Warranty Period”) on all Work with eighteen (18) month rewarranty for any Work replaced or reworked during the Warranty Period. In addition, a latent defects warranty period commencing on the beginning of the nineteenth (19)month following SC and ending at the end of twenty four (24) months after SC (“Latent Defects Warranty Period”) shall apply to design defects within the Plant having a material effect on Plant performance with twelve (12) month rewarranty for any Work replaced or reworded during the Latent Defects Warranty Period, provided; (i) such defects were not reasonably discoverable before expiration of the Warranty Period, taking into account Contractor’s published inspection and maintenance procedures, and (ii) liability for resulting damage is excluded. Contractor shall repair or replace all Work, which does not conform to the foregoing warranty at its sole cost and expense and shall have full responsibility for all “in and out” efforts and cost associated with any warranty Work. The EPC Agreement will contain a provision that the warranties to be set forth in the EPC Agreement are exclusive and there are no other warranties either expressed or implied. In conjunction with Company, Contractor shall negotiate in good faith with vendors and suppliers to obtain extended Equipment warranties beyond the Warranty Period. Such extensions shall be for the benefit and to the account of Company. |
| - Title / Risk of Loss | Provisions for the passing of title shall be agreed on a Project-by-Project basis pending the Project specific tax profile. Notwithstanding the passing of title, Contractor shall maintain risk of loss for the Facility until SC. |
| - Exclusive Remedy | The Parties intend that their respective rights, obligations and liabilities as provided in the EPC Agreement shall be exhaustive of the rights, obligations and liabilities of each of them to the other arising out of, under or in connection with the EPC Agreement, whether such rights, obligations and liabilities arise in respect or in consequence of an indemnity or warranty or by reason of any breach of contract or of statutory duty or by reason of tort (including negligence and strict or absolute liability) or by reason of any other legal or equitable theory. Accordingly, the remedies expressly stated in the EPC Agreement for specific breaches of particular provisions thereof are intended to be and shall constitute the sole and exclusive remedies of the Parties to the exclusion of remedies for such breaches whether at law or equity or whether expressed or implied. |
| - Insurance | Contractor Provided Insurance: Commencing at NTP and until the expiration of the Latent Defects Warranty Period Contractor shall maintain insurance coverage’s of at least the following; Workers Compensation and Employer’s Liability Insurance; Statutory limits for Workers Compensation with a $2m per accident limit for Employer’s Liability, which shall include coverage for bodily injury by disease. Commercial or Comprehensive General Liability Insurance; As primary coverage, on an occurrence basis against third party personal injury and property damage claims, shall include; products-completed operations, blanket contractual, premises/operation, explosion, collapse and underground hazard coverage, broad form property damage, broad form contractual liability, personal injury, independent contractor liability, hostile fire liability and include a severability of interest or cross liability clause. The policy shall provide cover of $2m per occurrence. Automobile Liability Insurance; Covering claims for personal injury and death and property damage, $2m per occurrence. Excess Liability Insurance; Covering claims for personal injury or death and property damage in excess of Employers Liability, CGL and Auto Liability and shall provide cover equal to or better than the underlying policies. $8m per occurrence. All Contractor insurance (except workers comp and employer’s liability) shall include Owner, Company and Lenders as additional insured’s with respect to all claims arising out of the Work, except for those arising out of Owner, Company or Lender’s sole negligence. All Contractor policies shall include a waiver of subrogation in favor of Company, Owner, Lenders, assignees, affiliates agents, officers and employees. Deductibles for Contractor insurances shall be to the account of Contractor, unless and to the extent the claim is proximately caused by Company, agents or employees. Company Provided Insurance; Builders “All Risk” and Marine Cargo Insurance; Covering full insurable value of the Equipment and Facility, covering physical loss and damage. Deductibles shall not exceed reasonable, commercially available limits. Insurance shall (i) not include any coinsured provision, (ii) provide for increase cost of construction and loss to undamaged property resulting from enforcement of building laws, (iii) include cost for removal of debris, (iv) include cover for phased in operational exposures during construction and (v) provide DE 3 or LEG 2 exclusions at a minimum. Insurance shall cover Owner, Company, Lenders, Contractor and Subcontractors to the extent of their respective interest in the Work. Workers Compensation and Employer’s Liability; Commercial General Liability; Automobile Liability Insurance; Excess Liability Insurance; Deductibles of Builders All Risk prior to SC shall be to the Party having risk of loss. After SC, Contractor shall be responsible for deductibles on policies covering damage to the Facility for any claims while performing warranty Work or Punch List items unless and to the extent caused by Company. Such deductibles shall be agreed on a project-by-project basis at commercially availably levels being; (i) available in the market place at time of placement, (ii) reasonably priced in comparison to similar coverage’s on similar power projects and (iii) that no material technical issues exists with respect to performance of the equipment. |
| - Changes | Changes shall result in an adjustment to the time and/or cost or other affected provisions of the EPC Agreement. Changes shall include but not be limited to changes in law, suspension or termination for reasons not attributable to Contractor or those for which it is responsible for, delay or non-performance of Company deliverables or obligations, or as otherwise mutually agreed by the Parties. Changes shall be priced on an open book lump sum basis unless agreed otherwise. Contractor shall perform Company directed changes provided that; (i) for any change authorized by Company which is greater than (10%) of the Contract Price, Company shall represent to Contractor that it has sufficient funding for such change,or (ii) for any change authorized by Company which is greater than (25%) of the Contract Price, Contractor shall be provided written verification from Company’s third party financial advisor or Project lender confirming that funding in amounts adequate to cover the amount of such change is available to Company and (iii) notwithstanding any ongoing discussion to agree the cost and/or schedule impact of a Company directed change, Contractor shall proceed with such Work on a cost reimbursable basis pending resolution. |
| - Retention Bond | Contractor may post a retention bond or other security acceptable to Company and Lenders, in the amount of (200%) for Punch List. |
| - Force Majeure | Force Majeure events shall include events beyond the control of the affected Party but shall require such party to mitigate. The affected Party’s obligations shall be suspended for the period of time which directly results from a Force Majeure event and the schedule shall be extended. The Party affected by Force Majeure shall notify the other within five (5) business days of learning of the event and the Parties shall meet to discuss the event within ten (10) business days after receipt of such notice. The Parties shall continue to perform all duties unaffected by any Force Majeure. Force Majeure shall not excuse an obligation to pay monies due in accordance with the terms of the EPC Agreement.. |
| - Site Conditions and Hazardous Material | Contractor is responsible for (i) hazardous waste it, or its Subcontractors or other parties it is responsible for, brings to the Site and (ii) subsurface risk disclosed in exhibits, geological reports or otherwise prior to NTP, except for materially unusual or abnormal geotechnical or subsurface matters which it could not have reasonably foreseen based upon the available soils analysis or what a Party exercising prudent practices could not have reasonably foreseen. Company is responsible for existing hazardous waste and other subsurface conditions. |
| - Suspension | #### At any time/for any reason, Company may suspend the Work or part thereof. Upon notice, Contractor shall suspend, protect and secure the Work, as Company reasonably requires. Contractor shall maintain its staff and labor on or near the Site ready to proceed with the Work upon notice. Company at any time following a suspension may give notice to proceed and Contractor shall proceed with such Work. #### Contractor may suspend the Work for non-payment as set forth in Section 11 hereto. Upon payment by Company of overdue amount, Contractor shall proceed with the Work previously suspended. In the event of suspension, which is not due to Contractors default, Contractor shall be entitled to a Change Order for reimbursement, on a monthly basis, for its actual, direct, out-of-pocket costs plus Contractor’s personnel costs (verified to Company’s reasonable satisfaction) which are reasonably incurred by Contractor as a direct result of such suspension and any increase in cost or delays resulting from such suspension, plus a mark-up of three (3%) percent for Contractor’s overhead and profit and shall be entitled to an extension of Project Schedule in respect of any actual delay incurred by such suspension. |
| - Default and Termination | ## Contractor shall be in default and subject to termination; (i) if any bankruptcy or insolvency proceeding is not dismissed within sixty (60) days of filing, or (ii) for Contractor assignment for the benefit of its creditors or, if a receiver is appointed on account of insolvency, or (iii) if Contractor seeks to take advantage of any other applicable law relating to bankruptcy, insolvency, reorganization, winding up or composition, or adjustment of debts, or (iv) if Contractor admits in writing its inability to pay its debts when due, then Company may terminate effective immediately upon giving written notice. ### Contractor shall be subject to termination for; #### material representation or warranty being incorrect as of the date made; #### failure to make prompt payment of undisputed invoices due Subcontractors or otherwise is in default of a material obligation to any Subcontractor; #### failure to correct defective Work pursuant to the EPC Agreement; #### purported assignment of the EPC Agreement in violation with its terms; #### any security being repudiated or ceasing to be valid, binding, and enforceable or default under any security; #### disregard of laws or governmental authorizations and such action could impair Contractor’s ability to perform pursuant to the EPC Agreement or Contractor persistently disregards any laws or governmental authorizations; #### failing to pay Delay or Performance LD’s, or any other amounts payable by Contractor when due; #### failing to begin Work within (15) days of the Notice to Proceed; #### abandoning the construction of the Facility; #### failing to achieve SC of a Unit within (an agreed date / Project) days after the Guaranteed Substantial Completion Date(s); or #### failing to perform its material covenants or agreements in the EPC Agreement not otherwise specified above. Company may immediately terminate; (i) failures above which involve payment of money or posting Security unless cured within (15) days of notice, or (ii) for non-monetary failures above unless cured within (45) days after receipt of notice provided however, company in its sole discretion may allow Contractor additional time to cure defaults which are not cured within such (45) day period. The (45) day cure period shall be extended to the extent the Parties agree in writing that the default is not curable within (45) days. During any such extended cure period, Company may immediately terminate if Contractor fails to continue all efforts with vigor and due diligence to cure the default. If terminated Company; (i) may employ a replacement contractor to finish the Work, (ii) shall be required to reasonably mitigate the cost. The EPC Agreement will contain provisions for Contractors obligations and actions upon termination. Upon termination, no further payments will be made to Contractor except for Work performed in accordance with the EPC Agreement prior to termination and Company shall determine the expenses incurred in connection with termination and completion of the Work, (“Cost to Complete”). If the Cost to Complete exceeds the balance of Contract Price (“Balance of CP”) unpaid at time of default, Company is not required to pay Balance of CP, and Contractor shall pay the amount of such excess, subject to Contractor’s limitation of liability. Such amount may be deducted from amounts due Contractor. If Cost to Complete is less than Balance of CP, Contractor shall be due (i) any unpaid portion of the Contract Price attributable to Work executed prior to termination, (ii) the value of excess materials on the Site furnished by Contractor and taken over by Company and have not already been paid for as part of the Contract Price, and (iii) the costs, if any, incurred by Contractor in protecting the Work pursuant to directions of Company (collectively, the “Termination Amount”) subject to limitation that Termination Amount shall not exceed the amount by which the Balance of the Contract Price is greater than the Cost to Complete. Contractor shall not be liable for the Replacement Contractor’s failure to perform. #### Company may cancel for convenience at any time by notice and Contractor’s sole remedy will be: after NTP Effective Date, (i) reimbursement for actual costs incurred by Contractor attributable to the Work and properly performed as of the effective date of cancellation, (ii) reimbursement for reasonable Subcontractor termination costs; and (iii) any other out-of-pocket expenses reasonably incurred by Contractor as a result of such cancellation which, could not reasonably be avoided and are a direct result of such termination (collectively “Termination Expenses”). In such case Contractor shall be entitled to receive; (x) the Termination Expenses plus (y) four percent (4%) of the Termination Expenses. Contractor shall use reasonable efforts to minimize Termination Expenses and all other costs of cancellation. Payment for cancellation shall be due within (30) days of Company’s receipt and acceptance of a substantiated, itemized invoice and the receipt of requested Work. ## Company shall be considered in default and subject to termination; (i) if any bankruptcy or insolvency proceeding is not dismissed within sixty (60) days of filing, or (ii) for Company assignment for the benefit of its creditors, if a receiver is appointed on account of insolvency, or (iii) if Company seeks to take advantage of any other applicable law relating to bankruptcy, insolvency, reorganization, winding up or composition, or adjustment of debts, or (iv) if Company admits in writing its inability to pay its debts when due, then Company may terminate effective immediately upon giving written notice. Any such termination shall be without prejudice to any existing rights, powers, or remedies of either Party under the EPC Agreement. ### Company shall be subject to termination for: #### failing to pay Contractor undisputed amounts pursuant to Section 11 hereto; #### failing to observe or perform its material covenants or agreements contained in the EPC Agreement; #### suspending the Work for more than eight (8) consecutive months or (12) months total; or #### a material representation or warranty of Company being incorrect as of the date made, Contractor may immediately terminate for failures above unless cured (45) days after receipt of Contractor’s notice of intent to terminate (unless noted otherwise herein); provided that before any terminate may be exercised, Contractor shall provide at least (30) days written notice to Lender setting forth the circumstances of Company’s default. Contractor shall have no right to terminate if Lender cures the default within such thirty (30) day period. Contractor shall be entitled to payment on the same basis as cancellation for Company convenience, provided that in no event will the aggregate sum of all payments received by Contractor exceed the Contract Price. |
| - Confidentiality | The EPC Agreement will contain confidentiality provisions similar to the CSA. |
| - Assignment of EPC Agreement | Company shall be free to assign the EPC Agreement, either prior to or after NTP to an affiliate. Company shall be free to assign the EPC Agreement, either prior to or after NPT to a non-affilliate provided Contractor has received written verification from Company’s or assignees financial advisor or Project lender confirming that funding in amounts adequate to cover the Contract Price is available to assignee. |
| - Contractors Representations and Warrants | Contractor shall represent and warrant that: (a) the Work and all Equipment, materials, supplies, etc., shall not infringe the intellectual property rights of any person, (b) good title free and clear of liens when transferred to Company, (c) it is a company in good corporate standing, (d) that it is not in violation of any law that would affect the performance of its obligations under the EPC Agreement, (e) it has all governmental authorizations required to perform the Work, (f) by executing the EPC Agreement it will not be in breach of any other agreement, (g) the EPC Agreement has been validily executed and delivered by it and is binding and enforceable in accordance with its terms, (h) it has; (1) the proper qualifications to perform the Work, (2) examined the EPC Agreement, (3) thoroughly investigated the site, (4) ascertained the location and character of the Work and other general and locations conditions and laws required to complete the Work, and (5) performed and examined results of testing as normally required to be conducted by a contractor entering into such an agreement. |
| - Company’s Representations and Warrants | Company shall represent and warrant that: (a) it is a company in good corporate standing, (b) that it is not in violation of any law that would affect the performance of its obligations under the EPC Agreement, (c) it has all governmental authorizations required to perform the Work, (d) by executing the EPC Agreement it will not be in breach of any other agreement and (e) the EPC Agreement has been validily executed and delivered by it and is binding and enforceable in accordance with its terms. |
| - Governing Law | For Projects inside the state of Texas, Texas law (with references to the Texas Deceptive Trade Practices Act excluded) shall govern. For Projects outside the state of Texas, New York law shall govern. . |
| - Dispute Resolution | - Mandatory senior executive, special meeting. - Arbitration, under AAA rules, three Arbitrators. - Optional Fast Track Arbitration, if mutually agreed between parties. - For Projects located inside the state of Texas, the location of arbitration shall be Texas. For Projects located outside the state of Texas, the location of arbitration shall be New York, New York. - Arbitrators shall be bound by the terms and conditions of the EPC Agreement in fashioning their award or remedy. |
| - General Provisions / Exhibits | The EPC Agreement shall include other standard and typical general provisions, e.g.; safety, entire agreement, language, amendments, severability, no waivers, heading, successors and assigns, independent contractor, further assurances, priority of documents, drawings/review/as builts and approval, labor relations, compliance with laws, survival, inspections/audits, liens/waivers, cooperation with other Company contractors on site, testing/commissioning and lenders rights. It shall also include certain standard and typical exhibits e.g.; Project Schedule, Scope of Work and Specifications, Project Document Requirements, Contract Price, Progress Payments, Liquidated Damages, Form of Invoice, Taxes and Fees, Form of Lien Waiver (invoice), Form of Lien Waivers (final release), Guarantees, Basis Conditions, Testing Guidelines, Change Order Pricing, Contractor Insurance Company Insurance, Site Location Map, Sample Substantial Completion Certificate, Sample Final Completion Certificate, Governmental Authorizations, Key Subcontractors (AVL) , Company Scope of Supply For Utilities and Interconnections, Operation and Maintenance Training, Contents Of Job Books, Documents for Review, List Of Key Personnel and Form of Contractor’s Parent Company Guarantee. |

EXHIBIT D

REQUIREMENTS FOR PROVISION OF OPEN BOOK LSTK PRICE

(ARTICLE 2.4 (c) and (d))

This Exhibit constitutes the definition of “Open Book Estimate”

Due to the exclusive positions of both Parties with regard to negotiating EPC Contract(s) for Conceptual Projects and the resultant absence of bidding competition, the general intent of the open book estimate concept is for the Consultant to fully disclose to and review with Company detailed information concerning Consultant’s pricing estimates and components used to develop and confirm the LSTK Price.

The Company recognizes Consultant’s concern for disclosing certain commercially sensitive estimating and pricing information that might be utilized by Consultant for competitively bid projects, however, in consideration for the right to negotiate exclusively with Company during the Exclusivity Period for each Conceptual Project, and Company’s confidentiality obligations contained in Article 3.5, and in recognition of Company’s need to verify that a fair and reasonable price would be paid for the Work, Consultant hereby agrees that it will; prepare, review, disclose and provide to Company, for its review, and alter if necessary in accordance with this Exhibit D,  such detailed pricing information to Company.

Therefore, for purposes of fulfilling the open book cost estimate requirements, the following principles shall apply;

The estimate will be prepared to reflect "Cost" in all areas of the estimate. The purpose of the Open Book concept is to allow both parties to review and agree to all areas of the estimate for the purpose of review, comment, discussion and alteration of the estimate if appropriate. The following Estimate data shall be made available:

- Provide a detailed "Basis of Estimate" that defines how the estimate was developed and most importantly the assumptions & exclusions in the estimate.

- Provide Indirect Construction Costs and detailed information such as Time-Phased Staffing Plans, Time-Phased Construction Equipment Schedules to be provided and reviewed. Temporary Facilities to be estimated based on a Construction Plan and estimates for such things as small tools will be agreed upon based on $/Craft Man-hour.

- Provide in writing all material costs components (i.e. the cost/CY of concrete and the justification of such rate, including price quotes.  It is understood that in most cases three price quotations (or more) will be received for such estimated costs.  However, in some cases such cost may be established from a master supply agreement Consultant may have with a supplier or from Consultant’s own history and “similar to” records.  In such instances, Consultant shall review and justify the basis and composition of such cost composition with Consultant..  Such provisions shall also apply to equipment costs in item 4 and subcontractor costs for item 5 below.

- Provide copies of equipment price quotations for each piece of equipment (based on a minimum of three quotations each). If telephone quote was used, provide written backup (vendor, date, equipment data and price).

- Provide copies of subcontractor price quotations for each subcontract (based on a minimum of three quotations each). If telephone quote was used, provide written backup (subcontractor, scope of work, date and price).

- For equipment manufactured by Consultant, Consultant shall provide evidence of cost for completed product.  If such equipment is comprised of one or more major units that are commercially available from third parties, the cost shall be evidenced to the unit level.

- Provide and justify how all bulk quantities were developed.

- Provide craft wage rate buildup by craft that will include as appropriate; Base Wage Rate, Fringe Benefits, Ins/Taxes and any planned overtime. These rates shall also include any per diem anticipated. Consultant shall provide Company a copy and review of its area/project Craft Labor Surveys.

- Provide craft productivity calculations used in the estimate. The estimate should be prepared based on US Gulf Coast Productivity (or other recognizes productivity standard) and if required a productivity adjustment (by craft) will be applied.

- Provide Unit man-hours for all components in the estimate (i.e. Concrete [by type of concrete], Steel [by size of framing and type of item, grating, handrail, stair framing, checkered plate, etc], Pipe [by size range and material 6"-8" CS], etc.).

- Provide Engineering & Engineering Related Estimate to be supported by a time-phased discipline manpower estimate and associated scope of work. The pricing should be broken down to provide the labor rates and cost components including expenses and overhead. The fee for engineering services should be included in Project Fee.

- Provide Home Office Project Management Estimate to be supported by a time-phased manpower estimate and associated scope of work. The pricing should be broken down to provide the labor rates and cost components including expenses and overhead.  The fee for Home Office Project Management services should be included in Project Fee.

- Contingency and fee shall be applied as per item 16 below.

- Company’s project personnel will visit Consultants offices during the estimate preparation to review methodology, progress, format and basis and Consultant shall make available one or more of Consultant’s employees who are knowledgeable of Consultant’s current estimating practices and responsible for development of the information provided to Company under this Exhibit D, for the purpose of reviewing and answering Company’s questions concerning, such information.  Company may elect to have such meetings and reviews in its Houston offices.

- The estimate will be provided in a format substantially similar to the following;

| Project: Location: |  |  |  |  |  |  |  |  |  |  |  | Date: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Material |  | Labor |  |  |  | Other / Subcontract |  |  |
|  | Item / Description | Qty | UM | U.P. | Total | Unit MH | Total MH | Hrly Rate | Total | U.P. | Total | Total |
| ITEM NO | COST SUMMARY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | SITE PREPARATION, SITEWORK |  |  |  |  |  |  |  |  |  |  |  |
|  | REMOTE SITE LAYDOWN, STAGING & PARKING |  | LS | $ - | $ - | - | - | $ - | $ - | $ - | $ - | $ - |
|  | SITE PREPARATION |  | AC | - | - | - | - | - | - | - | - | - |
|  | EXCAVATION - (Include Pricing with Concrete) |  |  | - | - | - | - | - | - | - | - | - |
|  | PILING |  | LF | - | - | - | - | - | - | - | - | - |
|  | Total Site Preparation, Sitework | 1 | LS |  | $ - |  | - |  | $ - |  | $ - | $ - |
| 2 | CONCRETE |  |  |  |  |  |  |  |  |  |  |  |
|  | CONCRETE | - | CY | - | - | - | - | - | - | - | - | - |
|  | Foundations & Slabs (< 3 CY) |  | CY |  |  |  |  |  |  |  |  |  |
|  | Foundations & Slabs (3 to 50 CY) |  | CY |  |  |  |  |  |  |  |  |  |
|  | Foundations & Slabs (> 50 CY) |  | CY |  |  |  |  |  |  |  |  |  |
|  | Grout |  | CF |  |  |  |  |  |  |  |  |  |
|  | Total Concrete | 1 | LS |  | $ - |  | - |  | $ - |  | $ - | $ - |
| 3 | STRUCTURAL & MISCELLANEOUS STEEL |  |  |  |  |  |  |  |  |  |  |  |
|  | STRUCTURAL STEEL |  | TN | - | - | - | - | - | - | - | - | - |
|  | MISCELLANEOUS STEEL |  | LS | - | - | - | - | - | - | - | - | - |
|  | HRSG BLDG STEEL FRAME (Erection Only) |  | TN | - | - | - | - | - | - | - | - | - |
|  | CHILLER SUPPORT STEEL |  | TN | - | - | - | - | - | - | - | - | - |
|  | Total Structural & Miscellaneous Steel | 1 | LS |  | $ - |  | - |  | $ - |  | $ - | $ - |
| 4 | BUILDINGS & ARCHITECTURAL |  |  |  |  |  |  |  |  |  |  |  |
|  | ROOFING |  | SF | - | - | - | - | - | - | - | - | - |
|  | SIDING |  | SF | - | - | - | - | - | - | - | - | - |
|  | HRSG BUILDING |  |  | - | - | - | - | - | - | - | - | - |
|  | CTG BUILDING |  |  | - | - | - | - | - | - | - | - | - |
|  | CTG/HRSG BLDG SOUND SUPPRESSION |  | LS | - | - | - | - | - | - | - | - | - |
|  | DECK OVER HRSG WAREHOUSE |  | SF | - | - | - | - | - | - | - | - | - |
|  | CONCRETE MASONRY UNITS |  | LS | - | - | - | - | - | - | - | - | - |
|  | HRSG BUILDING VENTILATION (15 FANS) |  | EA | - | - | - | - | - | - | - | - | - |
|  | MISCELLANEOUS BUILDINGS |  | SF | - | - | - | - | - | - | - | - | - |
|  | Total Buildings & Architectural |  |  |  | $ - |  | - |  | $ - |  | $ - | $ - |
| 5 | MECHANICAL EQUIPMENT |  |  |  |  |  |  |  |  |  |  |  |
|  | MAJOR EQUIPMENT |  |  |  |  |  |  |  |  |  |  |  |
|  | CTG |  | EA |  | - |  |  | - |  |  |  |  |
|  |  |  |  | - |  | - | - |  | - | - | - | - |
|  | CTG - Generator Upgrade to 200 MW |  | LS | - | - | - | - | - |  | - | - | - |
|  | HRSG |  | EA | - | - | - | - | - | - | - | - | - |
|  | HRSG - Additional 200 Tns Bldg Steel |  | TN | - | - | - | - | - | - | - | - | - |
|  | HRSG - Increase in NOX Catalyst |  | LS | - | - | - | - | - | - | - | - | - |
|  | GSU |  | EA | - | - | - | - | - | - | - | - | - |
|  | BOP EQUIPMENT - PLANT |  |  |  |  |  | - |  |  |  |  |  |
|  | CTG Cooling Coil & Inlet Air Filter |  | EA | - | - | - | - | - | - | - | - | - |
|  | Inlet Fogging |  | EA | - | - | - | - | - | - | - | - | - |
|  | CTG Overhead Crane |  | EA | - | - | - | - | - | - | - | - | - |
|  | HP BFP |  | EA | - | - | - | - | - | - | - | - | - |
|  | HRSG Blowdown Sump Pump |  | EA | - | - | - | - | - | - | - | - | - |
|  | BFW Heater - HRSG Supply |  | EA | - | - | - | - | - | - | - | - | - |
|  | FG Heater - HRSG Supply |  | EA | - | - | - | - | - | - | - | - | - |
|  | Phosphate/Amine/Anti-Oxidant Injection Units |  | EA | - | - | - | - | - | - | - | - | - |
|  | Compressor Blade Washing Unit |  | EA | - | - | - | - | - | - | - | - | - |
|  | FO Drain/Wash Water/HRSG Blowdown Sumps |  | EA | - | - | - | - | - | - | - | - | - |
|  | HRSG Supplied Equipment |  | LS | - | - | - | - | - | - | - | - | - |
|  | CO Cataylst |  | LS | - | - | - | - | - | - | - | - | - |
|  | BOP EQUIPMENT - UTILITY AREA |  |  |  |  |  |  |  |  |  |  |  |
|  | Cooling Tower |  | EA | - | - | - | - | - | - | - | - | - |
|  | No. 7 Turbine Condensate Pumps |  | EA | - | - | - | - | - | - | - | - | - |
|  | No. 8 Turbine Condensate Pumps |  | EA | - | - | - | - | - | - | - | - | - |
|  | FO Unloading/Forwarding Pumps |  | EA | - | - | - | - | - | - | - | - | - |
|  | Demin Water Supply Pumps |  | EA | - | - | - | - | - | - | - | - | - |
|  | Cooling Water Pumps |  | EA | - | - | - | - | - | - | - | - | - |
|  | Condensate Holding Tank |  | EA | - | - | - | - | - | - | - | - | - |
|  | Condensate Pumps |  | EA | - | - | - | - | - | - | - | - | - |
|  | Demin Water Storage Tank |  | EA | - | - | - | - | - | - | - | - | - |
|  | Cooling Water Treatment Unit |  | EA | - | - | - | - | - | - | - | - | - |
|  | Ammonia Generation Unit |  | EA | - | - | - | - | - | - | - | - | - |
|  | Chilled Water Unit |  | EA | - | - | - | - | - | - | - | - | - |
|  | No. 7 Surface Condenser Nozzle |  | EA | - | - | - | - | - | - | - | - | - |
|  | No. 8 Surface Condenser Nozzle |  | EA | - | - | - | - | - | - | - | - | - |
|  | Revenue Steam Meter |  | EA | - | - | - | - | - | - | - | - | - |
|  | Dump Condenser |  | EA | - | - | - | - | - | - | - | - | - |
|  | Condensate Return Pumps @ Dump Condenser |  | EA | - | - | - | - | - | - | - | - | - |
|  | EQUIPMENT BUY-DOWN |  | LS | - | - | - | - | - | - | - | - | - |
|  | Total Mechanical equipment | 1 | LS |  | $ - |  | - |  | $ - |  | $ - | $ - |
| 6 | MECHANICAL PIPING SYSTEMS |  |  |  |  |  |  |  |  |  |  |  |
|  | U/G PIPING (Includes Excavation & Backfill) |  | LF | - | - | - | - | - | - | - | - | - |
|  | A/G PIPING - PLANT AREA |  | LF | - | - | - | - | - | - | - | - | - |
|  | A/G PIPING - UTILITY AREA |  | LF | - | - | - | - | - | - | - | - | - |
|  | HRSG PIPING (with HRSG Erection) |  | LF |  |  |  |  |  |  |  |  |  |
|  | CTG PIPING (with CTG Erection) |  | LF |  |  |  |  |  |  |  |  |  |
|  | Total Mechanical Piping Systems | - | LF |  | $ - |  | - |  | $ - |  | $ - | $ - |
| 7 | INSULATION & FIREPROOFING |  |  |  |  |  |  |  |  |  |  |  |
|  | Pipe Insulation - PLANT AREA |  | LF | - | - | - | - | - | - | - | - | - |
|  | Pipe Insulation - UTILITY AREA |  | LF | - | - | - | - | - | - | - | - | - |
|  | EQUIPMENT INSULATION - HRSG |  | SF | - | - | - | - | - | - | - | - | - |
|  | EQUIPMENT INSULATION - CTG |  | LS | - | - | - | - | - | - | - | - | - |
|  | Total Insulation | 1 | LS |  | $ - |  | - |  | $ - |  | $ - | $ - |
| 8 | ELECTRICAL - CONSTRUCTION BULKS |  |  |  |  |  |  |  |  |  |  |  |
|  | T-LINE |  | LS | - | - | - | - | - | - | - | - | - |
|  | PLANT AREA |  |  |  |  |  |  |  |  |  |  |  |
|  | U/G Conduit |  | LF | - | - | - | - | - | - | - | - | - |
|  | A/G Conduit |  | LF | - | - | - | - | - | - | - | - | - |
|  | Cable Tray & Fittings |  | LF | - | - | - | - | - | - | - | - | - |
|  | Wire & Cable (P&C) |  | LF | - | - | - | - | - | - | - | - | - |
|  | Grounding |  | LS | - | - | - | - | - | - | - | - | - |
|  | Miscellaneous |  | LS | - | - | - | - | - | - | - | - | - |
|  | BFW Pump Motors w/Breaker |  | EA | - | - | - | - | - | - | - | - | - |
|  | Aux Transformer/Breaker (4160 SWGR) |  | EA | - | - | - | - | - | - | - | - | - |
|  | CTG Starting Motor (2250 HP 4160 KV) |  | EA | - | - | - | - | - | - | - | - | - |
|  | Main FO Pump Motor (275 HP) |  | EA | - | - | - | - | - | - | - | - | - |
|  | Electrical Equipment |  | LS | - | - | - | - | - | - | - | - | - |
|  | Buss Duct |  |  |  |  |  |  |  |  |  |  |  |
|  | Transformers - Dry |  |  |  |  |  |  |  |  |  |  |  |
|  | MCC |  |  |  |  |  |  |  |  |  |  |  |
|  | UPS System |  |  |  |  |  |  |  |  |  |  |  |
|  | UTILITY AREA |  |  |  |  |  |  |  |  |  |  |  |
|  | U/G Conduit & Duct Bank |  | LF | - | - | - | - | - | - | - | - | - |
|  | A/G Conduit |  | LF | - | - | - | - | - | - | - | - | - |
|  | Cable Tray & Fittings |  | LF | - | - | - | - | - | - | - | - | - |
|  | Wire & Cable (P&C) |  | LF | - | - | - | - | - | - | - | - | - |
|  | Grounding |  | LS | - | - | - | - | - | - | - | - | - |
|  | Miscellaneous |  | LS | - | - | - | - | - | - | - | - | - |
|  | Electrical Equipment |  | LS | - | - | - | - | - | - | - | - | - |
|  | Transformers - Dry |  |  |  |  |  |  |  |  |  |  |  |
|  | MCC |  |  |  |  |  |  |  |  |  |  |  |
|  | Total Electrical | 1 | LS |  | $ - |  | - |  | $ - |  | $ - | $ - |
| 9 | INSTRUMENTATION |  |  |  |  |  |  |  |  |  |  |  |
|  | Field Mounted Instruments |  | EA | - | - | - | - | - | - | - | - | - |
|  | Inline Devices |  | EA | - | - | - | - | - | - | - | - | - |
|  | DCS System |  | LS | - | - | - | - | - | - | - | - | - |
|  | Analytical Instrumentation |  | EA | - | - | - | - | - | - | - | - | - |
|  | Instrumentation Bulks |  | LS | - | - | - | - | - | - | - | - | - |
|  | Total Instrumentation | 1 | LS |  | $ - |  | - |  | $ - |  | $ - | $ - |
| 10 | MISCELLANEOUS |  |  |  |  |  |  |  |  |  |  |  |
|  | PAINTING |  | LS | - | - | - | - | - | - | - | - | - |
|  | PAVING & PATHWAYS |  | SF | - | - | - | - | - | - | - | - | - |
|  | Concrete Paying |  | SF |  |  |  |  |  |  |  |  |  |
|  | Asphalt Paving |  | SF |  |  |  |  |  |  |  |  |  |
|  | Brick Pathway |  | SF |  |  |  |  |  |  |  |  |  |
|  | Total Miscellaneous | 1 | LS |  | $ - |  | - |  | $ - |  | $ - | $ - |
| 11 | NOISE ABATEMENT |  |  |  |  |  |  |  |  |  |  |  |
|  | HRSG/EQUIPMENT SOUND SUPPRESSION |  | SF | - | - | - | - | - | - | - | - | - |
|  | Total Noise Abatement | 1 | LS |  | $ - |  | - |  | $ - |  | $ - | $ - |
|  | PRODUCTIVITY ADJUSTMENT |  | % | - | - | - | - | - | - | - | - | - |
|  | Subtotal - Direct Costs | 1 | LS |  | $ - |  | - |  | $ - |  | $ - | $ - |
|  | Freight | 1 | LS | - | - | - | - | - | - | - | - | - |
|  | Subtotal - Freight | 1 | LS |  | - |  |  |  |  |  |  | - |
|  | Escalation | 1 | LS | 0% | - | 0% | - |  | - | 0% | - | - |
|  | Subtotal - Escalation |  | LS |  | - |  | - |  | - |  | - | - |
|  | TOTAL - DIRECT COSTS |  | LS |  | - |  | - |  | - |  | - | - |
| INDIRECT / OVERHEAD COSTS |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Engineering (Incl Laser Surv, Arch & Conslts) |  | HRS |  |  |  |  |  |  |  |  | - |
|  | Start-up |  | LS |  |  |  |  |  |  |  |  | - |
|  | Heavy Haul ( CGT/HRSG/GSU ) |  | LS |  |  |  |  |  |  |  |  | - |
|  | Heavy Lift Cranes (Const Equipt) |  | LS |  |  |  |  |  |  |  |  | - |
|  | Field Indirects |  | LS |  |  |  |  |  |  |  |  | - |
|  | Const Support |  | LS |  |  |  |  |  |  |  |  | - |
|  | Vendor Reps |  | LS |  |  |  |  |  |  |  |  | - |
|  | Contractor's All Risk Insurance |  | LS |  |  |  |  |  |  |  |  | - |
|  | Taxes |  | LS |  |  |  |  |  |  |  |  | - |
|  | TOTAL - INDIRECT / OVERHEAD COST |  | LS |  |  |  |  |  |  |  |  | - |
|  | Design Devl Allow (Excl CTG,HRSG & GSU) |  | % |  |  |  |  |  |  |  |  |  |
|  | Contingency |  | % |  |  |  |  |  |  |  |  |  |
|  | Fee |  | % |  |  |  |  |  |  |  |  |  |
|  | TOTAL ESTIMATED PROJECT COST |  | LS |  |  |  |  |  |  |  |  | $ - |

15.	Provide copies of estimates, quotes, calculations, and other supporting documentation requested by Company and necessary to reasonably evidence composition of the estimated prices.

16.	The following rates have been agreed by Company and Consultant and shall be used in the composition of the LSTK Price.

|  | < 250MW | 251 – 450MW | 451 – 600MW | > 600MW |
| --- | --- | --- | --- | --- |
| Corp. Overhead | (1) | (1) | (1) | (1) |
| Contingency | (1) | (1) | (1) | (1) |
| Fee / Profit | 8% | 7% | 6% | 6% |

Note (1) To be reviewed and agreed on a project-by-project basis.

Target Pricing shall remain valid for any Conceptual Project for which Company issues a Notification Letter prior to the expiration of the subject Validity Period indicated above, notwithstanding the expiration of the said Validity Period prior to the provision of an OOM by Consultant, pursuant to Article 2.4(c).