CHANGE ORDER #3

To

PURCHASE CONTRACT ENA-2-99

By and Between

WESTDEUTSCHE LANDESBANK GIROZENTRALE, NEW YORK BRANCH

ACTING THROUGH ITS AGENT

ENRON NORTH AMERICA CORP.

AND

GE PACKAGED POWER, INC.

For The Purchase Of

24 LM6000 GAS TURBINE GENERATOR SETS

THIS CHANGE ORDER #3 TO PURCHASE CONTRACT ENA-2-99 (this "Amendment") is entered into effective as of September ___, 2000, by and between GE PACKAGED POWER, INC. (“GE”) and ENRON NORTH AMERICA CORP. (“Enron”), as agent for WESTDEUTSCHE LANDESBANK GIROZENTRALE, NEW YORK BRANCH (together with its successors and permitted assigns, “Purchaser”).

WHEREAS, GE, Enron and Purchaser entered into that certain Agreement dated [May 12, 2000] (the “Agreement”); and

WHEREAS, GE and Enron have mutually agreed to amend the Agreement to change certain scheduling dates and milestone payment terms.

NOW THEREFORE, in consideration of the mutual promises contained herein, and other good and valuable consideration, the receipt and sufficiency of which are hereby acknowledged, the parties agree as follows:

- The Guaranteed Unit Delivery Dates described in Section 10.2.1 of the Agreement for the Units described below are hereby revised as follows:

| Unit # | Original Guaranteed Unit Delivery Date | New Guaranteed Unit Delivery Date |
| --- | --- | --- |
| 19 | February 28, 2001 | July 30, 2001 |
| 20 | February 28, 2001 | July 30, 2001 |
| 23 | April 30, 2001 | July 30, 2001 |
| 24 | April 30, 2001 | August 15, 2001 |

- The following Milestone Payments described in Section 6.1.2 of the Agreement are hereby revised as follows:

| Milestone Payment # | Payment Date | Milestone | % of Purchase Amount |
| --- | --- | --- | --- |
| 10 | February 15, 2001 | Units, 21 and 22 in production, Units 16, 17 & 18 and all related Major Components Ready to Ship Ex-Works | 0% |
| 10A | May 15, 2001 | Units 19, 20, 23 & 24 in production, Units 21 & 22 and all related Major Components Ready to Ship Ex-Works by March 30, 2001 | 5% |
| 11 | July 30, 2001 | Units 19 and 20 and all related Major Components Ready to Ship Ex-Works | 5% |
| 12 | August 15, 2001 | Unit 23 & 24 and all related Major Components Ready to Ship Ex-Works | 5% |

- Except as modified in this Amendment, all other terms and conditions of the Agreement remain unchanged and in full force and effect.

IN WITNESS WHEREOF, the undersigned have executed this Amendment effective as of the date first above written.

Enron North America Corp., as Agent

By:

Michael J. Miller

Title:		Vice President

Date:

and

GE Packaged Power, Inc., as Seller

By:

Title:

Date: