ANTELOPE VALLEY ENERGY FACILITY, L.L.C. -

SOUTHERN CALIFORNIA EDISON COMPANY

GENERATION TIE-LINE

# STUDY AGREEMENT

1.	Summary: Antelope Valley Energy Facility, L.L.C. (“AVEF”) applied to Southern California Edison Company (“SCE”) for interconnection of 1006 MW of capacity at SCE’s Vincent Substation under the terms of the Transmission Owner (“TO”) Tariff.  AVEF proposes to interconnect at Vincent Substation and transmit Energy and/or Ancillary Services to the California Independent System Operator (“ISO”).  Notwithstanding AVEF’s TO Tariff application, AVEF has requested that SCE provide AVEF a cost estimate for SCE to engineer, design, construct and own the 230 kV generation tie-line between AVEF’s proposed Antelope Valley Project and the point of interconnection to the ISO Controlled Grid at SCE’s Vincent Substation.  Therefore, SCE and AVEF wish to enter into this Generation Tie-Line Study Agreement (“Agreement”) providing the terms for SCE to perform a Generation Tie-Line Study (“Study”) to determine the right-of-way requirements, transmission facilities, substation facilities, and appurtenant equipment necessary to construct a generation tie-line between the proposed Antelope Valley Project and SCE’s Vincent Substation.  This agreement does not create any obligations by either SCE or AVEF to proceed with SCE’s engineering, design, construction and ownership of such generation tie-line.

2.	Definitions:  All terms with initial capitalization not otherwise defined herein shall have the meanings assigned to them in the TO Tariff.

- Scope:  SCE will determine the right-of-way requirements, transmission facilities, substation facilities, and appurtenant equipment necessary for SCE to construct and own a new 230 kV generation tie-line between AVEF’s proposed Antelope Valley Project and the ISO Controlled Grid at SCE’s Vincent Substation.  The interconnection facilities required to terminate the new generation tie-line at Vincent Substation will not be determined pursuant to this Agreement.  Such facilities shall be determined pursuant to a separate TO Tariff Facilities Study Agreement.

- Content:  The Study will include an estimate of (i) the cost of the required right-of-ways (including AVEF’s allocation of required existing SCE right-of-ways), transmission facilities, substation facilities, and appurtenant equipment to be charged to AVEF, and (ii) the time required to complete construction of the required facilities.  The Study will include a list of major equipment required.  The cost estimate will include an estimate of the one-time payment (including the capital cost of the right-of-ways and facilities, associated ITCC, and expenses not capitalized) which are required to be paid in advance by AVEF in accordance with a payment schedule prior to completion of construction.

- Assumptions:  The assumptions utilized in performing the Study shall be as follows:

- The point of interconnection to the ISO Controlled Grid shall be SCE’s Vincent Substation @ a nominal 230 kV.

- The Antelope Valley Project will be located approximately five miles east of the city of Mohave, California, and one mile south of Highway 58.

- The 230 kV generation tie-line between the Antelope Valley Project and SCE’s Vincent Substation is assumed to be single circuit, 2-bundled 1780 ACSR conductor, and have an approximate length of fifty-five miles.  The Vincent end of the generation tie-line shall terminate at, and shall include, the dead end structure within SCE’s Vincent Substation.  The Antelope Valley Project end of the generation tie-line shall terminate at, and shall include, the line position and 230 kV circuit breaker at the Antelope Valley Project switchyard.

- The generation tie-line will be capable of transmitting a minimum of 1006 MW under normal operating conditions.

- An estimated operating date of April 1, 2004 (as requested by AVEF), until Study results, permitting requirements, design, land issues and material lead times are known, so that an actual determination can be made.

- AVEF will install, own, operate and maintain all ISO metering equipment.  All ISO metering equipment will be located on AVEF’s side of the point of interconnection.

6.	Time Required for Completion:  SCE will use due diligence to complete the Study within sixty (60) calendar days following receipt of a fully executed copy of this Agreement and payment pursuant to Section 12 of this Agreement.

7.	Additional Time for Completion:  At any time that SCE determines that the Study cannot be completed within sixty (60) calendar days in accordance with Section 6 of this Agreement, SCE shall notify AVEF and provide an estimated completion date, along with an explanation of the reasons why additional time is required to complete the Study.

8.	Exchange of Information:  SCE and AVEF shall confer with one another as necessary to exchange information that will provide for the most accurate analysis possible with the information available at the time the Study is performed.

9.	Third Party Review:  SCE will not provide for review of the Study by the ISO, Western Systems Coordinating Council, or any transmission owner potentially impacted by the proposed generation tie-line.

10.	Results Based on Information Available at Time of Study:  Substantial portions of technical data and assumptions used to perform the Study, including, by way of example and without limitation, system conditions and unit modeling may change after SCE provides the Study results to AVEF.  Study results will reflect available data at the time SCE provides the Study to AVEF.  Additionally, Study results will reflect the ISO Tariff, rules and protocols in effect at the time SCE provides the Study to AVEF.  Such Tariff, rules and protocols are subject to change.  SCE shall not be responsible for any additional costs (including without limitation, costs of new or additional facilities, system upgrades, or schedule changes) that may be incurred by AVEF as a result of changes in such data or the ISO Tariff, rules and protocols which occur following provision of this Study.

11.	 New Study at AVEF’s Costs:  In the event that AVEF and SCE determines that a new Study or revision of the Study is required (a) as a result of information received from the ISO, Western Systems Coordinating Council, or any transmission owner regarding any potential impact to a third party's electrical system, or (b) to reflect changes which occur following provision of this Study, then AVEF shall either enter into a separate agreement providing that it shall reimburse SCE for the costs of such new or revised study if AVEF desires a new or revised Study by SCE.

12.	Payment:  AVEF shall pay the full cost for SCE to perform the Study as follows:

a.	AVEF shall reimburse SCE for SCE’s cost of performing the Study; provided, however, that AVEF shall not be required to reimburse SCE for amounts in excess of the estimated Study costs of $50,000, except as provided in Section 13 of this Agreement.

- AVEF shall advance to SCE $50,000 for the Study upon execution of this Agreement.

- SCE shall refund to AVEF, without interest, any amounts received by SCE which exceed the cost of the Study, even if terminated pursuant to Sections 13 or 15 of this Agreement.

13.	Increased Costs: If at any time SCE determines that the Study is expected to cost more than $50,000, SCE shall notify AVEF and provide an estimate of any additional costs. Upon receipt of such notice, AVEF shall either:  (i) request that SCE terminate the Study; or (ii) provide a written request to SCE that SCE continue the Study, and agree to pay any additional costs to SCE.  SCE shall be under no obligation to incur costs in excess of $50,000 for the Study, unless and until it receives notice pursuant to this Section 13 and an agreement from AVEF to pay costs in excess of $50,000.

14.	Records and Accounts:  SCE shall maintain records and accounts of all costs incurred in performing the Study in sufficient detail to allow verification of all costs incurred, including, but not limited to, labor and associated labor burden costs, materials and supplies, outside services, and administrative and general expenses.  AVEF shall have the right within two calendar years following completion of this Study, upon reasonable notice, at a reasonable time and place, and at its own expense, to audit SCE’s records as necessary and as appropriate in order to verify costs incurred by SCE for performing the Study.

- Termination Upon Demand:  AVEF may demand that SCE terminate the Study at any time.  Immediately following receipt of written notice of such termination from AVEF, SCE shall terminate the Study as demanded.  In such case, AVEF shall reimburse SCE only for costs actually incurred or irrevocably committed to be incurred for the performance of the terminated Study.  If AVEF so requests in its notice of termination, SCE shall submit to AVEF the results of the incomplete Study in a report including assumptions and calculations available at the time SCE receives AVEF’s termination notice.

- Signature Clause:  This Agreement shall become effective on the date the fully executed Agreement and payment pursuant to Section 12 of this Agreement are received by SCE.  If SCE does not receive the fully executed Agreement and payment within 10 business days of AVEF’s receipt, then the offer reflected in this Agreement will be rescinded and this Agreement will be of no effect.

By:_________________________

Name:  Ronald D. Nunnally

Title:  Director, Federal Regulation and Contracts

Southern California Edison Company

ACCEPTED AND AGREED to this _______day of _______, 2001

By:___________________________

Name:  David Parquet

Title:  Vice President

Antelope Valley Energy Facility, L.L.C.