#### APPROVAL AMOUNT REQUESTED

Amount:	Up to $3.4 million of incremental exposure, increasing total development cost exposure to the Arcos project to $35.9 million, exclusive of turbine commitments..

Purpose:	To fund further pre-Notice-To-Proceed (NTP) engineering costs ($1.6 million of cash plus $1.2 of cancellation charges) to support the permitting effort for the Arcos project through December 2001 and $0.6 million that are payable for the Municipal Works Licence.

# EXPOSURE SUMMARY

Existing Exposure in Arcos:			$12.5 million* (development funds already committed to the project)

$20.0 million (projected termination cost of gas pipeline capacity)

This Investment:	Cash				  $2.2 million**

Cancellation Exposure		  $1.2 million

Total Exposure After This Transaction: 		$35.9 million***

* This includes $3.5 million approved in the first pre-NTP DASH dated 25 August 2000 and an additional $6.5 million approved through a second pre-NTP DASH dated 3 November 2000. This does not include (i) payments related to the purchase of turbines and (ii) termination costs under the gas Transportation and Regasification Agreements (TPA)(see DASH dated 26 September 2001).

* See Annex 1 for breakdown of costs up to date.

** See Annex 2 for Schedule of engineering works commitments until June 2002.

***This excludes the present cancellation cost of the three GE 9FA turbines expected to be employed in this project of $175 million .  The turbines may be redeployed to another project [discuss transfer restrictions] if not used for the Arcos project.

## DEAL DESCRIPTION

Transaction:

The Arcos power project is a 1,200 MW combined cycle gas-fired power plant to be built in Arcos de la Frontera, in southern Spain. It would be the first independent power plant in Spain and is designed to have have sufficient operational flexibility to react to demand fluctuations in the Spanish electricity pool.

The Project was delayed due to the unwillingness of Enagas to provide capacity in its LNG regasification and natural gas transportation network. The previously assumed NTP date of January 2001 was not tenable due to this delay. Enagas and the Project finally entered into agreements for LNG regasification and natural gas transportation capacity; these agreements are effective as of September 28 2001. These agreements give the project the ability to bring fuel to the power plant which significantly enhances the feasibility of the Project. The commercial team is currently pursuing a bifurcated strategy of: 1) assessing the value of the Project, in its current state, to potential third party purchasers and 2) continuing with the development of the Project. All of the development work currently underway on the Project serves to maintain the Project’s competitive advantage over other projects in Spain and will enhance the value of the Project to a potential purchaser.

Should the market not realize an appropriate value for the Project in its current state, the development and financing of the Project is expected to continue  to further enhance the value of this development project.. If some of the design, engineering and procurement work for long-lead items (not including the placement of procurement orders for these items) does not continue, the target date for financial closure would have to be moved back from April 2002, as this work would be key to ensure the granting of the preliminary ‘Autorizacion Administrativa’ by the Ministry of Economy, a condition precedent for financial closure.

If the Project is developed, the total cost is of the Project on an unlevered basis is expected to be $547 million.  Assuming debt financing during construction, the total cost of the project, including financing and interest costs during construction of $156 million, is $703 million.

Enron would develop the project and put in place a CTA [define] to offtake the power from the plant. The tentative financing plan would comprise: $610 million senior debt; $35.7 million from other equity holders for 80% of equity; and $57.3 million from Enron in the form of sub-debt and the remaining 20% of the equity.  [FASH from Global Finance?]

[Since the design and procurement work will be included in the work schedule under the EPC contract, the $1.6 of the payments approved through this DASH for engineering work (together with the $6.5 million of engineering costs already paid or committed) will be deducted from the first payment due to EECL under the EPC contract in case the project is finally developed, as soon as NTP is given. – Relevance?] If Enron decides to abandon the project before giving NTP then it will incur cancellation charges of $1.2 million to cover winding-up costs.

Background:

See DASH dated 26th September 2001 for background of the project.

## TRANSACTION SOURCES AND USES OF FUNDS

| Incremental Exposure | Sources |  |  | Uses |
| --- | --- | --- | --- | --- |
| Enron Balance Sheet | $3.4 million |  | Costs | $3.4 million |
| Total | $3.4 million |  | Total | $3.4 million |
| Total Exposure | Sources |  |  | Uses |
| Enron Balance Sheet | $35.9million |  | Costs | $35.9 million |
| Total | $35.9 million |  | Total | $35.9 million |

| RETURN SUMMARY |  |
| --- | --- |

The engineering work and continuation permiting is expected to add value to the project irrespective as to whether the value is gained from the sale of the Project or the continued development, provided the development of the Arcos project is completed.  [Discussion of the risks of abandonment due to inability to overcome political opposition or otherwise].

At this stage and based on the traders’ power and gas curves in Spain, the economics of the Arcos project are estimated as follows: (i) equity value = $10 million (as per commercial team model); (ii) CTA [define] value = $10 million (as per structuring model); and (iii) value of Enron Corp’s implicit guarantee = $(175) million, as estimated by RAC.  Additional work will be needed on the modeling in order to come up with a definite overall project NPV and IRR [RAC should provide current estimate of value, why a purchaser may pay more than our estimate of value, and attach ValSum as appendix to this DASH].

# CASH FLOW SUMMARY

N/A [Preliminary summary should be provided]

## TRANSACTION UPSIDES/OPTIONALITY

N/A [For the first transaction in Spain, this section should be expanded—Spanish market and EU market upsides/optionality]

EXIT STRATEGY

The commercial team is currently pursuing both the sale of the Arcos project and the continued development of the Arcos project. By Decemeber 2001 it will be known as to whether or not an economically viable sale is possible at the current state of the Project’s development. If the sale is viable, the new owner of the Project will take over the Project and assume the risk and responsibility of the development. Should the sale not be economically viable, appropriate approvals will be sought to continue with the development and financing of the Project and sale will be pursued at financial close.

## RISK MATRIX

The table below outlines some of the key issues that are currently anticipated in this project. Other risks that might emerge once the final commercial structure has been decided will be assessed as part of the overall project DASH that will be submitted to Management and the Board for approval before NTP is issued.

| DESCRIPTION | MITIGATION/COMMENTS |
| --- | --- |
| # Commodity Price Risk (Power and gas) | Enron is expected to contract for 100% of the output of the plant and to pay the costs for 100% of the gas used during 15 or 20 years. This is likely to be achieved through a CTA or equivalent structure. The gas tolled through the plant by Enron will probably be purchased from the continental gas desk. The power generated will be sold into the Spanish pool by the power desk. This will give Enron a sizeable long position in the power-gas spread in Spain. Given the current illiquidity in the Spanish energy markets Enron will have significant price exposure. |
| # TPA contracts | See DASH dated 26 September 2001 (attached) |
| # Development Risks | The development of the project would bear the typical risks of an IPP project. Issues of particular concern on this deal are likely to include: - Water Risk: The plant needs a considerable amount of water to secure its operation. The commercial team plans to secure the water from an 800 Hm3 water reservoir built in 1996, which is full today and hasn’t experienced any dryness problems since it was built. The team got the concession for the usage of water (379.7 litres/second for 8,500 hours in each year, together with a supplementary volume of 115 litres/second for 1500 hours in each year) from the The Confederación Hidrográfica del Guadalquivir (CHG) on April 2001. Under the concession, only the domestic and ecological (small amount) uses of water have priority of usage over the Arcos power plant, which has priority of usage over agricultural water requirements. The Diputacion (entity representing the villages nearby the power plant) has challenged that concession in the last week. The commercial team will find out which was the reason why the Diputacion challenged the concession and will fight for it in the following weeks. - Public Opposition: Public opposition to the power plant became public in February 2001. The main instigators are a local environmental group, which has links with 'Ecologistas en Accion', a national environmental organisation. There has been one major public demonstration this year against the proliferation of power plants in the region (Enron just happens to be the first and therefore a focal point for some of the protesters). There were approximately 4,000 people (according to official figures) at the demonstration - these were primarily from around Andalucia (about 400 people from the town of Arcos). The plataforma remains active in trying to incite protest against the plant. While the struggle for public opinion is fairly balanced at the moment, the risk still exists definitely as protests can be triggered very quickly by any small event at any time. [Required permits and other governmental approvals and status?] - Political risk: From a political point of view, the Diputacion, which is an entity representing the villages nearby Arcos de la Fontera, is currently lead by the Socialist Party and is opposing the project. - Financing risk: The CTA structure for 15-20 years should make banks comfortable to underwrite the senior debt. RBS and BBVA should be able to underwrite the senior debt and Enron should be able to sell 80% of the equity. |

Construction Risk, Development Risk, Regualatory Risk?

# KEY SUCCESS FACTORS (relative sliding scale)

|  | NA | # Poor | # Excellent |
| --- | --- | --- | --- |
| Core Business |  | X |  |
| Strategic Fit |  | X |  |
| Upside Potential | X |  |  |
| Management | X |  |  |
| Risk Mitigation |  | # X |  |

OTHER RAC COMMENTS

This project is being developed for a sale to a third party, much like the successful sales of developmental power projects in the U.S. (e.g., Pittsburg, Fountain Valley, etc.).  [Corroboration that there appears to be a asset market for such partially developed projects in Spain/Europe?]

CONDITIONS PRECEDENT

N/A

MILESTONES

Nothing prior to 31 May 2002?

#### On or before 31 May 2002:

#### (i) the TPA has to be transferred to a third party by a sale of the Arcos project or otherwise; or

#### (ii) appropriate approval has been obtained to financially close the Arcos project, issue NTP and recapitalize EEG; or

#### (iii) the TPA has been renegotiated in order to reduce EEG’s potential liability; or

#### (iv) appropriate approval is obtained to extend the 31 May 2002 deadline set above.

| # APPROVALS |  | Name |  | Signature |  | Date |
| --- | --- | --- | --- | --- | --- | --- |
| Origination |  | Andrew Makk |  |  |  |  |
| Continental Trading & Orig. |  | Eric Shaw |  |  |  |  |
| Engineering & Technical Services |  | John Chappell |  |  |  |  |
| Legal |  | Mark Evans |  |  |  |  |
| RAC Management |  | Rick Buy/Dave Gorte |  |  |  |  |
|  |  | Ted Murphy |  |  |  |  |
| Enron Global Finance |  | Andy Fastow/Ben Glisan |  |  |  |  |
|  |  | Anne Edgley |  |  |  |  |
| Regional Management |  | John Sherriff/Michael Brown |  |  |  |  |
| ENE Management |  | Ken Lay/Mark Frevert/Greg Whalley |  |  |  |  |

Annex 1– Breakdown of Arcos pre-development costs until August 31, 2001 (in ‘000 $)

Purchase of Land: 					                912

EE & CC:						  	6,596

Consultancy:					  	2,453

Audit&Legal		   				  	1,557

Travel & Entertainment Expenses:	 		    	  415

Other Expenses:					      	    92

12,025

* $1,000,000 of the total amount of $6,596,000 has already been committed by the EE&CC department, although it has not been paid yet.

Annex 2 – Cash Commitments Schedule (in ‘000 $)  [What about cash spent to date?; shouldn’t this be cumulative?]

Legal Risk Memo?