“BEEP Split’ Market Simulation Plan

April 30, 2001-May 2, 2001

Contact Information

ISO Test Floor:  (916) 351-4476 & (916) 351-4499

Market Simulation Bridge Line:

(Telephone #: 1-888-837-2407 Passcode: 362256)

Market Simulation Execution & Contact: Alan Parson, Jr.

(aparsonjr@caiso.com) (916) 351-4405

Connectivity and Web Issues: Ginger Seitles (gseitles@caiso.com) (916) 351-4420

Market Simulation Support & Coordination: Rod Fudeh

(rfudeh@caiso.com ) (916) 351 2290

URL for Test Machine: https://alhidev30/iso

# Test Plan and Script

# Monday, April 30, 2001

#### Tasks & Objectives

- ISO issues SC passwords for testing

- SC’s setup and test connectivity to test machine

- SC’s submit schedules for May 1, 2001, using the existing production template format.

- ISO runs the market using the production version software.

- SC’s submit hour ahead and supplemental schedules for May 1, 2001, using the existing production template format.

- ISO downloads the SC data before upgrade and  converts the data to new template format

- ISO upgrades the software to BEEP Split version and  uploads the converted  template data.

The objective of the above two steps is to exercise the transition from the existing production version of software to BEEP Split version with the market participants.

#### Scenarios

Day Ahead – existing production version software

- SC’s setup and test connectivity to test machine

- SC’s submit day ahead schedules for May 1, 2001, using the existing production template format

- ISO runs day ahead market

- SC’s submit  hour ahead and supplemental schedules for May 1, 2001

The following steps do not require SC participation

- ISO downloads SC’s schedules, which are associated with modified templates.

- ISO upgrades the  software to BEEP Split version

- ISO converts the down loaded templates to the new format, assuming default CONTINGENCY_FLG of “NO”.

- ISO uploads the new template schedules.

- ISO runs the hour ahead and real-time market for May 1, 2001.

SC Data Requirements

Day Ahead:

- Balanced generation and intertie energy schedules. Please do not include any inter-SC energy trade to eliminate any inter-SC coordination.  Also no FTR/ETC usage is needed. Feel free to submit FTR/ETC if it necessary to test your software.

- Regulation, spin, non-spin and replacement generation bids, non-spin loads, and spin, non-spin, and replacement  intertie bids.

Hour  Ahead & Real-Time:

- Spin & non-spin generation bids, non-spin loads,  and spin &  non-spin  intertie schedules.

- Supplemental energy for testing of  new SC specific Generation, Load, Interchange Ex-Post  Schedule/Price web pages.

| Time | # Task | Responsibility | () |
| --- | --- | --- | --- |
| 0900 | Open Day Ahead market for May 1, 2001 | ISO |  |
| 0900-1000 | Help SC’s resolve any connectivity issue | ISO |  |
| 0900-1100 | Submit Day Ahead schedules for May 1, 2001 | SC’s |  |
| 1100 | Close Day Ahead Preferred and Revised market | ISO |  |
| 1200 | Publish Day Ahead final results | ISO |  |
| 1200 | Submit Hour Ahead and supplemental energy schedules for May 1, 2001 | SC’s |  |
| 1400-1600 | Download and convert the day ahead and hour ahead schedules (In actual implementation this would happen after hour ahead publication of hour 24, around 21:15) | ISO |  |
| 1400-1600 | Upgrade software to BEEP Split version | ISO |  |
| 1400-1600 | Upload the converted schedule data | ISO |  |
| 2200- next day | run hour ahead and real-time market | ISO |  |

# Tuesday, May 1, 2001

#### Tasks & Objectives

- Demonstrate running of market in the transition day

- Test new BEEP Split version templates for  Day  Ahead for May 2, 2001 and Hour Ahead for May 1, 2001

- Test new SC specific Ex-Post Market Information web pages and templates.

#### Scenarios

### Day Ahead

- SC’s submit Day Ahead data for May 2, 2001

###### Hour Ahead

- SC’s submit hour ahead schedules for spin & non-spin generation, non-spin loads, and spin & non-spin interties, using new templates, for.

SC Data Requirements:

Day Ahead

- Balanced generation and intertie energy schedules. Please do not include any inter-SC trade energy trade to eliminate any required coordination.  Also no FTR/ETC usage is needed. Feel free to submit FTR/ETC if it necessary to test your software.

- Regulation, spin, non-spin and replacement generation bids, non-spin loads, and spin, non-spin, and replacement  intertie bids.

Hour  Ahead & Real-Time:

- Spin & non-spin generation bids, non-spin loads,  and spin &  non-spin  intertie schedules.

- Supplemental energy for testing of new SC specific Generation, Load, Interchange Ex-Post  Schedule/Price web pages. This is essential if you choose CONTINGENCY_FLG to be “YES” for your ancillary services.

| Time | # Task | Responsibility | () |
| --- | --- | --- | --- |
| all day | ISO runs hour ahead and real-time market. BEEP instructions are automatically acknowledged by ISO, no ADS instruction are sent to SC’s | ISO |  |
| all day | SC’s may download SC specific Ex-Post Market Information templates for May 1, 2001 | SC's |  |
| all day | SC’s may submit Hour Ahead and supplemental energy schedules for May 1, 2001 | SC's |  |
| Before 1000 | Submit Preferred day ahead Schedules for May 2, 2001 | SC's |  |
| 10000 | Close Day Ahead Preferred Market | ISO |  |
| 1100 | Publish Day Ahead Adjusted results for May 2, 2001 | ISO |  |
| 1100 – 1200 | Download Adjusted Energy and A/S Schedules and DA Interim Public Market Information | SC’s |  |
| 1100-1200 | Submit Revised Preferred Schedules and bids for May 2, 2001 | SC’s |  |
| 1200 | Close Day Ahead Revised Preferred Market | ISO |  |
| Before 1300 | Publish Day Ahead Final results for May 2, 2001 | ISO |  |
| After 1300 | Download Day Ahead results, if you require. | SC’s |  |
| After 1300 | Submit Hour Ahead and supplemental energy schedules for May 2, 2001. | SC’s |  |

# Wednesday, May 2, 2000

#### Tasks & Objectives

- To test new BEEP Split version templates for  Hour Ahead and Real-Time for May 2, 2001

- To provide new SC specific Ex-Post Market Information web pages and templates.

#### Scenarios

Hour  Ahead & Real-Time:

- SC’s submit spin & non-spin generation bids, non-spin loads, and spin &  non-spin  intertie schedules.

- SC’s submit supplemental energy for testing of new SC specific Generation, Load, Interchange Ex-Post  Schedule/Price web pages. This is essential if the CONTINGENCY_FLG is set to “YES” for all ancillary services.

| Time | # Task | Responsibility | () |
| --- | --- | --- | --- |
| all day | ISO runs hour ahead and real-time market. BEEP instructions are automatically acknowledged by ISO, no ADS instruction are sent to SC’s | ISO |  |
| all day | SC’s may down load 24-hour SC specific Ex-Post Market Information templates for May 1, 2001 | SC's |  |
| all day | SC’s submit hour ahead an supplemental energy schedules for May 2, 2001 | SC's |  |
| all day | SC’s down load hourly SC specific Ex-Post Market Information templates for May 2, when they become available. | SC’s |  |