Commercial

Jan. 12, 2001	-	Send Bison Shippers Precedent Agreements

Feb. 22, 2001 	- 	Executed Precedent Agreements

-	Letter from Bison to Border requesting capacity

Feb. 23, 2001 	-	NBPL Shipper letters invoking ROFR process

(Contracts expiring on or before 10/31/03 only*)

Mar. 9, 2001 	-	ROFR Responses Due

Mar. 12, 2001 	- 	Posting of available NBPL capacity

Apr. 2, 2001 	-	 Posting concludes

Apr. 9, 2001	 	- 	Notify capacity holder of bids and give ROFR notice

May 7, 2001 	- 	NBPL Shipper responses due

May 8, 2001 	-	Notify Bison Shippers of available capacity

May 22, 2001	-	Execute NBPL Service Agreements w/Bison Shippers

-	Satisfaction of Downstream Capacity condition

Nov. 2002		-	Execute Bison Service Agreements

*  2001-	 2 Contracts =    27.6 MMcf/d

2003- 31 Contracts = 996.198 MMcf/d

Regulatory/Construction

Mar. 2001 		- 	Begin Environmental Assessment for

Certificate Application

# Aug. 2001 		-	File FERC Application including Tariff sheets

### Nov. 2002 		- 	Receive FERC Certificate Approval

Order pipe

#### May 2003 		- 	Commence Construction

Nov. 2003 		- 	IN-SERVICE