CHANGE ORDER NUMBER 2

(Add Storage of Unit #1)

to

CONTRACT BD-2-00

By and Between

E-NEXT GENERATION LLC

as Purchaser

Acting through its Agent

ENRON NORTH AMERICA CORP.

AND

GENERAL ELECTRIC COMPANY

as Seller

BLUE DOG PROJECT

(GAS TURBINE GENERATOR PACKAGES)

CHANGE ORDER NUMBER 2

(Gas Turbine Generator Contract)

# PART I  REQUIREMENTS

1.	In accordance with Contract Article XI of Contract BD-2-00 between General Electric Company and Enron North America Corp., as Agent for Purchaser, dated May 31, 2000 (the "Agreement"), Purchaser hereby amends the Agreement to include all changes set forth in this Change Order Number 2.

2.	Summary of Change:  Pursuant to Section 5.5.2 of the Agreement, Purchaser directs and Seller agrees to perform delivery of Unit #1 only to storage facilities in accordance with the following requirements:

2.1	The gas turbine and generator of "Unit 1", (as so identified in Exhibit B-2 of the Agreement), will be shipped from the Delivery Point to a Sellercontracted storage facility at Houston, TX and/or Newport News, VA on or prior to the Guaranteed Unit Shipment Date(s) for Unit 1 set forth in Exhibit B-2 of the Agreement.

2.2	All other Unit 1 Major Components and ancillary non-Major Components for Unit 1 (sometimes managed by Seller using the terminology of materials shipped direct or "MSD") will be shipped from the Delivery Point to a storage facility in Oklahoma on or prior to the Guaranteed Unit Shipment Date(s) for Unit 1 set forth in Exhibit B-2 of the Agreement. The equipment referenced in 2.1 and 2.2 shall be referred to in this Change Order as “Unit 1 Equipment”.

2.3	The storage cost for the Unit 1 Equipment is based on storage through June 30, 2001.

2.4	The Unit 1 Equipment will be preserved for long-term storage in accordance with relevant Seller publications on the subject. Periodic inspection / audits will be carried out, as required.  Seller shall not be responsible for correction of cosmetic deterioration to external surfaces which occur during storage, unless caused by Seller or its Subcontractors.

2.5	All duties and taxes in connection with storage of the Unit 1 Equipment are not included in this quotation and shall be payable by Purchaser or reimbursed to Seller in accordance with Section 5.5.2 of the Agreement.

2.6	Subject to Section 2.4 above, Seller shall retain  risk of loss under the Agreement and shall be responsible for the care and custody and risk of damage and loss to the equipment) while in storage.  Passage of title and warranty obligations of Seller with respect to the Unit 1 Equipment remain unchanged under the Agreement.

2.7	For planning purposes, upon Agent's notice to Seller that shipment will commence from storage to the Site, (whether such shipping is to be performed by Seller or by others) Agent should plan for the last shipment of Unit 1 Equipment to arrive at the Site no sooner than 120 days from the effective date of such notice.  Therefore, April 1, 2001 should be recognized to be the latest date by which Agent may issue notice of shipment without requiring certain items of Unit 1 Equipment to remain in storage beyond June 30, 2001.

2.8	Seller agrees to continue the storage obligation under like terms after June 30, 2001 at the rate of sixteen thousand U.S. dollars ($16,000.00) per additional month (not to be pro rated) with such rate valid through September 30, 2001 and thereafter the rate shall be subject to negotiation by the parties.  Any additional monthly charges incurred shall be added to the Agreement Change Order executed by both parties prior to payment of such additional amounts.

2.9	Damage discovered during storage shall be reported to Agent as soon as reasonably possible, and shall be repaired while in storage to the extent practical.

2.10	Seller shall provide insurance to cover the Unit 1 Equipment during transport to the storage facility and while in storage for 110% of the value of the Unit and on other terms and with an insurance carrier reasonably acceptable to Purchaser.  Seller’s obligation to provide All Risk coverage under Section 19.1.1 shall extended so long as Seller is storing the Unit 1 Equipment pursuant to this Change Order. The storage coverage shall be primary to any other coverage maintained by Seller, Purchaser or Agent, and Purchaser and Agent shall be named insureds and provided a waiver of subrogation under such policy.

2.11	Seller's responsibility for risk of loss to the Unit 1 Equipment shall pass to Purchaser (following Agent's notice to commence shipment from storage), upon the occurrence of the following:

(i) placement of the Unit 1 Equipment onto the tractor trailer at the storage facility; or

(ii) placement of the Unit Equipment onto the rail car at the nearest accessible rail siding to the storage facility;

as the case may be.

2.12	Seller agrees to provide a proposal for transportation from the storage location to the site if requested by Purchaser or Agent at a later date.

3.	Change to the Agreement: Delete the current Exhibit N-1 and replace it with the Exhibit N-1 attached hereto as Attachment 1 and hereby made part of this Change Order through this reference.

4.	Seller shall provide a separate invoice for this Change Order 2 addressed to Purchaser using the following address:

E-Next Generation LLC

c/o Wilmington Trust Company

Rodney Square North

1100 Market Street

Wilmington, Delaware 19890

Attn: Corporate Trust Administration.

5.	Seller shall deliver the invoice for this Change Order 2 to Agent at the following address:

Enron North America Corp.

as Agent for E-Next Generation LLC

1400 Smith Street

Houston, Texas 77002

Attn: Jody Pierce

6.	Upon execution of this Change Order, subject to Seller's provision of a properly prepared invoice, Purchaser agrees to pay the full amount added by this Change Order to the Purchase Amount, by wire transfer net 10 days.

PART II COST

Revised Purchase Amount: The lump sum amount added to the Purchase Amount by this Change Order is four hundred sixty nine thousand U.S. dollars ($469,000.00).  Summary of the Purchase Amount through this Change Order Number 2 is as follows:

Original Purchase Amount					USD 37,656,200

Purchase Amount through Change Order number 1		USD 38,634,200

Purchase Amount as of this Change Order number 2	USD 39,103,200

PART III TERMS AND CONDITIONS

1.	The terms and conditions of this Change Order number 2 are as set forth in the Agreement as amended by Change Order number 1, except as otherwise amended pursuant to the terms of this Change Order number 2.

2.	The effective date of this Change Order Number 2 shall be January 31, 2001.

3.	All other terms and conditions of the Agreement not changed by this Change Order remain in full force and effect.

## Enron North America Corp.

As Agent for E-Next Generation LLC

as Purchaser

By:

Title:                                                  		Date:

and

General Electric Company

as Seller

By:

Title:	                                                  	Date:

# Attachment 1 to Change Order 2

EXHIBIT N-1  PURCHASE AMOUNT RECONCILIATION Revision 2

| Item | U.S. Dollars |
| --- | --- |
| Base Price for each Unit | $19,117,500 |
| Total Base Price (for two Units) | $38,235,000 |
| Transportation Deduct/Option | ($198,000/unit) |
| Export Packing Deduct/Option | ($83,400/unit) |
| Open Cooling Water System vs Closed | $9,000 |
| 2 Stage Static Filtration vs. Self Cleaning | $9,000 |
| Eliminate APU | ($16,000) |
| Open ventilated Generator vs. TEWAC Generator | $0 |
| 65 kVA bus bracing vs 42 kVA | $1,700 |
| Historian (1 total) | *$130,000 |
| <I> to <HMI> $35K/HMI x 3HMIs | *$105,000 |
| Interconnecting cables for PEECC | $67,800 |
| Galvanized air filter support steel | $5,900 |
| Air Filter Interior Lighting | $9,400 |
| Peak Load Capabiliy | $11,000 |
| Pull out PT=s | $6,100 |
| Bleed Heat Piping | $31,400 |
| Generator curves on HMI | $3,700 |
| Delete Switchgear compt (Generator Breaker), add GLAC | ($325,000) |
| Add CT=s (5 per Unit) | $11,000 |
| 96M Multitransducer | $13,800 |
| 27TN Relay (Stator Ground Fault) | $9,800 |
| Didode Fault Monitor | $1,900 |
| Flux Probe | $6,900 |
| Monitor Brush Rigging | $13,700 |
| Smoke Detector in Collector Compartment | $1,400 |
| Dual element RTD=s in gas generator path | $700 |
| 3-phase collector heaters | $1,300 |
| Inlet Chiller Coil Space for each Unit | $489,000 |
| Storage and Preservation of Unit #1 through June 30, 2001 | $469,000 |

| Cost Attributable to Unit #1 | $19,786,100 |
| --- | --- |
| Cost Attributable to Unit #2 | $19,317,100 |
| Total (the Purchase Amount) | $39,103,200 |