February 2, 2001

Brian J. Whalen Jr.

IPP Project Manager, Transmission Business Development

Sierra Pacific Power Company

PO Box 10100

Reno, Nevada 89520-0024

Dear Mr. Whalen:

On March 2, 2000, Enron North America Corp. (ENA, parent company of Enron Power Marketing Inc. (EPMI)) notified Nevada Power that it was requesting the initiation of studies to determine requirements of integrating the Las Vegas Cogeneration Facility (LV Cogne) into the Nevada Power Company transmisison system.  On June 29, 2000, ENA signed a letter agreement for an interconnection study.  In spite of EPMI’s requests, Nevada Power indicated that it could act faster on EPMI’s request if we agreed to act informally rather than insisting that the interconnection agreement specify that it was being performed under Sierra Pacific’s tariff.  Accordingly, EPMI signed an agreement that did not insist on referencing the tariff provision establishing that the interconnection study be completed within sixty days  (See attached changes to Letter Agreement proposed by EPMI) in spite of the FERC’s clear recent statements  that interconnection was simply the receipt point portion of transmission service and that the procedures for requesting such service were the same.  Tennessee Power Company, 90 FERC 61,238 (2000).

On August 14, 2000, Enron Power Marketing Inc. (EPMI) submitted to Nevada Power Company an application for 230 MW of long-term firm point-to-point transmission service under Sierra Pacific Resources’ Open Access Transmission Tariff for service from LV Cogen to the Mead Substation.  On September 13, 2000, Nevada Power submitted to EPMI a letter agreement for a system impact study, which EPMI signed and returned on September 15, 2000.  Nevada Power therein agreed to use due diligence to complete the study within sixty days.

By a November 20, 2000 letter, Nevada Power advised EPMI of its belief that five pending applications for transmission service overlapped with Enron’s application, thereby barring Nevada Power from providing EPMI the requested firm point to point transmission service without making additions to Nevada Power’s transmission system. And that such transmission additions are distinct and separate from those required to interconnect the proposed expansion of LV Cogen to Nevada Power’s transmission system.  The letter stated that Nevada Power had to analyze the five transmission applications as a prerequisite to evaluating and defining transmission requirements for Enron’s application.  Accordingly, Nevada Power estimated that its System Impact Study would be distributed on or before December 29, 2000.

EPMI met with Nevada Power in mid-September and recommended that Nevada Power interconnect these five large IPP projects at 230 or 500 kV and route the line around the low voltage Las Vegas city center.  It was clear to EPMI that the 69 kV system in their city center, core, was not capable of transferring power from the merchant plants in the queue.

EPMI recommended the five pending applications should logically interconnect with Nevada Power’s 500kV in the vicinity of Harry Allen whereas, LV Cogen should logically interconnect to Nevada Power’s 230 kV or at the 69 kV and therefore should not overlap with the five pending applications.

Nonetheless, by your January 4, 2001 letter, you once again advised of your belief that our transmission request conflicted with and was in the queue behind “several transmission requests” for use of your 230 kV system.

By your January 22, 2001 letter you provided a status of studies for our pending applications for Interconnection and Transmission Service. Following extensive delays, your letter appears to adopt our suggestion that interconnecting the IPP customers at the Harry Allen 500 kV is the better plan for integrating these customers.

Although your letter seems to offer promise that we might soon receive definitive responses to our applications, your letter still does not provide a date certain for completing the system impact study for LV Cogen, let alone for providing EPMI transmission and interconnection agreements for signature.  Rather, we read your letter to mean that the revised system impact for the IPP customers will be issued by Friday February 2, 2001.

While we can understand the complexity of integrating a number of projects into the NPC transmission grid, you have had almost one year to figure out that LV Cogen would most logically be interconnected to the 230kV.  That should have been sufficient time to do any system impact studies that needed to be done.  Further, five months was certainly sufficient to determine whether transmission service was available where there is no one else in the queue and the capacity is available.  This is especially true since EPMI laid out the option of LV Cogen interconnecting to the 230 kV system more than four months ago.  Nevada Power has already taken much more time than envisioned by Sierra Pacific’s tariff to submit interconnection and transmission agreements for EPMI’s signature.

Moreover, at this point your continued delays are impacting the viability of the project.  In addition to the project construction schedule impacts, our project financing is dependent upon satisfactory completion of these studies and having the appropriate agreements in place.

We trust that the NPC staff is now in a position to expeditiously complete the work on our requests.  Moreover, the system impact study should be simple since, although your letter does not clarify, as EPMI understands it, your change in plans for the IPP Projects removes the obstacles to completing the studies for our requests and we are first in the queue for use of the 230 kV.

It appears the contingencies to providing the transmission service we have requested, as referenced in your letter of January 4, 2001, have been removed by this change in the interconnection plan for those projects with higher queue priority. We expect that our requested transmission service can now be provided without requiring incremental transmission facilities.

We are prepared to assist in any way we can to complete this work in a timely fashion.  Further, if we do not receive executed transmission and interconnection agreements from you by ________, we ask that you file these agreements unexecuted with FERC pursuant to section ____ of the tariff, to ensure that the project can get financing.

Please contact me at (503) 464-8862.

Sincerely,

Mary Hain

C:	Mark Shank,  Nevada Power

Larry Luna,  Nevada Power

Chris Calger