February 7, 2001

Brian J. Whalen Jr.

IPP Project Manager, Transmission Business Development

Sierra Pacific Power Company

PO Box 10100

Reno, Nevada 89520-0024

Re:	Your January 22, 2001 letter

Dear Mr. Whalen:

As detailed below, Enron North America Corp. (ENA), on behalf of Southwest Power, L.L.L. (SWP), requests executed transmission and interconnection agreement from you by February 28, 1001.  In the alternative, we ask that you file unexecuted agreements with FERC (and provide ENA with a copy of the filing) no later than March 1, 2001.

On March 2, 2000, ENA, on behalf of SWP, requested in writing that Nevada Power initiate studies to determine requirements of integrating new generation at the LV Cogen II Facility into the Nevada Power Company transmission system.  On June 29, 2000, ENA, again on behalf of SWP, signed a letter agreement for an interconnection study.

In spite of ENA’s requests, Nevada Power indicated that it could act faster on ENA’s request if we agreed to proceed informally rather than insisting that the interconnection agreement specify that it was being performed under Sierra Pacific’s tariff.  Accordingly, ENA signed an agreement that did not insist on referencing the tariff provision establishing that the interconnection study be completed within sixty days  (See attached changes to Letter Agreement proposed by ENA) in spite of the FERC’s clear recent statements that interconnection was simply the receipt point portion of transmission service and that the procedures for requesting such service were the same as for transmission service. Ref: Tennessee Power Company, 90 FERC 61,238 (2000).

On August 14, 2000, Enron Power Marketing Inc. (EPMI, a subsidiary of Enron North America) submitted to Nevada Power Company an application for 230 MW of long-term firm point-to-point transmission service under Sierra Pacific Resources’ Open Access Transmission Tariff for service from the existing LV Cogen Substation to the Mead Substation.  On September 13, 2000, Nevada Power submitted to ENA a letter agreement for a system impact study, which ENA signed and returned on September 15, 2000.  Nevada Power therein agreed to use due diligence to complete the study within sixty days.

By a November 20, 2000, letter, Nevada Power advised EPMI of its belief that five pending applications for transmission service overlapped with Enron’s application, thereby barring Nevada Power from providing EPMI the requested firm point to point transmission service without making additions to Nevada Power’s transmission system. These transmission additions were stated to be distinct and separate from those required to interconnect the proposed addition of the LV Cogen II Facility to Nevada Power’s transmission system.  The letter stated that Nevada Power had to analyze the five transmission applications as a prerequisite to evaluating and defining transmission requirements for Enron’s application.  Accordingly, Nevada Power estimated that its System Impact Study would be distributed on or before December 29, 2000.

During a meeting with Nevada Power on September 12, 2000, EPMI pointed out that Nevada Power’s interconnection of these five large IPP projects at 500-kV was a preferable approach. It was clear to EPMI that the 138-kV and 69- kV systems through the city center were not capable of effectively transferring power from all the merchant plants in the queue.  Nonetheless, by your January 4, 2001 letter, you once again advised us of your belief that our transmission request conflicted with and was in the queue behind “several transmission requests” for use of your 138? kV system.

By your January 22, 2001, letter you provided a status of studies for our pending applications for Interconnection and Transmission Service. Following extensive delays, your letter appears to adopt our suggestion that interconnecting the Harry Allen area IPP customers at the 500 kV level is the better plan for integrating these customers.  Although your letter seems to offer promise that we might soon receive definitive responses to our applications, your letter still does not provide a date certain for completing the system impact study for the LV Cogen II Facility, let alone for providing transmission and interconnection agreements for signature.  Rather, we read your letter to mean that the revised system impact for the other IPP customers will be issued by Friday, February 2, 2001 (a date which has now passed).

NPC’s continued delays are threatening the viability of the LV Cogen II Facility project.  In addition to delays imposed in the project construction schedule as a result of the uncertainties surrounding transmission access, project financing is dependent upon satisfactory completion of these studies and having the appropriate agreements in place.  It is vital that the transmission and interconnection issues be resolved at the earliest possible date.

We trust that the Nevada Power staff is now in a position to expeditiously complete the work on our requests.  Moreover, the system impact study should now be simple since, as we understand it (although your letter did not clarify this), your change in plans for the IPP Projects removes the obstacles to completing the studies for our requests and since we are first in the queue for transportation across the 138 kV line.

It appears the contingencies to providing the transmission service we have requested, as referenced in your letter of January 4, 2001, have been removed by this change in the interconnection plan for those projects with higher queue priority. Accordingly, it is our expectation that the requested transmission service for the LV Cogen II Facility can now be provided without requiring incremental transmission facilities.

In a separate letter to Larry Luna, we will similarly address specific issues associated with the interconnection studies and interconnection plan for our project.

We are prepared to assist in any way we can to complete this work in a timely fashion.  If we do not receive executed transmission and interconnection agreements from you by February 28, 2001, we ask that you file these agreements unexecuted with FERC pursuant to section 15.3 of the tariff no later than March 1, 2001, to remove this hurdle to the ability of the  LV Cogen II Facilityto obtain financing.

Please contact me at (503) 464-8862.

Sincerely,

Mary Hain

C:	Gary Porter, Sierra Pacific

Mark Shank,  Nevada Power

Larry Luna,  Nevada Power

Chris Calger, ENA