enovate, L.L.C.

# Business Setup Items

| Item | Updated | Description | Status | Key Action Items |
| --- | --- | --- | --- | --- |
| Legal Documents |  |  |  |  |
| Hub Agency Agreement | 15-Sep | enovate - PGL. enovate as agent for existing PGL Hub. $50,000/month administration fee, x% of profits. LLC termination at either Member's election after June 25 if no executed agreement. Needs to be submitted to ICC for approval. If satisfactory ICC approval is not received by 12/31/00, either member may elect to terminate the LLC. | - Enron counsel (Kay Mann) sent enovate draft to PGL (Mary Klyasheff, Simon Halfin) on 9/8 | - Peoples review Treasury and credit issues (Jim Burns, Aparna Huprikar) - PEC legal review – Speak to PEC commercial on agreement, hold legal discussions directly with Enron counsel - Commercial signoff (Laura Luce, Gregg Penman, Roy Rodriguez, Dave Wear) |
| PERC Peaking Agency Agreement | 15-Sep | enovate - PERC. enovate as agent for PERC Peaking facility. Profits shared subject to Transfer Price Agreement. | - No draft yet | - PEC commercial (Tim Hermann) to communicate concepts to PEC legal for first draft |
| Transfer Price Side Letter | 15-Sep | enovate - PEC. Transfer price arrangement for PGL Hub Services, Enhanced Hub Services, PERC Peaking and any other transactions. | - Enron counsel (Kay Mann) prepared first draft - Delivered to PEC (Bill Morrow) 9/14 | - PEC review of documentation (Bill Morrow, PEC legal) |
| Third Party Master Purchase and Sale Agreement | 15-Sep | enovate - Third Parties. Preferred template agreement for physical transactions. | Complete. | - Distribute to potential counterparties for review immediately |
| GISB Agreement | 9/22/00 | enovate - Third Parties. Alternate agreement for physical transactions with third parties that won't execute Master Purchase and Sale Agreement | - Final GISB sent to PGL (Mary Klyasheff) on 9/22 | - PGL review - Distribute to potential counterparties for review immediately |
| Third Party Parent Guarantee | 15-Sep | Parents - Third Parties. Preferred template agreement for parent guarantees. Determine procedure for issuing/negotiating guarantees. | - Transactions to date have been handled on a one off basis - Need to develop plan for going forward | - Scheduling meeting for early next week with Enron and PEC legal and credit to discuss various options |
| Umbrella Parent Guarantees | 15-Sep | Enron – PEC. Establish umbrella parent guarantees to cover ongoing business. | - Need to determine the level and form of guarantee | - Legal – Exchange forms of guarantee - Commercial – Determine appropriate level |
| ISDA Agreements | 15-Sep | enovate - Third Parties. Preferred template agreements for Schedule to Master Agreement and Paragraph 13 to Credit Support Annex for financial transactions. | - Enron counsel (Sara Shackleton) revising standard forms | - Completed forms forwarded to PEC (Aparna Huprikar, PEC legal) for review by 9/18 |
| Affiliate Master Purchase and Sale Agreement | 15-Sep | enovate - PGL. Blanket filing with ICC for physical transactions. Individual transactions will be attached as confirmations. | Complete. - Fully executed agreement - PEC preparing petitions for submission to the ICC | - PEC submit petitions to ICC for approval |
| Confidentiality Agreements | 15-Sep | CA's for employees working in the LLC. | - Draft CA sent to PEC (Tim Hermann) on 6/14 | - Discuss and forward to PEC legal |
| LLC Loan Facility Agreement | 15-Sep | Establish intercompany loans from each parent to enovate for equal working capital funding requirements. | - Enron counsel (Kay Mann) to prepare loan documentation for PEC review | - First draft delivered to PEC by 9/25 |
| Services Agreement | 15-Sep | Services Agreement for provision of cash management services from ENA to enovate. | - General commercial agreement on funding/reporting protocol - Enron counsel (Kay Mann) to prepare agreement for PEC review | - Determine remaining details of funding/reporting protocol by 9/22 (Enron - Gregg Penman, Mary Lynne Ruffer, Sam Round, PEC -Jim Burns, Paul Burgener) - First draft delivered to PEC by 9/25 |
| Policies and Procedures |  |  |  |  |  |
| Risk Management Policy | 15-Sep | Risk policy establishing limits, notifications, approved traders, etc. LLC termination option at either Member's election until approved. | - General commercial agreement on policy - PEC (Judy Pokorny) presenting to Board for approval - Final revisions to be made after PEC Board approval of general structure | - PEC Board meeting October 4th |
| Risk Procedures and Control Guidelines | 15-Sep | Transaction flow process from deal inception to collection of receivable. LLC termination option at either Member's election until approved. | - Drafts have been presented to PEC and Enron personnel for review | - Final signoff by PEC and Enron personnel |
| Credit Policy | 9/22/00 | Approved counterparties, credit limits and ongoing credit process management. LLC termination option at either Member's election until approved. | - Enron credit (Molly Harris) redrafting policy to clearly define roles and what constitutes an "approved" transaction - Additions to approved counterparty list sent to PEC and ENA on 9/22 | - Enron credit to complete draft and forward to PEC by 9/22 |
| Administrative |  |  |  |  |
| Setup and fund bank account | 15-Sep | Establish LLC bank account and make initial funding of $100,000 each. | - enovate account has been setup at Citibank | - Fund by 9/30 |
| Accounting | 9/22/00 | Establish financial reporting, including variance explanation, process, address MTM vs. accrual issues, document audit procedures, etc. | - Monthly statements being prepared - Accounting for individual transactions being reviewed (MTM vs. accrual) - Audit protocol determined | - Finalize accounting treatment for individual transactions - ENA accounting assist in recognition of quarter end income |
| Tax | 15-Sep | Confirm tax treatment of enovate structure. | Complete. - Ongoing transactions subject to review |  |
| Qualify MEH | 15-Sep | Qualify enovate to conduct business in Midwest states. | Complete. - Qualified in all states with nexus – currently limited to Illinois |  |
| Marketing materials | 15-Sep | Prepare LLC marketing materials describing business, products and potential contracts. | Complete. | - Continue to roll out enovate to target customers |
| Final name of LLC | 15-Sep | Change name. | Complete. - enovate, L.L.C. | - Enron counsel (Kay Mann) to prepare amendment to LLC agreement by 9/22 |
| Prepare schedules A & B | 15-Sep | Section 6.7.2 (d) of MEH Operating Agreement. Grandfathered transations. If not approved by 6/25, either member may elect to terminate the L.L.C. | - First draft complete for both | - PEC (Tim Hermann) revise Schedule for existing transactions subject to transfer price vs. grandfathered transactions - PEC (Tim Hermann) and ENA (Laura Luce,Gregg Penman) commercial signoff |
| Audit existing Hub transactions | 15-Sep | Review existing PGL Hub transactions and determine value under transfer price agreement. | - Existing Hub transactions disclosed on PGL schedule | - Enron (Mark Mixon) complete review by 9/30 |
| Appoint officers, Commercial Development Manager, Business Development Manager, alternate Board Members. | 15-Sep | Need to put names with titles in MEH Operating Agreement. Determine need for officers and appointment of alternate board members. Name any designees for risk, credit or other reporting and control needs. | - enovate commercial personnel are discussing various roles and responsibilities | - enovate GM (Laura Luce) determine assignments by 9/25 with input from enovate commercial personnel (Gregg Penman, Richard Tomaski, Tim Hermann) - Enron counsel (Kay Mann) prepare Board resolutions by 9/29 |
| Initial Budget | 15-Sep | Prepare operating budget and related marketing and operating plans by August 1st per MEH Operating Agreement. Determine cash flow requirements of LLC. | - First budget numbers given to Laura on 9/8 - Aggregating numbers to determine overall business budget | - Review individual budgets for accuracy - Aggregate numbers to determine overall business budget |
| Back Office Support/Booking | 15-Sep | Confirm readiness of back office functions, including risk management, logistics, and accounting, to support transaction processes. | Complete. - All deals being entered into Enron systems - Deal tickets delivered to PEC daily - Daily Position Report being generated |  |