enovate, L.L.C.

# Business Setup Items

| Item | Updated | Description | Status | Key Action Items |
| --- | --- | --- | --- | --- |
| Legal Documents |  |  |  |  |
| Hub Agency Agreement | 27-Oct | Enovate - PGL. enovate as agent for existing PGL Hub. $50,000/month administration fee, x% of profits. LLC termination at either Member's election after June 25 if no executed agreement. Needs to be submitted to ICC for approval. If satisfactory ICC approval is not received by 12/31/00, either member may elect to terminate the LLC. | - Enron counsel (Kay Mann) sent enovate draft to PGL (Mary Klyasheff, Simon Halfin) on 9/8 - Commercial discussions held 10/19 and 10/25 | - Meeting scheduled for week of 10/30 to discuss open legal issues - Continue commercial meetings to discuss specifics of compensation |
| PERC Peaking Agency Agreement | 15-Sep | Enovate - PERC. enovate as agent for PERC Peaking facility. Profits shared subject to Transfer Price Agreement. | - No draft yet | - PEC commercial (Tim Hermann) to communicate concepts to PEC legal for first draft |
| Transfer Price Side Letter | 27-Oct | enovate - PEC. Transfer price arrangement for PGL Hub Services, Enhanced Hub Services, PERC Peaking and any other transactions. | - Commercial discussions held 10/25 to discuss multiple alternatives | - Evaluate economics and documentation of potential alternative structures - Expect preliminary decision by 11/3 |
| Third Party Master Purchase and Sale Agreement | 15-Sep | enovate - Third Parties. Preferred template agreement for physical transactions. | Complete. | - Distribute to potential counterparties for review immediately |
| GISB Agreement | 06-Oct | enovate - Third Parties. Alternate agreement for physical transactions with third parties that won't execute Master Purchase and Sale Agreement | Complete. | - Distribute to potential counterparties for review immediately |
| Third Party Parent Guarantee | 27-Oct | Parents - Third Parties. Preferred template agreement for parent guarantees. Determine procedure for issuing/negotiating guarantees. | Complete. - PEC and ENA have each provided individual templates for distribution to 3rd parties - PEC and ENA will negotiate guarantees separately - Discussions will continue regarding potential of moving towards a common guarantee form | - Distribute to counterparties upon request |
| ISDA Agreements | 27-Oct | enovate - Third Parties. Preferred template agreements for Schedule to Master Agreement and Paragraph 13 to Credit Support Annex for financial transactions. | - Discussions held 10/23 - PEC to provide comments on Enron ISDA form | - PEC and Enron joint development of initial templates |
| Affiliate Master Purchase and Sale Agreement | 27-Oct | enovate - PGL. Blanket filing with ICC for physical transactions. Individual transactions will be attached as confirmations. | Complete. - Fully executed agreements - Testimony has been reviewed and approved by Enron regulatory counsel | - PEC submit testimony and petition to ICC for approval |
| Confidentiality Agreements | 15-Sep | CA's for employees working in the LLC. | - Draft CA sent to PEC (Tim Hermann) on 6/14 | - Discuss and forward to PEC legal |
| LLC Loan Facility Agreement | 27-Oct | Establish intercompany loans from each parent to enovate for equal working capital funding requirements. | - Draft delivered to Enron counsel for review - Expect delivery to PEC end of week of 10/30 | - Enron legal and commercial finance review of draft |
| Services Agreement | 15-Sep | Services Agreement for provision of cash management services from ENA to enovate. | - General commercial agreement on funding/reporting protocol - Enron counsel (Kay Mann) to prepare agreement for PEC review | - Deliver first draft to PEC |
| Policies and Procedures |  |  |  |  |
| Risk Management Policy | 27-Oct. | Risk policy establishing limits, notifications, approved traders, etc. LLC termination option at either Member's election until approved. | Complete. - All approvals have been received - Final execution expected later this afternoon | - Enron prepare and deliver confidentiality agreement to PEC regarding enovate curves and other market information |
| Risk Procedures and Control Guidelines | 27-Oct. | Transaction flow process from deal inception to collection of receivable. LLC termination option at either Member's election until approved. | Complete. |  |
| Credit Policy | 27-Oct. | Approved counterparties, credit limits and ongoing credit process management. LLC termination option at either Member's election until approved. | Complete. |  |
| Administrative |  |  |  |  |
| Setup and fund bank account | 06-Oct. | Establish LLC bank account and make initial funding of $100,000 each. | ## Complete. |  |
| Accounting | 06-Oct. | Establish financial reporting, including variance explanation, process, address MTM vs. accrual issues, document audit procedures, etc. | ## Complete. |  |
| Tax | 06-Oct. | Confirm tax treatment of enovate structure. | Complete. |  |
| Qualify enovate | 15-Sep | Qualify enovate to conduct business in Midwest states. | Complete. |  |
| Marketing materials | 15-Sep | Prepare LLC marketing materials describing business, products and potential contracts. | Complete. | - Continue to roll out enovate to target customers |
| Final name of LLC | 15-Sep | Change name. | Complete. |  |
| Prepare schedules A & B | 15-Sep | Section 6.7.2 (d) of enovate Operating Agreement. Grandfathered transations. If not approved by 6/25, either member may elect to terminate the L.L.C. | - First draft complete for both | - PEC (Tim Hermann) revise Schedule for existing transactions subject to transfer price vs. grandfathered transactions - PEC (Tim Hermann) and ENA (Laura Luce,Gregg Penman) commercial signoff |
| Audit existing Hub transactions | 06-Oct. | Review existing PGL Hub transactions and determine value under transfer price agreement. | Complete. |  |
| Appoint officers, Commercial Development Manager, Business Development Manager, alternate Board Members. | 15-Sep | Need to put names with titles in enovate Operating Agreement. Determine need for officers and appointment of alternate board members. Name any designees for risk, credit or other reporting and control needs. | - enovate commercial personnel are discussing various roles and responsibilities | - Determine appointments - Enron counsel (Kay Mann) prepare Board resolutions by 9/29 |
| Initial Budget | 15-Sep | Prepare operating budget and related marketing and operating plans by August 1st per enovate Operating Agreement. Determine cash flow requirements of LLC. | - First budget numbers given to Laura on 9/8 - Aggregating numbers to determine overall business budget | - Review individual budgets for accuracy - Aggregate numbers to determine overall business budget |
| Back Office Support/Booking | 05-Oct. | Confirm readiness of back office functions, including risk management, logistics, and accounting, to support transaction processes. | Complete. |  |