Customer Choice Facilitation Program

Large Commercial Group

--- Next Steps ---

11/10 		SDG&E to Provide ESPs with:  (in preparation for discussion 11/14)

- Processing/Mailing Options

- Refinement of Mailer (ie. self-select options)

- Revised draft of radio script

12/1		Final Program Agreement sent to ESPs

11/14		Meeting in SD (10am – 3:30pm) with ESPs to discuss & reach agreement on:

- Processing/Mailing options

- Refinement of Mailer (i.e. self-select option)

- Final decision on % of contribution for radio & content

- Revised budget estimates

- Firm Implementation Date

11/28		SDG&E to provide ESPs with final draft of radio script

11/30	SDG&E to provide new draft of mailer to ESPs (including spacing sample for ESP service offering)

12/4	Conference call to discuss:

- Radio script sent 11/28

- Draft of direct mailer sent 11/30

12/7 		Final draft of Radio script to ESPs

12/8	SDG&E to provide ESPs with final contribution amount

12/8                Draft of Direct Mailer (w/out ESP service offerings) sent to ESPs based on feedback from 12/4

conference call

12/11              Conference call to review final draft of mailer

12/12		Sign-off due to SDG&E on radio script

12/13               Final version of mailer sent to ESPs for sign-off

12/15		Sign-off due to SDG&E on direct mailer

12/15 		Final Agreement & contribution amount due to SDG&E

12/15		ESP Service Offering due to SDG&E  (if applicable, two versions.. one with DA AB265, one without)

2days after DA AB265 decision --  Conference call with ESPs to:

- review decision

- confirmation of next steps

Late January or 10 days after DA AB265 decision -- Radio campaign begins

Late January/early February or 15 days after DA AB265 decision -- Direct mail campaign begins