Customer Choice Facilitation Program

Large Commercial Group

--- Next Steps ---

11/10 		SDG&E to Provide ESPs with:  (in preparation for 11/14 discussion)

- Processing/Mailing Options

- Refinement of Mailer (ie. self-select options)

- Revised draft of radio script

11/10		Final Program Agreement sent to ESPs

11/14		Meeting in SD (10am – 3:30pm) with ESPs to discuss & reach agreement on:

- Processing/Mailing options

- Refinement of Mailer (i.e. self-select option)

- Final decision on % of contribution for radio & content

- Revised budget estimates

- Firm Implementation Date

11/20		SDG&E to provide ESPs with final draft of radio script

11/22	SDG&E to provide new draft of mailer to ESPs (including spacing sample for ESP service offering)

11/22	SDG&E to provide ESPs with final contribution amount

11/28	Conference call to obtain feedback on:

- final comments on radio script sent 11/20

- Draft of direct mailer sent 11/22

12/1 		Final Agreement & contribution amount due to SDG&E

12/1		ESP Service Offering due to SDG&E  (if applicable, two versions.. one with DA AB265, one without)

12/5 		Final draft of Direct Mailer & Radio script to ESPs

12/8		Conference call to review 12/5 draft (direct mailer w/out ESP service offerings)

12/8		Sign-off due to SDG&E on radio script

12/12		SDG&E to provide final draft of direct mailer to ESPs (including ESP service offerings)

12/15		Sign-off due to SDG&E on direct mailer

2days after DA AB265 decision --  Conference call with ESPs to:

- review decision

- confirmation of next steps

10 days after DA AB265 decision -- Radio campaign begins

15 days after DA AB265 decision -- Direct mail campaign begins