| # CHECKLIST FOR INTRODUCTION OF ENRONONLINE |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## ISSUE | RESPONSIBILTY | COMPLETION | STATUS | DUE DATE |
| Compliance with Corporations Law and Exempt Market Declaration for trading in Australian electricity derivatives | MSJ | Sign off from Legal and external counsel | ### External advice received [COMPLETE] | 15 December 1999 |
| Compliance with Corporations Law for trading weather, crude oil, interest rates | MSJ | Sign off by Legal and external counsel | - Identified issues relating to use of standard GTC’s that need to be checked | Deferred |
| Procedures developed to ensure operation of EnronOnline complies with EAF legislative and electricity market obligations | D. Minns / MSJ | Sign off from Legal and external counsel | - Obligations identified - Need to review organisational details for EnronOnline in Australia | 31 December 1999 |
| Amend Password Agreement & Electronic Trading Agreement for Australia | D. Minns MSJ | Sign off from Legal and external counsel | - Draft of each prepared by DM - Awaiting MSJ advice | 31 January 2000 |
| Produce GTC’s for each electricity derivative product | D. Minns / MSJ | Sign off from Legal and external counsel | - Draft prepared by DM - Awaiting MSJ advice | 31 January 2000 |
| Description for each electricity product |  | Each product description signed off by Legal | Form prepared for swap | 31 January 2000 |
| Review existing Master agreements to ensure consistent with application to EnronOnline | D. Minns/MSJ | Sign off from Legal and external counsel | Standard Enron ISDA reviewed and no required amendments identified | 31 January 2000 |
| Register all Business names & intellectual property associated with EnronOnline | MSJ | Sign off from Legal and external counsel |  | 15 December 1999 |
| Confirm enforceable of contracts entered into through EnronOnline | MSJ | Sign off from Legal and external counsel | - Advice from MSJ [COMPLETE] | 15 December 1999 |
| Confirm no other regulatory impacts through use of EnronOnline | MSJ | Sign off from Legal and external counsel | - No issues identified [COMPLETE] | 15 December 1999 |
| Register domain names in Australia to prevent misuse | E.Katz | “enrononline.com.au” registered | [COMPLETE] | 30 November 1999 |
| Ensure Enrononline complies with of evidence Act and other legislation | ### D. Minns/MSJ | Capable of proving to counterparties that system will provide sufficient evidence on terms of transactions (eg version of GTCs that apply to particular transaction). | - Legislation reviewed - Clarifying operation of EnronOnline |  |
| Ensure presentation material contains no statements that may be misleading or deceptive under the Trade Practices Act. | D. Minns/MSJ | Legal signoff of presentation material |  | Prior to release to third parties |