Critical Path Items to Financial Closing

(See Closing List for key to acronyms)

Next conference call to discuss status:  [To be scheduled.] Tuesday, April 25, 2000 (FF to distribute dial-in information)

| Issue | Responsibility |
| --- | --- |
| 1. Central Bank (A) Finalize Central Bank guarantee by Sponsors (B) Amendments to FIRCE applications (C) Supplementary Agreement (D) Status of registration of project documents with Central Bank, including approval of take-or-pay with longer makeup period (E) Status of registration of subdebt | (A) Lenders and Enron and Shell to have a had conference call on 4/12 re draft distributed by FF on 4/4 4/18; FF (Raciti) to distribute revised guarantee by April 23 (B) OPIC (Mervenne) to confirm that revised versions of FIRCE amendments re OPIC loan require no further changes signoff once receive new schedule from Enron and reset first payment date (C) Lenders to review draft sent by FF (Raciti) (C) C&P (Unna) to discuss with KfW and provide comments to FF on a conference call on 4/13 (D) Lenders to comment on letter sent by Enron South America to (D) Enron (Lammers, Gay) to advise Lenders of any developments in discussions between Furnas and Central Bank of Brazil as per which Enron cannot extend the makeup period without cost; Enron (Friedlander) to send Lenders copy of presentation made to Furnas and Eletrobras re pass-through of cost for extended makeup period (E) V&E (Barquin) to obtain forward information from Patricia Gonzalez) to FF (Raciti) |
| 2. YPF/Gas Supply (A) Finalize Sponsor Guarantee re gas supply (B) Gas Price Differential Guaranty (C) Status of Amendment to GasBol Transportation Agreement | (A) Enron (Friedlander) to coordinate Sponsor comments to revised draft distributed by FF (Raciti) on 4/11; Enron and Lenders to discuss approach vis-à-vis YPF (C) Lenders and Enron had conference call on 4/18; FF (Raciti) to distribute revised guarantee on 4/20; FF (Raciti) and C&P (Schumacher) to prepare letter to EPE re fuel supply conditions to loan by 4/25 and Enron (Lammers) to prepare letter to YPF (offer to participate) by 4/25; V&E (Lefler) to draft a Replacement Contract (B) (D) V&E (Lefler) and Enron (Novak) to coordinate distribution of agreement to Lenders by 4/20 (C) (E) V&E (Lefler) to advise when it will be executed |
| 3. PPA (A) Aditivo No. 2 (B) Aditivo No. 3 (C) Eletrobrás / Furnas consent and opinion (D) Force majeure relating to pipeline delays (E) S&W Site Visit | (A) Signature of Eletrobrás pending final language of the Legal Opinion - Enron (Lammers) to follow up (Legal Opinion would be on Eletrobras board agenda on 4/18 or 4/25) (B) Signature of Eletrobrás pending final language of the legal opinion; Enron (Lammers) to follow up (Furnas has already approved the language)(C) Enron (Novak) to check with TFTS (Bonelli) re scheduling a meeting with Maria Aparecida and Lenders' Brazilian counsel on 4/17 or 4/18 to discuss opinion and Maria Aparecida's comments on Consent (or whether willing to use March 1999 version of Eletrobras Consent without making changes) (D) Conference (C) Lenders conveyed final comments to legal opinion; TF (Bonelli) to coordinate delivery of final legal opinion to Maria Aparecida; TF (Bonelli) to prepare draft of Furnas opinion based on Eletrobras opinion; Enron (Novak) to advise re whether Eletrobras will insist on comments to Consent after meeting between Banantine and Fermino (D) OPIC (Mervenne, Mahaffey), C&P (Shapiro) to advise KfW (Klusener) re preliminary conference call scheduled for 4/13 among Barquin, Shapiro, Friedlander, and O'Brien to discuss Lenders' questions re FM; Enron (Friedlander)(Lammers) to send Lenders copy of talking paper sent to Furnas; EPE (Powell) to advise of updates upon return to office 4/24 (E) S&W (Barta) available for site visit in early May; OPIC (Mervenne) has prepared(E) OPIC (Mervenne) to coordinate with S&W for site visit (S&W to discuss with Powell and/or ISO/ONS issues re dispatch); OPIC (Mervenne) to prepare list of issues to be discussed at meeting site visit in early May (e.g., stabilizers needed) (S&W to discuss with Powell and/or ISO/ONS issues re dispatch); Enron (Ayres) to coordinate call between S&W and Siemens; Enron (Gay) to arrange for execution of S&W contract before site visit |
| 4. Governmental Authorizations (A) Status of IBAMA permit (installation license) (B) Status of ANEEL letter | (A) Enron (Lammers) to advise Lenders when receive IBAMA permit (likely to be on the weeks of 4/17 or 4/24), impact on construction schedule, and amendments to EPC Contract (B) Enron (Lammers) to confirm that letter forward to FF (Raciti) copy of the letter that was sent to ANEEL |
| 5. Amendment to CTA (A) Extension of Commitments (B) Cleanup changes | (A) Enron (Friedlander) and V&E (Barquin) to give comments to Lenders on Amendment No. 1 (B) V&E (Rankin) Lenders to send review list of proposed changes to FF; sent by V&E (Rankin); after receipt of such list, review FF (Elorza) to distribute draft Amendment No. 2 |
| 6. Bolivian Security Documents | Follow up to conference call of 4/11 among FF, C&P, FA, IA and V&E C&P to provide note to V&E re mechanism for step-in as it relates to collateral of TBS and SCG; based on such note, V&E to provide final comments C&P (Sierra-Escalante) to distribute memo re step-in; conference call tentatively scheduled for 4/27 among V&E, C&P, BA, IA and FF to discuss final changes (if any) to pending Bolivian Security Documents (3 agreements) |
| 7. Brazilian Security Documents | Follow up to C&P (Sierra-Escalante) to distribute memo re step-in; conference call of 4/6 conference call tentatively scheduled for 4/13 with Brazilian counsel 4/27 among V&E, C&P, BA, IA and FF to discuss final comments on pending changes (if any) to Brazilian Security Documents |
| 8. Taxes (A) Tax issues raised by Citibank (B) Taxes payable with respect to subdebt | (A) OPIC (Mervenne) to follow up with PWC (FA and BA have confirmed that concerns re 13.5% transfer tax raised by Citibank are not founded) FF (Raciti) has advised Citibank that according to PWC there is not issue (B) OPIC (Mervenne) to follow up with PWC and arrange call with (B) OPIC (Mervenne) to arrange call with PWC (Martin) and Enron (Hopkinson) re effect on model ; (Felsberg has confirmed that withholding tax is payable whether or not interest is paid) and whether issue can be addressed by drafting changes (i.e., if tax computed on accrual basis, can document state that interest does not accrue until interest paid?) |
| 9. Liquid Fuel Supply Contract (A) Translation of signed copy (B) Status of need for amendment (C) Petrobrás opinion and consent | (A) Enron (Novak) to track down translation and send to Lenders (B) Enron (Lammers) confirmed that none needed for increase in diesel usage (C) Enron (Novak) to arrange meeting with Petrobras to discuss Lenders' comments to consent and opinion |
| 10. Accounts Agreements (A) Disbursement Agreement (B) Cayco Accounts Agreement, TBS Shareholders Account Agreement (C) Interborrower Agreement | (A) Sponsors and counsel to provide comments to FF draft of 4/3 (B) FF (Raciti) to distribute (C) FF, C&P, OPIC and KfW Sponsors to discuss comments on 4/13 and provide written comments to Sponsors of Lenders |
| 11. Equity Contribution Agreement | Three open points: 1. Excess Contribution Amount – Enron (Lammers) will propose amount in light of anticipated delays 2. Dispute resolution – OPIC (Mahaffey) to respond to Friedlander proposal and FF (O'Brien) to discuss 3. Indemnity language – Enron and OPIC (Mahaffey) and V&E (Rankin) to discuss at business level |
| 12. Amendment to OPIC Loan Agreement; [Amendment to KfW Loan Agreement] | V&E (Barquin) to coordinate comments from Sponsors to Amendment to OPIC Loan Agreement; C&P (Unna) to prepare draft of Amendment to KfW Loan Agreement |
| 13. Comments to Legal Opinions | Local counsel to provide comments to forms of legal opinions |
| 14. Schedules to Financing Documents | FF (Elorza) to redistribute list of missing schedules; Enron (Lammers) Enron (Rankin) to provide update after revised model produced distributed FF (Elorza) |
| 15. FOGA | OPIC (Mahaffey) and FF (O'Brien) to discuss distribute revised draft incorporating V&E comments; [Enron (Friedlander) and V&E (Rankin) to discuss Citibank comments of 4/6] |
| 16. Insurance | Follow up from conference call of 4/12 with Bignell and Vincent Enron to advise how much coverage for insurance will cost as it expires in April 2001 |
| 17. U.S. Security Documents | Two points: 1. Sponsors and their counsel to provide comments to 3/3 drafts distributed by C&P 2. C&P (Unna) to distribute remaining U.S. Security Documents |

Ancillary List to the Critical Path Items to Financial Closing

(See Closing List for key to acronyms)

Next conference call to discuss status: [To be scheduled.]

| Issue | Responsibility |
| --- | --- |
| 1. YPF/Gas Supply (A) YPF Consent (B) Andina due diligence (C) Amendment to YPF Gas Supply Agreement | (A) Enron (Lammers) to arrange meeting call/meeting with YPF and Lenders on 4/12/4/13 to discuss pending issues – week of 4/24 (B) OPIC (Mervenne) and FF (Raciti) to confirm that Andina consent has covenants re dedication of reserves; Enron (Lammers) to follow up with Andina re missing information for due diligence (C) Enron (Lammers) to find out if YPF willing to sign now if not already signed |
| 2. PPA (A) Extension of 60-day period under Assumption Agreement (B) Performance bond | (A) Enron (Lammers) has advised that performance bond needs to be amended only if increase diesel operation to 300 MW Sponsors and Lenders to discuss rationale for extension requested (B) Enron (Lammers) to advise whether performance bond will be amended to show increase amounts based on changes in schedule after discussions with Furnas |
| 3. Liquid Fuel Supply (A) Environmental issues (B) Governmental Approvals required in connection with possible increase in diesel usage (C) Status of need for amendment | (A) OPIC (Mervenne) to follow up with Moss re compliance with World Bank Guidelines and OPIC Handbook in connection with proposed increase in diesel fuel consumption (B) TFTS and TRW to advise Lenders re additional permits required for extension of 300 MW on diesel fuel phase; Enron to advise re status of obtaining same [NB. This will be moved to critical path items list depending on outcome of force majeure claims submitted to Furnas.] (C) Enron (Lammers) confirmed that none needed for extended diesel usage |