Pacific Gas and Electric Company

Summer 2001 Transmission Capacity Projects

Monthly Status Report to CPUC Required under AB 970 OII

7/01/2001, Page 1 of 3

| No. | Project Title | NOC Required? | NOC Status | Construction Status | Additional Information |
| --- | --- | --- | --- | --- | --- |
| 1 | Tesla-Newark Transmission Reinforcement | Yes | Effective | Project is operational as of 5/6/01, post operational construction work continues. |  |
| 2 | Lockeford-Lodi (Lockeford Area Reinforcement | Yes | Effective | Complete. The project was placed in service on 5/25/01. |  |
| 3 | Ravenswood Ames Capacity Upgrade | No | NA | Complete. The project was placed in service on 6/3/01. |  |
| 4 | Lakewood 115kV Transmission Reinforcement | Yes | Effective | Project is operational as of 6/1/01, post operational construction work continues. |  |
| 5 | Eight Mile (Stagg Voltage Support) | Yes | Effective | Complete. The project was placed in service on 5/26/01. |  |
| 6 | Pittsburg-Tassajara | Yes | Effective | Complete. The project was placed in service on 5/11/01. |  |
| 7A & T652 | Humboldt: Bridgeville-Cottonwood Upgrade | No | NA | In the planning stage. Construction work is forecast to start in July 2001. | This project is not needed for Summer 2001. |
| 7B | Humboldt: Janes Creek Sub Install SCADA on Switches | No | NA | In the planning stage. Construction work is forecast to start in July 2001. | This project is not needed for Summer 2001. |
| 8 | Tesla 500/230 kV Bank | No | NA | Project is operational as of 6/10/01, post operational construction and maintenance work continues. | On 6/11/01, the C-phase unit failed. To date the bank has not been placed back into service. |
| 9 | Metcalf 500kV Shunt Capacitor Banks | No | NA | Complete. The project was placed in service on 6/3/01. |  |
| 10 | Martin 115kV Capacitor Banks | No | NA | Project is operational as of 4/28/01, post operational construction work continues. |  |
| 11 | Mountain View-Whisman 115kV Loop | No | NA | Complete. The project was placed in service on 2/23/01. |  |
| 12A | Re-rate Jefferson 230/60kV Bank 1 | No | NA | Complete. The project was placed in service on 2/16/01. |  |

Pacific Gas and Electric Company

Summer 2001 Transmission Capacity Projects

Monthly Status Report to CPUC Required under AB 970 OII

7/01/2001, Page 2 of 3

| No. | Project Title | NOC Required? | NOC Status | Construction Status | Additional Information |
| --- | --- | --- | --- | --- | --- |
| 12B | Re-rate Moss Landing 500/230kV Bank 9 | No | NA | Complete. No construction work was required to complete the re-rate. |  |
| 23 | Re-rate Ravenswood 230/115kV Bank 1 | No | NA | Complete. The project was placed in service on 4/22/01. |  |
| 25 | Fulton No. 1 60kV Line Reinforcement | Yes | Effective | Construction work is in progress. |  |
| 29 | Cooley Landing Bank 3 Replacement | No | NA | Construction work is in progress. | This project is not needed for Summer 2001. |
| 31 | Metcalf 230/21kV Distribution Substation (Coyote Valley) | No | NA | Project is on hold. | This project has been placed on hold due to recent planning information. |
| T647 | Metcalf-Monta Vista 230 kV Line Separation | No | NA | Complete. The project was placed in service on 5/5/01. | Circuit #1 was released for service 5/17, and on 5/31 Circuit #2 is expected to be operational. |
| T239 | Re-rate Newark 230/115 kV Banks 7, 9 & 11 | No | NA | Construction work is in progress. |  |
| T667 | Grant Eastshore 115kV Transmission Upgrade | No | NA | Complete. The project was placed in service on 6/3/01. |  |
| T668 | Moss Landing 115kV Circuit Breaker (Sw 570) Upgrade | No | NA | Project is operational as of 6/19/01, post operational construction work continues. |  |
| T362 | Oakhurst Area Reinforcement Phase 1: Oakhurst Jct. - Kerckhoff 115kV Line Reconductoring Phase 2: Kerckhoff 1 - Kerckhoff 2 Line Separation | No | NA | In final engineering. Construction work is forecast to start in July 2001. | This project is not needed for Summer 2001. |

Pacific Gas and Electric Company

Summer 2001 Transmission Capacity Projects

Monthly Status Report to CPUC Required under AB 970 OII

7/01/2001, Page 3 of 3

| T449 | Brighton 230/115kV Transformer Re-rate | No | NA | Complete. No construction work was required. |  |
| --- | --- | --- | --- | --- | --- |