# First Revised  (Based on Feedback Received thru 2/24/00)

# "Project Why" Task Force Scope

#### Questions Raised at Offsite Strategy Session

- Should we consider outsourcing transactional processing?

- How does our commercial support strategy compare to the strategies of EES and ENA?

- Are we organized optimally?

- Do we have an e-business strategy going forward or do we continue to react to GISB and FERC requirements?

# Scope of Task Force Assignment

- Inventory current processes

- Are all the tasks necessary?

- Which tasks can be automated with IT/technology solutions?

- Which tasks can be outsourced?

- Should any tasks be realigned to put the data capture closer to its intended user?

- Can any tasks be more efficiently consolidated across operating companies?

- Develop an e-business strategy

- Educate GPG management on e-business models

- Determine customer's needs.  Do we see value in providing customers with ready access to transactional data?  Can this approach be cost-justified? How would e-business impact the customer's perspective on service?

- Determine feasibility of creating an on-line transportation intermediary.

- Identify e-business partnerships.

Proposed Work Plan

| Step | Date | Responsibility |
| --- | --- | --- |
| - Confirm Scope | 2/29 | Operating Company Presidents (Shelley /Jenny will contact to confirm) |
| - Assessment/Classification of Current Processes by Each Operating Company - Inventory current tasks (e.g. capturing daily gas pricing at market centers, determining discount offers, setting the amount of available capacity, preparing web site postings). - Categorize tasks as "competitive advantage" or "transactional processing." - Identify where these tasks are currently performed. - Determine the cost of each task and how many people it takes to perform the task. | 3/31 | Operating Company Presidents |
| - Educate GPG Management on e-business models - Define/Implement Executive Internet mentoring project - Overview e-business presentation at March 30 staff meeting | 3/31 | Shelley/Jenny/John Pavetto |
| - Research and Document other entities (internal & external) transactional processing approaches & e-business strategies | 4/15 | Shelley/Jenny/Tammy Hopkins |
| - Analysis - Identify overlap in transactional process activities - Develop list of e-business opportunities - List sharable best practices | April 2000 | Shelley/Jenny/Market Services Council |
| - Make Preliminary Recommendations | May 9 Staff Meeting |  |