CSUF Substation

Chain of Events

CSUF has been indicating for years to the energy supplier community that a voltage buy up opportunity existed for the campus. The campus main service is currently at primary, i.e. 12 kV, level.  With a current peak demand of 8 mW and planned near-term growth, a transmission level substation is a feasible option as it would decrease the unit cost per kWh by a significant percentage.

Savings resulting from the voltage buy-up were estimated by the local serving utility, PG&E, in the order of approximately $600,000 per year.  During August 1998 CSUF received an unsolicited bid from PG&E to realize the transfer to the transmission rate. PG&E’s proposal, submitted under its filed Electric Rule 2, Special Facilities, included modifications to the serving substation on Bullard Avenue, Fresno, and a dedicated distribution line from the substation to the existing campus electric service point.

As specified under Rule 2, CSUF would not incur up front payments, but rather would have monthly payments in perpetuity subject to an indexed interest rate. PG&E estimated the payments to be in the order of $22,500 per month. PG&E’s proposal effectively would allow CSUF to ‘rent’ the special facilities as long as needed without ever becoming the asset owner. Moreover, if CSUF exercised the Rule 2 buy-off option, i.e. a NPV of the future payment stream, the system improvements would remain vested in PG&E.  Under PG&E’s proposal, the total CSUF exposure over 30 years would approximate $8,100,000.

Enron was made aware of the PG&E proposal by CSUF and offered a counter solution during November 1998. Enron provided a true financial analysis by comparing the PG&E route versus a third party financed option with Enron as the general contractor. The analysis clearly showed a major advantage of going with an Enron-like financial structure, as it would reduce CSUF’s exposure by almost $5 Million over the same 30 year period. CSUF then decided to issue an RFP in December 1998 to ensure proposal compatibility.

As a prospective responding party, Enron initiated a dialogue with PG&E to obtain cost estimates for work to be performed by PG&E to accommodate the eventual interconnection. At first, PG&E brushed off Enron’s requests for detailed information. Enron’s next approach entailed a detailed request for costs associated with a specific routing of the transmission line extension, work to be performed within PG&E's substation, and other associated utility expenditures.  Despite PG&E attempts to delay responses to Enron’s requests, and PG&E’s requests to postpone the RFP due date, Enron was able to extract sufficient information from PG&E’s cost estimates to prepare a comprehensive proposal that was submitted in February 1999. CSUF awarded the substation project to Enron based upon the financial advantages and a commitment to complete the project within 275 days of the Notice to Proceed date.

After going through several iterations, CSUF and Enron signed a Standard Agreement on October 6, 1999 formalizing our relationship and authorizing Enron to act as CSUF’s agent in PG&E’s interconnection proceedings. The agreement consists of a firm substation construction cost ($1,876,000), and an allowance ($1,099,000) for PG&E-dictated expenditures associated with the interconnection with their system. The allowance was derived from initial cost estimates provided by PG&E during the proposal preparation stage.

Immediately after October 6, Enron held meetings with CSUF and PG&E, and submitted single-line drawings to PG&E to request detailed cost figures for the interconnection. While PG&E was given ample time to respond, and had been given sufficient background information, PG&E finally replied on January 12, 2000. The formal reply indicated that the interconnection costs had increased to $3.3 Million. This figure includes all taxes (34%) and a one-time Cost-of-Ownership charge. Enron requested a justification for the $2.2 Million increase and was told by PG&E that; 1)design standards and protection schemes dictated the increase; 2) they had made a mistake in their prior estimate; and 3) that the less expensive interconnection options provided earlier were no longer deemed feasible.

Enron then requested a detailed cost breakdown of the $3.3 Million figure which PG&E submitted. Enron proceeded with an RFQ for the same engineering and construction services that was issued to three contractors who routinely perform such services for PG&E. The following is a synopsis of the cost comparisons:

| Item | By PG&E | By Enron | Difference |
| --- | --- | --- | --- |
| Transmission Line | $512,208 | $316,152 | $196,152 |
| Substation Engineering | $179,776 | $36,750 | $143,026 |
| Substation Removal & Distribution Relocation | $63,985 | No Charge or Included with Other Line Items | $63,985 |
| Substation Work | $723,220 | $273,972 | $449,248 |
| Totals | $1,479,189* | $626,874 | $852,411 |

*Exclusive of ITCC taxes and Cost-of-Ownership Charge

Enron believes that PG&E has not made a serious attempt to keep the interconnection cost to a minimum, and indeed it appears that the costs are out of line with industry standards. Enron and CSUF were informed by PG&E at the last meeting on March 7, 2000 that they have driven their prices down as far as possible and that no further price review on PG&E’s part is warranted.

On behalf of CSUF, Enron intends to escalate the interconnection pricing issue within the Enron Corp organization, PG&E Corporation, and if required the California Public Utilities Commission. An escalation plan is under development as of March 8, 2000. It includes possible assistance from CSUF through its most appropriate channels.