| Critical Steps |  | Senior Management | Operations | Legal | Communications |  |  | Regulatory Affairs | RAC/Credit | Risk |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Customer | Account Management | External |  |  |  |
|  |  | Dan Leff Marty Sunde | Wanda Curry Evan Hughes | Mike Smith Jim Keller | Scott Gahn Eric Melvin | Eric Melvin Scott Gahn | Peggy Mahoney | Jeff Dasovich | Denise Furey | Don Black Meredith Eggleston |
| 1 | Establish Active PG&E Account List (by book, by customer) |  |  |  |  |  |  |  |  |  |
| 2 | Establish Active SCE Account List (by book, by customer) |  |  |  |  |  |  |  |  |  |
| 3 | Analyze Financial Exposure with PG&E (by book, by customer) |  |  |  |  |  |  |  |  |  |
| 4 | Analyze Financial Exposure with SCE (by book, by customer) |  |  |  |  |  |  |  |  |  |
| 5 | Coordinate State and Federal Regulatory Issues |  |  |  |  |  |  |  |  |  |
| 6 ## Work in Progress | Prepare Disconnect DASRs (D-DASR) for PG&E |  |  |  |  |  |  |  |  |  |
| 6B | Prepare Disconnect DASRs (D-DASR) for SCE |  |  |  |  |  |  |  |  |  |
| 7 | Establish Transmission Protocols (Send & Confirm Receipt) for PG&E |  |  |  |  |  |  |  |  |  |
| 7B | Establish Transmission Protocols (Send & Confirm Receipt) for SCE |  |  |  |  |  |  |  |  |  |
| 8 | Draft Customer Communication Letter |  |  |  |  |  |  |  |  |  |
| 9 | Approve Customer Communication Letter |  |  |  |  |  |  |  |  |  |
| 10 | Establish Confidentiality with PG&E |  |  |  |  |  |  |  |  |  |
| 11 | Segment Customers into Opportunity Categories for PG&E |  |  |  |  |  |  |  |  |  |
| 11B | Segment Customers into Opportunity Categories for SCE |  |  |  |  |  |  |  |  |  |
| 12 | Define Customer Specific “new” Products/Strategies |  |  |  |  |  |  |  |  |  |
| 13 | Approve Customer Specific “new” Products/Strategies |  |  |  |  |  |  |  |  |  |
| 14 | Coordinate Switching, Metering, Billing & Settlement Logistics with PG&E (negotiate transition plan) |  |  |  |  |  |  |  |  |  |
| 15 | Document PG&E Accountability for all active accounts as of 02/01/01 (in writing) |  |  |  |  |  |  |  |  |  |
| 16 ## Work in Progress | Coordinate Switching, Metering, Billing & Settlement Logistics with SCE (detail transition plan) |  |  |  |  |  |  |  |  |  |
| 17 | Final Decision to D-DASR all PG&E non-residential Accounts |  |  |  |  |  |  |  |  |  |
| 18 | Final Decision to D-DASR all SCE non-residential Accounts |  |  |  |  |  |  |  |  |  |
| 18A | Send D-DASR Transmission to PG&E |  |  |  |  |  |  |  |  |  |
| 19 | Send Customer Communication Letters |  |  |  |  |  |  |  |  |  |
| 20 | Confirm D-DASR Receipt |  |  |  |  |  |  |  |  |  |
| 21 | Implement Transition Plan w/PG&E |  |  |  |  |  |  |  |  |  |
| 22 | Schedule Customer Contact Meetings |  |  |  |  |  |  |  |  |  |
| 23 | Propose Customer Specific Contract Amendments/Changes |  |  |  |  |  |  |  |  |  |
| 24 | Document Customer Specific Contract Amendments/Changes |  |  |  |  |  |  |  |  |  |

## Work in Progress