CHANGE ORDER NUMBER 1

to

PURCHASE CONTRACT US-398-LM6K-2001

By and Between

WESTDEUTSCHE LANDESBANK GIROZENTRALE, NEW YORK BRANCH

ACTING THROUGH ITS AGENT

ENRON NORTH AMERICA CORP.

AND

ABB POWER T & D COMPANY, INC.

For The Purchase Of

POWER TRANSFORMER PACKAGES

CHANGE ORDER NUMBER 1

PART I  REQUIREMENTS

1.	In accordance with Contract US-398-LM6000-2001, Article 11, the parties hereby agree to amend the Agreement to include all changes set forth in this Change Order Number 1.

2.	Summary of Changes:

# Upon payment to Seller of $3,701,640.00 as calculated in this Change Order Number 1, Agent and Seller agree to the cancellation of Units LNL 9517-5 and LNL9517-6, and that the Purchase Amount less the Retention Amount as of the date hereof is hereby paid in full for as set forth below.

PART II COST

1.	The cost for the changes to the scope of supply as set forth in PART I shall change the Purchase Amount as set forth herein.

- Summary of Cancellation Charges and Purchase Amount Deduct:

a. Cancellation Charge for Units LNL9517-5 & LNL9517-6		    	        $323,200

b. Purchase Amount Deduct for Units LNL9517-5 & LNL9517-6		   ($1,572,000)

3.	Summary of the Purchase Amount:

a. Purchase Amount:	$7,404,600.00

b. Less Deduct for Units LNL9517-5 & LNL9517-6:		      	          ($1,572,000.00)

c. Purchase Amount after Cancellation of

Units LNL9517-5 & LNL9517-6:		             $5,832,600.00

- Summary of Change Order #1 Payment:

a. Purchase Amount after Cancellation of

Units LNL9517-5 & LNL9517-6:	             $5,832,600.00

b. Less Progress Payments made to date*:                                                  ($1,840,900.00)

(*excludes progress payments of $176,800.00 made on Units LNL9517-5 & LNL9517-6)

c. Cancellation Charge for Units LNL9517-5 & LNL9517-6:	    $323,200

d. Less early payment discount:                                                           	($30,000.00)

e. Less Retained Amount:                                                                            	($583,260.00)

f. Total Change Order #1 Payment:                                                   	$3,701,640.00

- Upon execution of this Change Order Number 1, the Purchase Amount for LM6000-2001 shall be decreased to Five Million Eight Hundred Thirty-Two Thousand Six Hundred U.S. dollars ($5,832,600.00). The total Change Order Number 1 Payment of $3,701,640.00 shall be due and payable upon execution of this Change Order, which satisfies all payments of the Purchase Amount as of the date hereof other than the Retained Amount. Seller acknowledges that upon payment of the Change Order #1 Payment, Purchaser shall be entitled to assign any rights and obligations under the Agreement to any party, including E-Next Generation LLC, CA Energy Development II, and/or Brazilian Power Development Trust.

PART III TERMS AND CONDITIONS

- The terms and conditions of this Change Order are as set forth in the Agreement are incorporated herein by reference and shall apply with respect to the rights and obligations of the parties under this Change Order Number 1.  Unless otherwise expressly defined or modified by the terms herein, all capitalized terms in this Change Order Number 1 shall be as stipulated in the Agreement.

- All other terms and conditions of the Agreement remain unchanged and in full force and effect.

3.	The effective date of this Change Order Number 1 shall be December 11, 2000.

REMAINDER OF THE PAGE LEFT INTENTIONALLY BLANK

Agreed and Accepted:

Enron North America Corp., as Agent for

Westdeutsche Landesbank Gironzentrale, New York Branch

By:

Title:

Date:

ABB Power T & D COMPANY, as Seller

By:

Title:

Date: