|  | Page/Section | Suggested Change | Comment | Disposition |
| --- | --- | --- | --- | --- |
| 1 | 10/Delivery Point def/n | Revert to original language or integrate site change mechanism (2.1 (c)) | Deal is for Purchaser to have until 6 months prior to delivery to specify site |  |
| 2 | 10/Earliest delivery date | Capture “no sooner than” concept somewhere in agreement | Purchaser should not be obligated to have site ready until after a specified date |  |
| 3 | 10/Direct fuelcell defn | Relate to a specification. |  |  |
| 4 | 10/Equipment | Broaden def’n to include Units plus BOP | Too confusing. |  |
| 5 | 10/Expected Delivery | Delete “major”. | Need standard for when delivery has been achieved. |  |
| 6 | 11/Guaranteed Acceptance Date | Incorporate delivery schedule which is applicable to orders released prior to 3/1/01. | Need to better capture commercial deal. |  |
| 7 | 11/Heat Rate | Specify location of measurement. | Need clarity. |  |
| 8 | 11/Heat Rate Guarantee | Retain def’n. | Need it for performance section. |  |
| 9 | 11/Maximum Output | Replace with Electrical Output and Guaranteed Output. | Need for price for performance section. |  |
| 10 | 11/O&M Spares | Need conceptual list at signing reinstated. | Reflects prior agreement. |  |
| 11 | 11/Preliminary Specification | Add definition. | Need to clarify specification development process. |  |
| 12 | 11/Punchlist | Retain definition, insert retention concept. | Reflects prior agreement. |  |
| 13 | 13/Scope of Work | Retain concept of Equipment/Units, delete reference to Purchaser. | Clarity, accuracy. |  |
| 14 | 13/Specifications | Concept needs development. |  |  |
| 15 | 15/2.1 | Delete Scope of Work reference | Purchaser’s responsibilities are separate from Seller’s scope. |  |
| 16 | 15/2.1 (c) | See comment 1. | Inconsistent with Seller’s requested changes. |  |
| 17 | 15/2.1 (e) | Delete “and other site…” | Too broad. Exhibit should describe Purchaser’s site responsibilities. |  |
| 18 | 15/2.1 (g) | Clarify for which units/models. | Clarity needed. |  |
| 19 | 16/ (b) and (c) | Delete. | (c) impossible to comply with due to size of organizations involved. |  |
| 20 | 17/3.1 (1st paragraph) | Retain original language. | Standard turnkey language. |  |
| 21 | 17/3.1 (2nd paragraph) | Change “or” to “and” in line 4. Also need to discuss changes in specs and impact of long lead items and permits. |  |  |
| 22 | 17/3.2.1 | Need “no earlier than” concept for delivery; obligation not limited to commercially reasonable efforts. | Needs to reflect agreement; obligation to perform not limited to commercial reasaonable standard. |  |
| 23 | 17/3.3 & 18/3.3(d) | Delete need for request from Purchaser. |  |  |
| 24 | 18/3.4, generally | Need to understand requested changes. |  |  |
| 25 | 18/3.4(c) | Retain “arising out of” and delete “of the circumstances...3.4”; insert “Seller’s use of hazardous materials”. | A compromise. |  |
| 26 | 19/3.5 | Delete “commercially reasonable efforts”, delete last sentence. | A compromise. |  |
| 27 | 19/3.7(a) | Retain sentence beginning on line 12; retain “Purchaser” on line 17; other requested changes accepted. | A compromise. |  |
| 28 | 20/3.7(b)(2) | Retain “Purchaser” on line 3;other requested changes acceptable. |  |  |
| 29 | 20/3.7(c) | Retain “Purchaser” on line 2. | This is a purchaser decision. |  |
| 30 | 20/3.7 |  |  |  |