#### Station Electrical Construction

Enron North America will install coal bed methane gathering systems in Northeast Wyoming during the fourth quarter of 1999. For the purpose of selecting a contractor(s) to do that work, we are soliciting a proposal for an electrical construction contractor to construct those facilities.

# Job Scope

The scope of work for this section is the electrical work to be performed at the facilities described in the section following. At this time, the scope of facilities to be constructed are as follows:

## Box Draw Compressor Station

Located approximately 10 miles northwest of Gillette, Wyoming (in Sec. 3, R73W/T51N), this compressor station is located on a new site and consists of:

- Gas Inlet Facilities, including pig receiver and slug catcher

- (2) Waukesha 7044/Arial Compressor (1600 HP nominal) skids – (Hanover packages)

- (1) Gas Dehydration skid – (J.W. Williams package)

- Electrical service provided by the local utility

- Gas Measurement

## Maverick Compressor Station

Located near I-90, Mile Post 102 (Sec. 32, T49N/R75W), this compressor station is located on a True Oil facility site that is largely inactive. This station consists of:

- (2) Caterpillar 3516/Arial Compressor (1000 HP nominal) skids – (Hanover packages)

- Electrical service provided by the local utility

- Gas Measurement

## Hannum Compressor Station

Located approximately 25 miles south and east (in Sec. 9, R47N/T73W),of the Maverick Compressor Station, this compressor station is located on a new site and consists of:

- Gas Inlet Facilities, including pig receiver and slug catcher

- (2) Waukesha 7044/Arial Compressor (1600 HP nominal) skids – (Hanover packages)

- (1) Gas Dehydration skid – (J.W. Williams package)

- Electrical service provided by the local utility

- Gas Measurement

## Billy Creek  Receipt Point

Located approximately 3 miles south of the Maverick Compressor Station, this meter site is the interconnection of the gas from the Maverick Compressor Station into the Ft. Union Pipeline. This site will be located adjacent to metering facilities from at least two other companies, as well as Ft. Union Pipeline facilities. This receipt point consists of:

- Gas Filter Skid; A pre-fabricated skid containing a gas filter and associated valving.

- Gas Meter Skid; A pre-fabricated skid containing a gas turbine meter, flow control valve and associated valving.

- RTU Building; A pre-fabricated building containing analyzers and SCADA systems.

- Electrical service provided by the local utility

## Hawk Point  Receipt Point

Located in proximity to the Hannum Compressor Station (SE ¼ - Sec. 8, T47N/R73W), this meter site is the interconnection of the gas from the Hannum Compressor Station into the Ft. Union Pipeline. This site will be located adjacent to metering facilities from one other company. This receipt point consists of:

- Gas Filter Skid; A pre-fabricated skid containing a gas filter and associated valving.

- Gas Meter Skid; A pre-fabricated skid containing a gas turbine meter, flow control valve and associated valving.

- RTU Building; A pre-fabricated building containing analyzers and SCADA systems.

- Electrical service provided by the local utility

## Wild Horse  Receipt Point

Located SWNW, Sec 28, T46N/R73W, this meter site is the interconnection of the gas from a compressor station installed by others into the Ft. Union Pipeline. This site will be located at a new site, not adjacent to any other facilities. This receipt point consists of:

- Gas Filter Skid; A pre-fabricated skid containing a gas filter and associated valving.

- Gas Meter Skid; A pre-fabricated skid containing a gas turbine meter, flow control valve and associated valving.

- RTU Building; A pre-fabricated building containing analyzers and SCADA systems.

- Electrical service provided by the local utility

### Job Specifics

The projects noted above will be conducted in the following circumstances:

- It is the desire of Enron to have one electrical contractor perform the work on all three stations and receipt points. However, Enron reserves the right to award  a single compressor station to a 2nd electrical contractor.

- The current construction schedule for the compressor stations is as follows:

- Box Draw Compressor Station

- Site work begin on Oct. 11, 1999.

- Electrical work begins on Nov. 1, 1999

- Compressor Delivery; Available Sept. 15, 1999

- Dehydrator Skids; Available October 4, 1999

- Electrical completion required on December 3, 1999

- Maverick Compressor Station

- Site work begin on Oct. 18, 1999.

- Electrical work begins on Nov. 8, 1999

- Compressor Delivery; Available Sept. 15, 1999

- Dehydrator Skids; Available October 4, 1999

- Electrical completion required on December 10, 1999

- Hannum Compressor Station

- Site work begin on Nov 1, 1999.

- Electrical work begins on Nov. 22, 1999

- Compressor Delivery; Available Sept. 15, 1999

- Dehydrator Skids; Available October 4, 1999

- Electrical completion required on Jan. 7, 2000

- Billy Creek Receipt Point

- Site work begin on Nov 8, 1999.

- Electrical work begins on Nov. 17, 1999

- Skids & RTU Building; Available Oct. 22, 1999

- Electrical completion required on Dec. 1, 1999

- Hawk Point Receipt Point

- Site work begin on Nov 29, 1999.

- Electrical work begins on Dec. 8, 1999

- Skids & RTU Building; Available Oct. 22, 1999

- Electrical completion required on Dec. 20, 1999

- Wild Horse Receipt Point

- Site work begin on Oct. 18, 1999.

- Site work begins on Oct. 27, 1999

- Skids & RTU Building; Available Oct. 22, 1999

- Electrical completion required on Nov. 12, 1999

- All materials, except those specifically called out as being supplied by the Contractor, will be provided by Enron.

- Enron supplied materials will be delivered to the site, with the Contractor responsible for off loading and assuming responsibility for the equipment upon delivery.

- Materials to be supplied by the Contractor are:

- All conduit, wire and fittings. Purchased by Contractor, invoiced to Enron.

- All necessary tools.

- Instrumentation, including tubing work, will be installed by the Mechanical/Civil Contractor.

- Enron will supply an on site Company Representative who will be the Contractor’s  contact for work at that site. Other technical or inspection support will be provided as required. The Contractor will be responsible for on site supervision and work direction of their labor force.

### Bid Conditions

Based on existing time constraints, it is not possible to provide bid packages of sufficient quality that Enron can ask for fixed price bids. It is Enron’s intent that the Work included in this scope shall be done under a rate sheet arrangement with the chosen Contractor(s).

In order to put a Contractor(s) in place for this work, Enron will conduct a selection process. Enron is asking for proposals from Contractors interested in being considered for this work.  Enron asks the Contractor to provide the following material in their proposal:

- Provide a rate sheet of labor and equipment costs that will be applicable for the work included in this scope of work.

- Provide a percentage markup for the material purchased by the Contractor and invoiced to Enron for use on this job, i.e. conduit, wire and fittings.

- Provide a resume of the individual who will be the Contractors manager or superintendent for all construction included in this scope of work.

- Included in this package is a set of drawings for a compressor station titled “Dry Creek Compressor Station”. This station is similar to the stations that will be constructed for Enron. Assume that the Contractor will have a set of drawings to build from of similar quality. The Bidders will provide the following:

- Provide an estimated cost of construction for this station, labor & equipment costs only.

- Provide a fixed price for mobilization costs, if applicable,  to do the work on the schedule given in this document.

- The estimate provided by the Contractor will not include the following:

- Cost of materials supplied by the Contractor, i.e. conduit, wire and fittings.

- Included in this package is a set of drawings for  the Hawk Point Receipt Point. This is the drawing set for the receipt point to be constructed for Enron. The Bidders will provide the following:

- This is the construction set of drawings that will be provided for the Hawk Point Receipt Point to be built by the Contractor.

- Provide an estimated cost of construction for this station, labor & equipment costs only.

- Do not include the cost of materials supplied by the Contractor, i.e. conduit, wire and fittings.

- Please note that the skids and the work on those skids are provided complete by Enron.

- Included in this package is a set of construction standards to be used on the scope of work. The individual standards that apply to the scope of work are as follows:

- Electrical Specification

- Instrument Specification (as applicable)

Upon receipt of these materials, Enron will determine a short list of potential Contractors. Within two weeks following receipt of these materials, Enron will interview that short list. It is important that the proposed Contractor’s Construction Manager for the work be at that interview.

The interview will be held in Denver, either at Enron or at Forerunner’s offices. Based on that interview, Enron expects to award the work the following work, with mobilization  to proceed thereafter to meet the schedules noted.