ENRON RISK ASSESSMENT AND CONTROL

DEAL APPROVAL SHEET

| DEAL NAME: SALSA (3) Counterparty: ABB Power Systems Business Unit: Americas East Origination Business Unit Originator: Ozzie Pagan Public Private Merchant Strategic Conforming Nonconforming | Date DASH Completed: March 8, 2000 RAC Underwriter / Analyst: Chip Schneider / Ethel Koskas Investment Type: Structured Off-take Agreement Capital Funding Source(s): Bridge Financing-Condor LT Financing –Project Financing or other Off B/S Financing Expected Closing Date: March 31, 2001 Expected Funding Date: March 31, 2001 Board Approval: Pending Received Denied N/A |
| --- | --- |

RAC Recommendation: Proceed with Transaction    Returns below Capital Price   Do not Proceed

#### APPROVAL AMOUNT REQUESTED

# EXPOSURE SUMMARY

Current exposure					$   3.6 million

This Request					$ 72.4 million

Total					$ 76.0 million

## RETURN SUMMARY

| Return Components: | PV @ Capital Price | ### Cumulative ### IRR |  | Capital Price Components |  |
| --- | --- | --- | --- | --- | --- |
| Cash Outflows | ($ 74,607) | N/A |  | Risk free rate (%): | 6.50% |
| Cash Inflows |  | N/A |  | Equity/Credit premium (%): |  |
|  |  | N/A |  | Country Premium (%): |  |
|  |  |  |  | Transaction-Specific (%): | 3.50% |
| Total NPV | ($11,447) | N/A |  | RAC CAPITAL PRICE: | 10.00% |

The NPV represents the PV of the revenue payments paid to the Project by Enron, less the PV of the capacity tariff and other operating fees paid to BPUB, over a 25-year period.  An all-in unlevered discount rate of 10% has been used to reflect turnkey construction risk under the ABB Contract, operating risk of BPUB and payment risk of Enron as sole off-taker of the DC-tie transmission capacity.

## DEAL DESCRIPTION

Project Overview

According to Mexican government officials, industrial customers and market observations, Mexico is currently experiencing significant electric supply constraints due to both a lack of adequate transmission capacity and a lack of generation capacity. Historically, Mexican industrial companies have been required to purchase electricity from the government-owned electric utility, Comisíon Federal de Electricidad (“CFE”).  Large retail consumers have therefore been forced to deal with an indifferent electricity provider, poor reliability, escalating tariffs and significant price fluctuations as a result of the CFE’s monopolistic position.  In 1992, Mexican industrial companies were allowed to either self-generate or import power for their own use.

Given the imbalance in supply and demand and to take advantage of existing regulations, Enron Americas [VIA A FINANCING DESIGNEE] intends to enter into power supply arrangements with large Mexican consumers and construct a transmission link to transport up to 300MWs of continuous base load power from the Texas power market (“ERCOT”) to the CFE grid in Mexico, south of Brownsville, Texas.

The U.S. and Mexican power transmission grids are not directly connected as each power grid is operated in different electrical phases and, consequently, are unsafe to connect together until synchronized.  To Americas transportation of power between the two grids, Enron Americas is proposing to construct a High Voltage Direct Current Tie (“HVDC Tie”) to convert high voltage AC electric current to high voltage DC electric current and then re-converts the DC electric current to AC electric current compatible with the intended market.  The HVDC Tie will be constructed  [VIA A FINANCING DESIGNEE] by ABB Power Systems under a fixed-price turn-key contract.

Business Rationale

Electricity demand in Mexico has grown at an average annual rate of 5.3% between 1989 to 1998. There are five primary types of customers: industrial (60% of energy sales), residential (23%), commercial (7%), agricultural (6%), and public services (4%).  Historically, energy sales growth has been driven mainly by the industrial customer base.  CFE forecasts 5.6% growth in electricity demand over the next ten years, with demand in the regions across the border from Texas expected to grow at an average of over 6%.

This high demand growth rate has been seen first hand by the Americas Mexico Group (“Americas Mexico”).  Americas’s Mexican industrial customers have expressed a strong desire for reliable sources of electricity.  Americas Mexico has executed one PPA and is in the process of negotiating other PPA’s representing demand of approximately 100-180MWs. Additional Mexican targets have been identified.

Mexican industrials have reached conceptual agreement to pay Americas a monthly capacity payment and energy charge under terms set forth in the PPA’s for delivered power. The capacity payment would be payable under all circumstances, including those arising under force majeure.  The term of the typical PPA is expected to be 15 years.  Americas’ responsibility for delivering power to the Mexican customers would end at the border.  The Mexican customer would be responsible for working with the CFE to “wheel” the power from the border to customer locations inside of Mexico.

$51.5MM

Operation of the HVDC Tie

The HVDC Tie will be located at or near the Loma Alta substation (“Loma Alta”) which is approximately 4.9 miles inside the U.S. (see Exhibit 1 above).  The HVDC Project also includes associated improvements.  These associated improvements include a 138-kV AC line, 150-kV DC line, a 230-kV AC line, rights-of-way, lease and/or purchase of land, and requisite interconnects to and systems upgrades in both the BPUB and CFE electrical power transmission and distribution systems.  Quail Energy, L.P., a Whitewing L.P. (Condor) entity,  will own the HVDC Tie and associated improvements during construction.  Enron does not intend to own the HVDC Tie and associated improvements subsequent to the commercial operation date (“COD”) due to PUHCA regulatory issues surrounding the ownership of transmission assets.  The Brownsville Public Utility Board (“BPUB”), the owner and operator of the Loma Alta substation (69kv side, CP&L and Magic Valley own the 138kv side of the substation), [see Project Salsa DASH dated 9/29/00 attached], will own the HVDC Tie and associated improvements once it becomes operational.  Table 1 below illustrates the anticipated construction and financing schedule for the HVDC Tie:

Table 1

Project Salsa Financing Milestones

| Milestone | Date |
| --- | --- |
| 1. Americas executed EPC Contract with ABB | October 27, 2000 |
| 2. Americas gave notice to proceed to ABB and amends EPC contract to provide for $250,000 cancellation fee if cancelled on or before December 22. | December 1, 2000 |
| 3. Americas paid ABB option premium of $3.0MM to move the optional cancellation date with total cancellation fees and exposure limited to this $3.0MM if Americas cancels contract by February 1, 2000. | December 26, 2000 |
| 4. Americas extends optional cancellation date with ABB to 4/1/02 in exchange for pushing HVDC in-service date to 6/1/02 | January 31,2002 |
| 4. Americas transfers contract to Quail Energy LLC, a Whitewing (Condor) owned financing entity, until long term, off-balance sheet financing can be put in place. | March 31, 2002 |
| 5. Off balance sheet financing group “buys” equity of Quail Energy LLC from Condor and provides financing through substantial completion date. | June 2002 |
| 4. Substantial Completion is achieved | [______], 2002 |
| 5. Quail Energy “sells” HVDC Tie and associated improvements to BPUB in exchange for 25 year transmission agreement | June, 2002 |
| 6. Commercial operations begin | June, 2002 |

Construction

ABB will provide engineering, manufacturing, construction, testing and commissioning of two HVDC Light Converter Stations.  ABB is also one of only two companies in the world marketing the “HVDC Light” technology required to transfer relatively high electrical loads.

In addition to the direct costs of the HVDC Tie, other requirements include approximately $14.9 million associated with (1) the construction of AC and DC transmission lines (the “AC/DC Transmission Lines”) connecting the HVDC Tie with the Loma Alta substation in the U.S. and CFE’s substation in Mexico (approximately 13 miles)($4.5MM); (2) network upgrades to the BPUB and CFE transmission system required by ERCOT, CFE and BPUB for capacity and reliability purposes ($3.2MM); (3) the acquisition of land leases in the U.S. and right-of-ways (ROWs) in the U.S. and Mexico ($0.7MM), and (4) other upgrades and soft costs (e.g. 230/138kv substations, engineering consulting, legal fees, etc.) ($6.5MM).

Enron Americas gave a terminable notice-to-proceed to ABB on December 1, 2000.  The EPC contract was amended at that time to (a) move back the initial construction draw payment of approximately $5.0MM to December 26, 2000; and (b) provide for payment of a $250,000 cancellation fee by Enron Americas if Enron Americas cancels the contract on or before December 22, 2000.

The CFE, largely as a result of the political ramifications of the administration change in Mexico, has taken longer than expected to (a) estimate wheeling costs from the border delivery point to potential customer locations, and (b) process permits for interconnection.  Therefore, in late December 2000 Enron Americas negotiated with ABB to, in exchange for a non-refundable option premium of $3.0MM, amend the EPC Contract to provide for the purchase of an option to cancel the EPC Contract at any time before 5:00 pm (Houston, Texas time), February 1, 2001 (the "Optional Cancellation Deadline"), without payment of any cancellation fees.  Further delays by the CFE prompted additional negotiations with ABB in late January 2001.   At that time, Enron Americas extracted a concession from ABB whereby the Optional Cancellation Deadline was extended to April 1, 2001.  In exchange for this concession, the HVDC in-service date was moved from April 1, 2002 to June 1, 2002.

## TRANSACTION SOURCES AND USES OF FUNDS ($ millions)

|  | Sources |  |  | Uses |
| --- | --- | --- | --- | --- |
| Quail Energy | $69.1 |  | HVDC Tie & Upgrades | $66.4 |
| Enron Americas* | $3.0 |  | Option Premium | $3.0 |
| Enron Americas (PV) | $3.9 |  | BPUB Fees (PV) | $3.9 |
|  |  |  | Other | $2.7 |
| Total | $76.0 |  |  | $76.0 |

## * to be refunded by Condor upon full funding.

## TRANSACTION UPSIDES/OPTIONALITY

- Americas expects that the typical PPA will include a 5-8% call-back on 100% availability.  This will allow Americas to call back power from the industrials during peak times in the ERCOT market, creating value for Enron.

- Current PPA’s are expected to have 15-year tenors.  Americas will have an additional 10 years of transmission capacity after the current contemplated PPA’s expire.

- To the extent all capacity on the HVDC Tie is not utilized immediately by long-term customers, excess capacity could be sold on the spot market.  The nearest comparable is a 36MW HVDC tie located at Eagle Pass, TX where capacity sells for approximately $14.00/Mwh.  NOTE –Due to the relatively small size of this comparable, the trading price may not be directly transferable to a 300MW HVDC Tie, however it does tend to indicate that a spot market for such capacity exists.

- This transaction represents a significant strategic step for Enron to be a first mover in the Mexican power market.  Opportunities to become a significant power merchant in Mexico, complementing Enron’s position in the U.S. and nascent position in Canada, may create significant additional value.

EXIT STRATEGY

## RISK MATRIX

| DESCRIPTION | MITIGATION/COMMENTS |
| --- | --- |
| CFE Interconnection Risk | - Enron Americas has successfully negotiated interconnection agreements with the CFE on the Vitro Power Project. This experience will be utilized to effectively replicate the process in this case – instead of interconnecting with a plant, they would interconnect with the HVDC Tie. Futhermore, BPUB has already worked through the process of interconnecting with the CFE (they currently have a letter of intent with the CFE to interconnect their power plant via a radial transmission line). - Any firm power supply agreements would contain conditions precedent language requiring proper interconnection relationships prior to Americas responsibility for power delivery. - Force majeure language in proposed contract would provide for day-to-day delay in power delivery if there were delays in receiving proper agreements or permits. |
| Presidential Permit Risk | Bracewell & Patterson due diligence (see attached memo) indicates that Presidential Permits have been issued to 78 border crossing facilities between 1977 and the present. During this time period, the Department of Energy ("DOE") has never denied a requested permit (although some permits have been withdrawn by the applicant). Potential environmental impact of the asset on the construction site is the primary issues that could delay reception of the Presidential Permit. The following mitigants exist: - The most likely right-of-way for the transmission lines are inside of ROW for which the Port of Brownsville has already applied for a Presidential Permit (from the U.S. State Department for an international bridge). - DOE action must comply with NEPA (National Environmental Protection Act). 2 possible environmental studies must be completed prior to granting of Presidential Permit: - Environmental Assessment – least onerous in terms of timing. Environmental assessments have been completed or are in process at each of the proposed HVDC Tie sites. - Environmental Impact Study– most onerous in terms of timing. Could take as long as 18 months. This occurs when for example, Native American burial grounds exist on the construction site. DOE has indicated that this is an unlikely scenario. - The Presidential Permit is required before construction can begin on the construction site. Site access (on the HVDC Tie) is not required by the construction contractors until [???]. Site access for the AC transmission lines is not expected to be critical due to the relatively short lead times required by transmission line construction projects. Bracewell & Patterson indicates that as long as no significant environmental impacts exist, the permit should be granted inside of six months. - In the event significant delays occur, timing issues with receiving the Presidential Permit could potentially fall under Force Majeure provisions in the EPC Contract. - If the presidential permit is NOT granted at the contemplated site, Americas has conducted initial due diligence at 2 additional site locations. However, these locations would necessitate going back to the CFE in order to analyze new injection points. |
| Right-of-way Acquisition Risk | According to the Project Participation Agreement entered into with BPUB, BPUB is responsible for acquiring all ROW (which Enron will reimburse them for). In the case of the Loma Alta substation, the ROW is owned by a sister organization – the Port of Brownsville. All currently envisioned ROW and easements are now in control of BPUB (via payment by Americas). |
| Construction & Technology Risk | - HVDC Tie construction: Turnkey project – ABB bears a significant portion of the construction risk. If ABB does not deliver by April 2002 (assuming necessary site access exists) ABB must pay liquidated damages for delay. Relative to Enron’s exposure for delay past the COD, ABB’s exposure is 1/3 for the first month, 1/2 for the second month, and 100% thereafter. Americas’s estimates its potential exposure would be approximately $2.0MM in month one and 1.0MM in month 2 after ABB’s payments. Dollar exposure in each of months one and two. - Interconnection – The 138kv bus of the Loma Alta substation is not owned by BPUB – it is owned by CP&L and Magic Valley. BPUB will be the interconnecting party since it will be the owner and operator of the HVDC Tie and associated improvements. BPUB already has a relationship with these parties. - Associated improvements – The engineering and construction of the transmission lines and requisite interconnects to and systems upgrades in both the BPUB and CFE electrical power transmission and distribution systems will be conducted by third-party contractors selected by Enron. These contracts will be structured to shift performance and delay risk to the selected contractors. While cost estimates on the Mexican side are believed to be conservative, there are no assurances these estimates are exact. However, Enron de Mexico’s experience with the Vitro project indicates that the CFE’s requirements fell generally in line with Enron engineering estimates. - The HVDC station will utilize “HVDC Light” technology. This technology, while relatively new, is expected to be reliable and operate within acceptable parameters (see EE&CC white-paper technology analysis attached). |
| Regulatory Risk | - The parties are relying on Sec. 163 of the Public Utility Code, which states that public and private entities may join together to develop electric generating facilities without complying with public bid requirements. This structure is similar to that used by the Austin Energy transaction. - The transmission lines into South Texas are currently constrained physically with respect to available transmission capacity (ATC). Studies conducted by outside consultants hired by Americas indicate that up to 166MW of ATC currently exists, and up to 300 MW of ATC potentially exists IF special protection schemes (SPS’s) are implemented. SPS’s call for load to curtail if dangerous or unstable transmission constraints occur in the system. Such curtailment would only occur in a Force Majeure event and should be covered under contemplated power supply agreements. Furthermore, meetings with the ERCOT ISO indicate that (a) SPS’s are possible for HVDC loads in South Texas, (b) the ERCOT ISO is planning to upgrade the constrained transmission line in 2003. For conservatism, financial modeling has assumed upgrades will only occur after 2005. |

# KEY SUCCESS FACTORS

|  | NA | # Poor | ##### Excellent |
| --- | --- | --- | --- |
| Core Business |  |  | X |
| Strategic Fit |  |  | X |
| Upside Potential |  |  | X |
| Management | X |  |  |
| Risk Mitigation |  | X |  |

OTHER RAC COMMENTS

The need for reliable base load and peak power in the rapidly growing northern region of Mexico, combined with expected competitively priced supplies of generation capacity in Texas (ERCOT), provides a reasonably sound rationale for investment in the Salsa project.  Enron America’s marketing efforts have yielded at least three long-term opportunities to market power to industrial consumers in northern Mexico.

Critical to the success of Salsa is the ability of Enron Americas to complete the permitting process, procure the necessary right-of-way, complete the construction of the tie-line on schedule/within budget and identify additional demand in the northern Mexican market.  RAC strongly recommends that Enron Americas management closely monitor the permitting process to ensure timely receipt of necessary clearances and match progress with a warranted amount of capital exposure.

CONDITIONS PRECEDENT

Conditions precedent to the execution of authority requested in this DASH:

- Final agreement with CFE on transmission tariffs, substation preference, upgrades and downstream constraints.

- Satisfactory due diligence by RAC on all regulatory matters related to FERC, PUCT, ERCOT and CRE.

- Creation of a “transmission price curve” for this capacity.

- Execution of necessary amendments to existing PPAs and MOUs.

MILESTONES

- Receipt of CFE Interconnect Agreement				03/31/01

- Notice to Proceed under EPC Contract				upon occurrence

- Project Status Report						calendar quarter-end beginning 06/30/01

| # APPROVALS |  | Name |  | Signature |  | Date |
| --- | --- | --- | --- | --- | --- | --- |
| East Origination |  | Ozzie Pagan |  |  |  |  |
| Regional Management |  | Kevin Presto |  |  |  |  |
| Americas Legal |  | Mark Haedicke |  |  |  |  |
| Americas Tech Services |  | Brian Redmond |  |  |  |  |
| Americas Accounting |  | Wes Caldwell |  |  |  |  |
| Americas Management |  | John Lavorato/Louise Kitchen |  |  |  |  |
| RAC Management |  | Rick Buy/Dave Gorte |  |  |  |  |
| ENE Global Finance |  | Andy Fastow/Ben Glisan |  |  |  |  |
| ENE Management |  | Jeff Skilling |  |  |  |  |

[NEED A FASH!]