ENRON RISK ASSESSMENT AND CONTROL

DEAL APPROVAL SHEET

| DEAL NAME: Tex-Mex Counterparty: ABB Power Systems Business Unit: East Origination Business Unit Originator: Ozzie Pagan Public Private Merchant Strategic Conforming Nonconforming | Date DASH Completed: 8/1/00 more current date????? RAC Analyst: Anila Hoxha Investment Type: Capital Funding Source(s): Bridge Financing: Condor LT Financing : Off BS - TBD Expected Closing Date: 11/__/00 revised date????? Expected Funding Date: 11/__/00 revised date????? Board Approval: Pending Received Denied N/A |
| --- | --- |

RAC Recommendation: Proceed with Transaction    Returns below Capital Price   Do not Proceed

#### APPROVAL AMOUNT REQUESTED

Capital Commitment							$65.1MM

# EXPOSURE SUMMARY

ABB HVDC Facility Engineering, Manufacturing and Construction		              $50.2MM

###### Associated work with the HVDC Project			              $14.9MM

Total							 	$65.1MM

## DEAL DESCRIPTION

Project Overview

According to Mexican government officials and industrial customers, Mexico is currently experiencing significant electric supply problems due to both a lack of transmission capabilities and a lack of generation capacity.  In addition, Mexican industrial companies are required to purchase electricity from the government-owned electric utility, Comisíon (plz check spelling – I got this one from yesterday’s definition of “direct assignment facilities”).Federal de Electricidad (“CFE”). Industrial companies have been forced to deal with an indifferent electricity provider, poor reliability, escalating tariffs and significant price fluctuations as a result of the CFE’s near monopolistic position,

To capitalize on this situation, Enron North America (“ENA”) intends to (a) finalize Power Purchase Agreements (“PPAs”) with Mexican industrial customers who are very interested in signing the PPAs as they represent an economic and reliable source of electricity, and (b) construct a High Voltage Direct Current Tie (“HVDC Tie”) allowing for electric transmission of up to 300MWs of continuous base load power from the Texas power market (“ERCOT”) to the CFE Mexico transmission grid.

The U.S. and Mexican power transmission grids are not directly connected with each other.  Each power grid is operated in different electrical phases and consequently is unsafe to connect the two grids together unless synchronized.  To synchronize the two transmission grids, and thus allow for the transmission of electricity from one grid to the other, an HVDC Tie will be inserted to convert AC electric current to DC electric current and then reconverts the DC electric current to AC electric current compatible with the intended market.

Construction and Operation of the HVDC Tie

The HVDC Tie will be located at or near the Loma Alta substation (“Loma Alta”) which is approximately 4.9 miles (at closest point) inside the U.S. (see Schematic 2 below).  Additionally, associated improvements are included in the HVDC Project.  These associated improvements include: 138-kV AC, 150-kV DC (connects the two components of the HVDC Tie), and 230-kV AC electrical power transmission lines, rights-of-way, lease and/or purchase of land, and requisite interconnects to and systems upgrades in both the BPUB and CFE electrical power transmission and distribution systems.  ENA (via its financing designee or affiliate) will own the HVDC Tie and associated improvements during construction.  Enron does not intend to own the HVDC Tie and associated improvements subsequent to COD due to PUHCA regulatory issues surrounding the ownership of transmission assets.  Brownsville Public Utility Board (“BPUB”), the owner and operator of the Loma Alta substation (69kv side, CP&L and Magic Valley own the 138kv side of the substation), pursuant to the participation agreement executed between ENA and BPUB (see Project Salsa DASH dated 9/29/00 attached), will own the HVDC Tie and associated improvements once it becomes operational.  Table 1 below illustrates the anticipated construction and financing schedule for the HVDC Tie:

THIS SPACE INTENTIONALLY BLANK

Table 1

Project Salsa Financing Milestones

| Milestone | Date |
| --- | --- |
| 1. ENA executes EPC Contract with ABB | October 27, 2000 |
| 2. ENA gives notice to proceed to ABB and transfers contract to Condor for bridge financing until long term, off balance sheet structure can be created. Condor pays initial construction draw of [$5.0MM of $65.0MM]. | December 1, 2000 |
| 3. Off balance sheet entity (SPV) “buys” project from Condor and provides financing through substantial completion date. Condor has financed approximately [$15MM of $65MM]. | March __, 2000 |
| 4. Substantial Completion is achieved | April 2002 |
| 5. SPV “sells” HVDC Tie and associated improvements to BPUB in exchange for 25 year transmission agreement | April 2002 |
| 6. Commercial ops begin | April, 2002 |

Construction Specifics

ABB will, in exchange for $49,500,000 US dollars, provide engineering, manufacturing, construction, testing and commissioning of two HVDC Light Converter Stations (combined to form the HVDC Tie – see Schematic 1).  ABB is a respected industry player that has a long-standing relationship with ENA.  ABB is also 1 of only 2 companies in the world possessing the HVDC “Light” technology required to transfer relatively high electrical loads.

In addition to the costs directly associated with the HVDC Tie, there are associated improvements amounting to approximately $14.9 million associated with (1) the construction of AC and DC transmission lines (the “AC/DC Transmission Lines”) connecting the HVDC Tie with the Loma Alta substation and CFE’s substation (approximately 13 miles ($4.5MM)), (2) network upgrades to BPUB’s and CFE’s transmission system required by ERCOT, CFE and BPUB for electrical capacity and reliability purposes ( $3.2MM), (3) the acquisition of land leases in the U.S. and right-of-ways (ROWs) in the U.S. and Mexico necessary for the AC/DC Transmission Lines ($0.7MM), and (4) other upgrades, e.g. 230/138kv substations, engineering consulting, legal fees, etc. ($6.5MM).

Schematic 1

Location and Capital Costs of HVDC Tie

138KV AC Xmission Line (Power in phase with ERCOT)

HVDC Tie

USA

$50.2MM

Loma Alta Substation

$14.9MM

MEXICO

230KV AC Xmission Line (Power in phase with Mexico) on US and Mexico Side

Substation

To ENA Customers (Existing CFE Lines)

Demand

Electricity demand in Mexico has grown at an average of 5.3% between 1989 to 1998. There are five primary types of customers: industrial (60% of energy sales), residential (23%), commercial (7%), agricultural (6%), and public services (4%).  Historically, energy sales growth has been driven mainly by the industrial customer base.  CFE forecasts5.6% growth in electricity demand over the next ten years, with demand in the regions across the border from Texas expected to grow at an average of over 6%.

This high demand growth rate has been seen first hand by the ENA Mexico Group (“ENA Mexico”).  ENA’s Mexican industrial customers have expressed a strong desire for reliable sources of electricity.  Currently, ENA Mexico is in the process of closing PPAs representing demand of approximately 100-180MWs, with additional Mexican industrials identified as likely targets going forward.

Mexican industrials are expected to pay ENA a monthly capacity payment and energy charge under terms set forth in the PPA’s for delivered power. The capacity payment would be payable under all circumstances, including those arising under force majeur situations.  The term of the typical PPA is expected to be 15 years.  ENA’s responsibility for delivering power to the Mexican customers would end at the border.  The Mexican customer would be responsible for working with the CFE to “wheel” the power from the border to customer locations inside of Mexico.

## TRANSACTION SOURCES AND USES OF FUNDS

|  | Sources |  |  | Uses |
| --- | --- | --- | --- | --- |
| Capital Expense | $65.1 MM |  | HVDC Tie | $550.2MM |
|  |  |  | AC/DC Transmission, BPUB network upgrades & ROW | $14.9MM |
| Total | $65.1MM |  |  | $65.1MM |

## RETURN SUMMARY

## TRANSACTION UPSIDES/OPTIONALITY

- ENA expects that the typical PPA will include a 5-8% call-back on 100% availability.  This will allow ENA to call back power from the industrials during peak times in the ERCOT market, creating value for Enron.

- Current PPA’s are expected to have 15 year tenors.  ENA will have an additional 10 years of transmission capacity after the current contemplated PPA’s expire.

- The $15.5MM capital cost associated with the AC/DC Transmission and ROW development is most likely overstated for conservatism.  Preliminary estimates indicate that these costs could be as low as $10MM.

- To the extent all capacity on the HVDC Tie is not utilized immediately by long-term customers, excess capacity could be sold on the spot market.  The nearest comparable is a 36MW HVDC tie located at Eagle Pass, TX where capacity sells for approximately $14.00/Mwh.  NOTE –Due to the relatively small size of this comparable, the trading price may not be directly transferable to a 300MW HVDC Tie, however it does tend to indicate that a spot market for such capacity exists.

EXIT STRATEGY (Merchant investments only)

NA

## RISK MATRIX (Maximum 5)

| DESCRIPTION | MITIGATION/COMMENTS |
| --- | --- |
| ENA (via BPUB) is unable to interconnect with CFE. | - ENA Mexico has successfully negotiated interconnection agreements with the CFE on the Vitro Power Project. This experience will be utilized to effectively replicate the process in this case – instead of interconnecting with a plant, they would interconnect with the HVDC Tie. - Any firm power supply agreements would contain conditions precedent language requiring proper interconnection relationships prior to ENA responsibility for power delivery. - Force Majeure language in proposed contract would provide for day-to-day delay in power delivery if there are delays in receiving proper agreements or permits. |
| ENA does not receive or is delayed in securing Presidential Permit to export power. | Bracewell and Patterson due diligence (see attached memo) indicates that Presidential Permits have been issued to 78 border crossing facilities between 1977 and the present. During this time period, the Department of Energy ("DOE") has never denied a requested permit (although some permits have been withdrawn by the applicant). Potential environmental impact of the asset on the construction site is the primary issues that could delay reception of the Presidential Permit. The following mitigants exist: - The most likely right-of-way for the transmission lines are inside of ROW which the Port of Brownsville has already applied for a Presidential Permit (from Dept. of State for an international bridge). - DOE action must comply with NEPA. 2 possible environmental studies must be completed prior to granting of Presidential Permit: - Environmental Assessment – least onerous in terms of timing. Environmental assessments have been completed or are in process at each of the proposed HVDC Tie sites. - Environmental Impact Study– most onerous in terms of timing. Could take as long as 18 months. This occurs when for example, Native American burial grounds exist on the construction site. DOE has indicated that this is an unlikely scenario. - The Presidential Permit is required before construction can begin on the construction site. Site access (on the HVDC Tie) is not required by the construction contractors until mid-June. Site access for the AC transmission lines is not expected to be critical due to the relatively short lead times required by transmission line construction projects. Bracewell & Patterson indicates that as long as no significant environmental impacts exist, the permit should be granted inside of 6 months. - In the event significant delays occur, the customer commercial contacts indicate that the customers would be amenable to receiving power later than the 2/1/02 delivery date. Furthermore, timing issues with receiving the Presidential Permit would ideally fall under Force Majeure provisions in the contract. |
| ENA is unable to acquire ROW | According to the Project Participation Agreement entered into with BPUB, BPUB is responsible for acquiring all ROW (which Enron will reimburse them for). In the case of the Loma Alta substation, the ROW is owned by a sister organization – the Port of Brownsville. |
| Construction Risk | - HVDC Tie construction: Turnkey project – ABB bears a significant portion of the construction risk. If ABB does not deliver by April02 (assuming they have necessary site access) they must pay liquidated damages for delay. Relative to Enron’s exposure for delay past the COD, ABB’s exposure is 1/3 for the first month, 1/2 for the second month, and 100% thereafter. - Interconnection – The 138 bus of the Loma Alta substation is not owned by BPUB – it is owned by CP&L and Magic Valley. BPUB will be the interconnecting party since they will be the owner and operator of the HVDC Tie and associated improvements. BPUB already has a relationship with these parties. - Associated improvements – The engineering and construction of the transmission lines and requisite interconnects to and systems upgrades in both the BPUB and CFE electrical power transmission and distribution systems will be conducted by 3rd party contractors selected by Enron. These contracts will be structured to shift performance and delay risk to the selected contractors. - The HVDC station will utilized “HVDC Light” technology. This technology, while relatively new, is expected to be reliable and operate within acceptable parameters (see EE&CC white-paper technology analysis attached). |
| BPUB required to bid project | The parties are relying on Sec. 163 of the Public Utility Code, which states that public and private entities may join together to develop electric generating facilities without complying with public bid requirements. |

# KEY SUCCESS FACTORS

|  | NA | # Poor | # Fair | # Good | # Very Good | ##### Excellent |
| --- | --- | --- | --- | --- | --- | --- |
| Core Business |  |  |  |  |  | X |
| Strategic Fit |  |  |  |  |  | X |
| Upside Potential |  |  |  |  | X |  |
| Management | X |  |  |  |  |  |
| Risk Mitigation |  |  |  |  | X |  |

OTHER RAC COMMENTS:

Key outstanding issues to be addressed prior to final approval of the investment in the HVDC Tie include:

- Requirements of the Presidential Permit.

- Other required permits and timing.

- FERC capacity release requirements under tariff. (Will there be a ceiling on our tariff to third parties)

- Transmission constraints on the CFE grid between the HVDC Tie Line and ultimate market in Mexico.

- Ability of CFE to deny or delay ENA’s request to interconnect with any of the desired substations.

- Completion of market analysis for power demand in northern Mexico.

- Ability of ERCOT to satisfy ENA’s need for firm transmission north of Brownsville.

- Sufficiency of technology for this location and application.

- Cancellation cost associated with ABB contract at 12/31/00 and 3/31/01.

Without significant progress on the matters listed above, ENA will be assuming a substantial amount of development risk if ENA were to proceed with NTP.

More to come.

| # APPROVALS |  | Name |  | Signature |  | Date |
| --- | --- | --- | --- | --- | --- | --- |
| Regional Mgmt. |  | Janet Dietrich/Ozzie Pagan |  |  |  |  |
| Legal |  | Mark Haedicke |  |  |  |  |
| RAC Management |  | Rick Buy/Dave Gorte |  |  |  |  |
| Enron Capital Management |  | Andy Fastow/Ben Glisan |  |  |  |  |
| ENA Management |  | Dave Delainey |  |  |  |  |

Global Finance Summary (addendum to DASH)

- Transaction Summary

|  | Amount ($000) |
| --- | --- |
| Total Deal/Project Capital Commitment |  |
| Less: Financings |  |
| Less: Syndications |  |
| Net Enron Investment |  |

- Investment terms and pricing:			 Market	 Above Market	 Below Market

Describe (if necessary):

- Financing terms and pricing:			 Market	 Above Market	 Below Market

Describe (if necessary):

- Legal or practical liquidity restrictions:		 Unrestricted	 Legally Restricted	 Practically Restricted

Describe (if necessary):

- Any recourse to Enron (other than investment):			 Recourse		 No Recourse

Describe (if any):

- Business unit intent to syndicate:			 None		 Partial		 All

Describe (if necessary):

- Intended Enron hold period:

- Likely Syndication Market:			 Industry/Strategic Partner	 Direct Private Equity

Capital Markets		 JEDI 1

JEDI 2			 Enserco

LJM 1 or 2			 Condor

Other:			 Margaux

- Is this a JEDI 2 “Qualified Investment”?		 Yes			 No

Global Finance Representative:

Signature			     Name (Printed)		Date