ENRON RISK ASSESSMENT AND CONTROL

DEAL APPROVAL SHEET

| DEAL NAME: Wolf Hollow 2 Counterparty: Parsons Energy & Chemicals Group Inc. (“Parsons”) Business Unit: NEPCO Business Unit Originator: Keith Dodson Public Private Merchant Strategic Conforming Nonconforming | Date DASH Completed: March 22, 2001 RAC Analyst/Underwriter: NA/Karen Barbour Investment Type: Joint Venture Capital Funding Source(s): NA Expected Closing Date: April 2001 Expected Funding Date: NA Board Approval: Pending Received Denied N/A |
| --- | --- |

RAC Recommendation: Proceed with Transaction    Returns below Capital Price   Do not Proceed

#### APPROVAL REQUESTED

- To release Parsons from a joint and several joint venture (the “JV”) initially formed with Enron in October 2000 and to be assigned to NEPCO for the purpose of bidding, as a JV, an engineering, procurement and construction (“EPC”) contract of the Wolf Hollow Power Plant (the “Project”) for AES and/or its affiliates (“AES”) under certain terms and conditions detailed below.

# EXPOSURE SUMMARY–Not changed with respect to AES under the EPC contract since NEPCO had joint and several liabilities under the JV structure; except that under the new structure, NEPCO’s recourse vis-à-vis Parsons for any defective services will be based on a subcontract with reduced limitations on liability.

## DEAL DESCRIPTION

- Enron and Parsons, bidding as a JV, won the EPC contract and is bound under a draft EPC contract upon accepting an extended limited notice to proceed (“XLNTP”) in October 2000.  The JV specifically delineated the engineering, procurement and construction responsibilities between Parsons and NEPCO, though they share joint and several liabilities under the EPC contract.

- A JV agreement under which Parsons was nominated as the JV leader was formalized but never executed by Parsons.  However, Enron legal and its outside counsel believe that since all business conducted in relation to the Project had been conveyed in the name of the JV, each party is regarded to have entered into a JV for the purpose of this Project.

- The Project progress is behind schedule mainly caused by Parsons’ delay in performing its engineering/procurement services.

- EEOS/NEPCO management believes that Parsons’ performance delay and certain quality issues may stem from its recent shift of strategic direction and the resulting decrease of home office support on this Project.  To effectuate this change in corporate direction Parsons is refusing to execute the finalized JV Agreement or finalized EPC contract needed for financial closing of the Project, and instead, desires to be released from the JV obligations and simply perform its engineering/procurement services under a service subcontract for a fixed fee.

- After several discussions with Parsons, NEPCO decided to release Parsons from the JV agreement and to enter into a service subcontract with Parsons guaranteed by its ultimate parent company, Parsons Corporation, for the same scope of work relating to engineering, procurement, and field/start-up assistance as specified in the XLNTP and the EPC contract or as otherwise acceptable to NEPCO.  The release is contingent upon RAC approval and Parsons’ ability to comply with the following major conditions:

- Parsons to post a $4 million LOC, issued by a bank approved by NEPCO, to secure the performance of all of its obligations under the service subcontract.  The LOC amount will step down based on pre-defined completion dates.

- Parsons to convey to NEPCO all right, title and interest in and to the engineering model, materials control system, and document control system developed for the Project by Parsons.

- Parsons to arrange for NEPCO to examine all Project related vendor contracts, and to have them assigned to NEPCO provided certain conditions are satisfied.

- Parsons to (a) assign and employ such of its present engineering, procurement, project management and field support personnel as NEPCO shall designate to the Project on an exclusive basis until the Parsons’ scope of work is complete or until NEPCO approves the reassignment of such personnel, and (b) require any purchaser of the stock in, or of all or substantially all of the assets of, Parsons that hires such personnel to agree, for the benefit of Parsons and Enron, to comply with such requirements, all on terms acceptable to NEPCO.

- Parsons to provide NEPCO with sufficient office space and equipment in its existing office in Houston for the Parsons personnel and for certain NEPCO personnel as set forth in the service subcontract.

- Parsons to provide an accounting to NEPCO of all funds previously received, paid, or disbursed by Parsons to or from AES, the vendors or any other party up to the time that the service subcontract is executed.

- Any release of Parsons under the JV and its obligations under the XLNTP is subject to acceptance of all terms and the  written concurrence of AES and/or its Lenders.

- The terms of the service subcontract will be written on a back-to-back basis per the terms of the EPC contract.

- Parsons’ total limitation of liability under the service subcontract will be limited to the subcontract price ($10,825,000).

## TRANSACTION SOURCES AND USES OF FUNDS

|  | Sources |  |  | Uses |
| --- | --- | --- | --- | --- |
| Project Revenue | $299.5 |  | EPC Contract Costs | $275.8 |
| Total | $299.5 |  | Contingency | 15.5 |
|  |  |  | Expected Profit | 8.2 |
|  |  |  | Total Contract Price | $299.5 |

## TRANSACTION UPSIDES/OPTIONALITY

- Though the originally anticipated upside relating to fuel supply, ENA trading opportunities and Caribbean asset sales did not materialize, EEOS/NPECO management believes that its commercial relationship with AES had strengthened from working together to resolve issues relating to Parsons’ performance.   NEPCO still intends to pursue two power plant EPC contracts with AES.

## RISK MATRIX – Project risks remain the same as originally identified.

OTHER RAC COMMENTS:

- Given Parsons’ weak financial status, the JV structure originally contemplated essentially exposed Enron/NEPCO to 100% of the project risks with a 50/50 economic distribution.  The disproportional risk/reward allocation was accepted based on the expectation that joint and several liabilities under the JV structure would serve to mitigate, to some extent, Parsons’ performance risks.

- Parsons’ performance since the JV’s acceptance of the XLNTP has been less than satisfactory.  Additionally, changes of its strategic direction had minimized the critical home office support for the Houston office that is performing the actual work.

- RAC recommends the acceptance of Parsons’ request to be released from the JV structure, under the specific terms and conditions, because the proposed service contract will allow NEPCO to step in the lead contractor role and take control of Parsons’ direct and indirect resources to finish its scope of work, if necessary.  The milestone payments to Parsons of the subcontract price with a discretionary project completion bonus is designed to hold it responsible and provide an incentive for the impact and completion of its scope of work on the Project.

| # APPROVALS |  | Name |  | Signature |  | Date |
| --- | --- | --- | --- | --- | --- | --- |
| Regional Mgmt. |  | Brian Stanley/Keith Dodson |  |  |  |  |
| Legal |  | John Schwartzenburg |  |  |  |  |
| RAC Management |  | Rick Buy/Dave Gorte |  |  |  |  |
| Enron Capital Management |  | Andy Fastow/Ben Glisan |  |  |  |  |
| ENE Management |  | Jeff Skilling |  |  |  |  |