| # Key Dates 1 (Rolling) | # Risks / Barriers / Complications |
| --- | --- |
| - Due - Responsible Party Date Status - Executive Steering Committee Sign Off Mends 11/01 Working - Management Update Acceptance Mends 11/01 Working - Content Management tool selection Governance Body 11/01 Working - Placemat and Information Architect Design Team 10/01 Working - Look and Feel Design Team 12/01 Working - Detail Requirements Gathering Begins Team 11/01 Working - Change Management Timeline Acceptance Hejka 11/01 Working - Technical Proof-of-Concept for Portal Tool Team 11/01 Working - Resource Planning Team 11/01 Working - Governance Body and Steering Committee - Roles and Responsibilities Sign Off Team 11/01 Working | - Some resources across IT and business areas are not attending project initiatives - Some resources across IT and business areas are not communicating project milestones and timelines to business unit heads - Project success is dependent upon enterprise data cleansing initiative success - Project success is dependent upon content owner support for effort - Project success is dependent upon single sign on project support - Some dissension on scope and business case amongst executive steering committee members - Some dissension on portal vision and scope amongst some governance body members - Governance is required to bridge the current BU/FU resources needed to establish portal content, and to unite/halt renegade efforts - Portal acceptance is dependent upon positive user experience with user interface, content, and portal response time |
| Schedule (Percent Complete To Date) | Recent Accomplishments |
| - Executive Steering Committee Sign Off Not Complete - Management Update Acceptance Not Complete - Tool Selection Process 90% Complete - Evaluation of Vendor RFI Responses and Demos 90% Complete - Detailed Requirements Gathering and Design 0% - Technical Architecture Design 25% Complete - Prototyping and Development 0% - Testing 0% - Implementation 0% | - Tentatively selected Yahoo Portal Builder - Reviewed and finalized portal charter/scope - Enlisted Enron experts for technical evaluation - Distributed technology overview and white papers - Conducted portal and content management demonstrations - Kicked-off Portal Communication Marketing Workgroup - Incepted Content Management Workgroup - Collaborated with clickathome project - Conducted evaluation of technical assets with GSS (software agreements) - Hosted Cisco Systems to review their portal - Prepared Management Update document to communicate project scope, status, and business case - Prepared placemat for visual reference to portal vision - Conducted inventory of Enron intranet, Internet and extranet sites |