Project Development Agreements

| Contracts | Fixed Price, Turn Key, Date Certain |
| --- | --- |
| Payment | [ ? ] |
| Guaranteed Completion Date | Las Vegas Cogeneration II ______, 2002 Pastoria ______, 2003 Moore ______, 200_ |
| Delay Liquidated Damages | [ ? ] |
| Non Completion LD’s | 100% of contract price for each project if project not completed within 2 years after Guaranteed Completion Date |
| Asset Transfer | [Transfer LLC’s immediately upon close, title to equipment transfers on or before it is delivered on site.?] |
| Performance Tests [Minimum Performance Levels?] | Output, Heat Rate performed when 100% of facility is complete |
| Operation before Completion | [Developer allowed to operate before complete, performance tests get adjusted for degradation] |
| Acceptance Tests | Plant emissions, reliability, other capability and sound, if applicable |
| Performance LD’s | Output % below guaranteed output x contract price Subject to a cap of 10% of contract price per plant Heat Rate [$_________] per Btu/kWh Subject to a cap of 10% of contract price per plant Overall maximum cap on Performance LD’s = 15% of contract price per plant |
| Performance Bonuses | Output [$_________] per kw Heat Rate [$_________] per Btu/kWh |
| Limitation of Liability | 100% of contract price (for each plant) until air permits received + turbines transferred 25% of contract price (for each plant) aggregate limit thereafter + Environmental Indemnification |
| Environmental Indemnification | 100% for hazards caused by Developer up to six (6) months after commercial operation. No cap. |
| Purchaser Approvals | Purchaser approves plans and specifications, then substantial completion, then punch list completion, then performance tests. |
| Alternative Project [NEED TO RE-THINK AND DISCUSS THE CRITERIA] | ### IRR Keep Whole clause ### Utilize the gas turbines ### [1200] operating hours ### Electrical and gas interconnects ### Same NERC subregion or transmission control area |
| Redesign of Facility [NEED TO RE-THINK AND DISCUSS THE CRITERIA] | ### Operating cost keep whole clause ### Utilize the gas turbines ### [1200] operating hours ### Electrical and gas interconnects ### Same operating parameters ### Within [20] miles of proposed location ### No additional operating resources |
| Warranty | 12 months from the date of substantial completion for good workmanship |