Project Development Agreements

| Project Developer | Enron North America Corp. |
| --- | --- |
| Contracts | Fixed price, turn key, date certain |
| # Payment | Amount and timing to be agreed upon (expected to have some portion payable up front with subsequent payments made on certain specified dates) |
| # Guaranteed Completion Date | Moore June, 2001 Las Vegas Cogeneration II March, 2002 Pastoria June, 2003 |
| Delay Liquidated Damages | A daily liquidated damage amount to be agreed upon by the parties and paid for failure to deliver on the Guaranteed Completion Date |
| Non Completion Liquidated Damages | 100% of contract price for each project if project not completed within 2 years after Guaranteed Completion Date |
| Performance Tests | Output, Heat Rate tests will be performed when 100% of facility is complete |
| Operation before Completion | Developer allowed to operate before complete, performance tests get adjusted for degradation |
| Acceptance Tests | Plant emissions, reliability, other capability and sound, if applicable |
| Performance Liquidated Damages | Output: % below guaranteed output x contract price Subject to a cap of 10% of contract price per plant Heat Rate: [$_________] per Btu/kWh Subject to a cap of 10% of contract price per plant Overall maximum cap on Performance LD’s = 15% of contract price per plant |
| Performance Bonuses | Output [$_________] per kw Heat Rate [$_________] per Btu/kWh |
| Limitation of Liability | 100% of contract price (for each plant) until air permits received + turbines transferred 25% of contract price (for each plant) aggregate limit thereafter + Environmental Indemnification |
| Environmental Indemnification | 100% for hazards caused by Developer up to six (6) months after commercial operation. No cap. |
| Purchaser Approvals | Purchaser approves plans and specifications, then substantial completion, then punch list completion, then performance tests. |
| Alternative Project | ### Project Developer shall have the right to substitute an alternative project (“AP”) if it is reasonably necessary to do so. The AP would be subject to the terms above would also have to meet certain mutually agreed upon parameters including, without limitation, the following: The AP would have to: ### Yield an internal rate of return greater than or equal to the rate of return expected for the original project ### Utilize the same gas turbines ### Be permitted to operate for an agreed upon minimum number of operating hours - Have the electrical and gas interconnection agreements in place ### Be located in the same NERC subregion or transmission control area |

| Redesign of Facility | ### Project Developer shall have the right to institute changes in the physical equipment or operating design of a facility provided that the performance guarantees remain the same and the revised facility meets certain mutually agreed upon parameters including, without limitation, the following: The revised facility would have to: ### Utilize the same gas turbines ### Be permitted to operate for an agreed upon minimum number of operating hours ### Have the electrical and gas interconnection agreements in place ### Have the same operating parameters ### Be located within a certain agreed upon distance from the originally proposed location In addition, the fixed price payable to the Project Developer shall be reduced to the extent necessary to compensate for any increase in operating costs which arises from the redesign. |
| --- | --- |
| # Warranty | 12 months from the date of substantial completion for good workmanship |