### Proposed Contingent Equity Amounts by Risk Category

| ## Category | Maximum Amount ($MM) | Disbursement Conditions | SubCap ($MM) | Fall Away Provisions or reductions | Acceleration |
| --- | --- | --- | --- | --- | --- |
| Operating Shortfall |  |  |  |  |  |
| Fuel Oil Reimbursement | $[ ] | EPE unable to pay unreimbursed fuel oil expenses from operating cash flows. Payments under the Petrobras Letter of Credit of $R17.5-38.5million count dollar for dollar against the max. |  | - The Furnas letter for 1st 150MW (rec’d) - Letter from ANEEL providing reimbursement for 2nd 150MW - Or, letter received from Eletrabras clarifying their obligation to reimburse or payment of an invoice. - Or, switch to natural gas | - No acceleration, but available if unused until full conditions met, for obligations incurred prior to acceleration date. |
| Contingent Penalties due to Furnas | $[ ] | Penalties to Furnas for pre-existing FM that EPE is unable to pay from operating cash flows | $[ ] | - Reduced to $11.0 million if Furnas letter acknowledging Phase II Tariff accepted by Lenders - Reduced to zero if evidence of Furnas acceptance of FM claim | - No acceleration, but available if unused until full conditions met, for obligations incurred prior to acceleration date. |
| Budget |  |  |  |  |  |
| Change Orders (disputed or currently forecasted) | $[ ] | A change order approved either by Lender consent or resulting from arbitration of current list | Refer to List for individual items | - Project completion | - No acceleration but available until all disputes resolved. |
| Contingency | $[ ] | An increased cost (other than change order) that EPE, GasMat or GasBol are unable to pay from operating cash flows |  | - Project completion | - Available |