ENGINEERING, PROCUREMENT, AND CONSTRUCTION CONTRACT






by and between




as Owner

and




[ENRON ENGINEERING & CONSTRUCTION COMPANY AFFILIATE]



as Contractor



Dated as of [   ]

TABLE OF CONTENTS

ARTICLE 1 DEFINITIONS	1

ARTICLE 2 RELATIONSHIP OF OWNER, CONTRACTOR, SUBCONTRACTORS AND OTHERS	8

2.1.	Status of Contractor.	8

2.2.	Subcontractors.	8

2.3.	Subcontract Provisions.	8

2.4.	Major Subcontracts.	8

ARTICLE 3 CONTRACTOR’S RESPONSIBILITIES	9

3.1.	Scope of Work.	9

3.2.	Spare Parts.	9

3.3.	Compliance with Drawings and Review of Drawings and Documents.	10

3.4.	Contractor’s Personnel and Labor Relations.	10

3.5.	Governmental Authorization and Contractor Assistance.	11

3.6.	Control of the Work.	11

3.7.	Cleanup; Non-Interference.	11

3.8.	Safety and Emergencies.	11

3.9.	Financing Assistance.	12

3.10.	Compliance with Applicable Laws.	12

3.11.	Books and Records.	13

3.12.	Taxes and Fees.	13

3.13.	Access and Inspections, Correction of Defects.	13

3.14.	Security of  the Site;  Storage and Related Matters.	14

3.15.	Cooperation and Non-interference.	14

3.16.	No Liens.	14

3.17.	Hazardous Substances, Archaeological Discoveries and Ground Risk.	15

3.18.	Traffic and Special Loads.	15

3.19.	Waterborne Traffic.	16

3.20.	PPA Requirements.	16

ARTICLE 4 OWNER’S RESPONSIBILITIES	17

4.1.	Owner Assistance to Contractor.	17

4.2.	Owner’s Services.	17

4.3.	Payment.	17

4.4.	Access to Site and Rights of Way.	17

4.5.	Governmental Authorizations.	17

4.6.	Operating Personnel.	17

4.7.	Coordination with Utility.	18

4.8.	Owner’s Representative.	18

4.9.	Divergences from Applicable Law.	18

4.10.	Owner Delay.	18

4.11.	Compliance with Laws.	18

4.12.	Taxes and Duties.	18

4.13.	Subcontractors.	18

ARTICLE 5 COMMENCEMENT OF WORK	19

5.1.	Commencement of Work.	19

5.2.	Project Schedule.	20

5.3.	Progress Reports and Consultation.	20

ARTICLE 6 CHANGES [TO BE REPLACED]	21

6.1.	Changes and Change Orders.	21

6.2.	Owner Change Direction.	21

6.3.	Change Order Requests.	21

6.4.	NOT USED.	22

6.5.	Information Supporting Change Order Request.	22

6.6.	Performance of Owner Change Directions.	22

6.7.	Other Provisions Unaffected.	23

6.8.	Change in Law , Owner Delay or Force Majeure.	23

ARTICLE 7 CONTRACT PRICE; PAYMENTS TO CONTRACTOR	24

7.1.	Contract Price.	24

7.2.	Payment of Contract Price.	24

7.3.	Payments Not Waiver or Acceptance of Work.	25

7.4.	Payment of Subcontractors.	25

7.5.	Waiver of Liens.	25

7.6.	Interest and Disputed Invoices.	25

ARTICLE 8 TITLE AND RISK OF LOSS	26

8.1.	Title.	26

8.2.	Risk of Loss.	26

8.3.	Use by Owner.	27

ARTICLE 9 INSURANCE	28

9.1.	Contractor’s Insurance.	28

9.2.	Owner’s Insurance.	28

9.3.	Certificates and Cancellations.	28

9.4.	Failure to Pay.	29

9.5.	Miscellaneous.	29

ARTICLE 10 DOCUMENTATION	30

10.1.	Delivery of Job Books.	30

10.2.	Machine Readable Information.	30

ARTICLE 11 COMPLETION [to be revised]	31

11.1.	Notices.	31

11.2.	Substantial Completion Certificates.	31

11.3.	Final Completion.	31

11.4.	Owner Acceptance of Completion Certificates.	32

11.5.	Punchlist.	32

11.6.	Long-Term Obligations.	33

ARTICLE 12 WARRANTY [TO BE REVISED]	34

12.1.	General Warranty.	34

12.2.	Warranty Period.	34

12.3.	Remedy.	34

12.4.	Subcontractor Warranties.	34

12.5.	Warranty Exclusions.	35

12.6.	No Implied Warranties.	35

12.7.	Exclusive Remedies.	35

ARTICLE 13 SCHEDULE GUARANTEES	36

13.1.	Guarantee of Timely Completion.	36

13.2.	Completion.	36

13.3.	Delay Liquidated Damages and Early Completion Bonus.	36

13.4.	Performance Guarantees and Liquidated Damages.	36

13.5.	Performance Tests.	36

13.6.	Contractor’s Right to Improve Performance.	37

ARTICLE 14 LIMITATION OF LIABILITY [to be further revised]	37

14.1.	Maximum Liability.	37

14.2.	Consequential Damages.	38

14.3.	Releases Valid in All Events.	38

14.4.	Liquidated Damages Not Penalty.	38

ARTICLE 15 REPRESENTATIONS OF CONTRACTOR AND OWNER	39

15.1.	Contractor Representations.	39

15.2.	Owner Representations.	39

ARTICLE 16 DEFAULT, TERMINATION AND SUSPENSION	41

16.1.	Default by Contractor.	41

16.2.	Optional Cancellation by Owner.	42

16.3.	Termination by Contractor.	43

16.4.	Suspension of Work.	44

ARTICLE 17 FORCE MAJEURE	46

17.1.	Force Majeure	46

17.2.	Excused Performance.	47

17.3.	Performance Continuation.	47

17.4.	Financial Consequences of Force Majeure.	47

17.5.	Owner Self-Help.	47

17.6.	Resumption of Performance.	48

17.7.	Burden of Proof.	48

17.8.	Termination for Force Majeure.	48

17.9.	Payment on Termination.	48

ARTICLE 18 INDEMNITIES	50

18.1.	Contractor Indemnity.	50

18.2.	Owner Indemnity.	50

18.3.	Patent Indemnity.	50

18.4.	Notice.	50

18.5.	Defense of Claims.	51

ARTICLE 19 DISPUTE RESOLUTION [to be revised]	52

19.1.	Arbitration Resolution.	52

19.2.	Fast-Track Arbitration.	52

19.3.	Applicable Law and Arbitration Act.	52

19.4.	Continuation of Services.	53

ARTICLE 20 CONFIDENTIAL INFORMATION	54

20.1.	Confidential Information.	54

20.2.	Notice Preceding Compelled Disclosure.	54

20.3.	Definition of “Confidential Information”.	54

20.4.	Remedies.	54

ARTICLE 21 SECURITY	55

21.1.	Retention Bond.	55

ARTICLE 22 MISCELLANEOUS PROVISIONS	56

22.1.	Governing Law.	56

22.2.	Notice.	56

22.3.	Assignment.	56

22.4.	Corrupt Practices.	56

22.5.	Miscellaneous.	56

ENGINEERING, PROCUREMENT & CONSTRUCTION CONTRACT

THIS ENGINEERING, PROCUREMENT & CONSTRUCTION CONTRACT (this “Agreement”), dated as of ____ (the “Effective Date”), between ____, a company organized and existing under the laws of [Host Country] (“Owner”), and [Enron Engineering & Construction Company Affiliate], a corporation organized under the laws of __________________ (“Contractor”).

PRELIMINARY STATEMENTS

A.	Owner desires to develop a power generation facility to be located in ____.

B.	Contractor has significant expertise in the design, engineering, procurement, construction, start-up, commissioning and testing of power generation facilities.

C.	Contractor, itself or through subcontractors, desires to provide design, engineering, procurement and construction services to build, start-up, test and commission the Facility (defined below) at the Site (defined below) all on a stipulated, fixed-price basis.

D.	Contractor is willing to guarantee the timely completion of the Work (defined below) and performance of the Facility.

NOW THEREFORE, Owner and Contractor agree as follows:

# DEFINITIONS

Capitalized terms used without other definition shall have the meanings specified in this Article 1, unless the context requires otherwise.

“Adjusted Heat Rate” shall mean the thermal efficiency of the Facility expressed as a ratio of fuel consumed to a unit of electric power output, as measured during a Heat Rate Test and Adjusted from test conditions to Base Conditions by the methods described in Exhibit E-3.

“Adjusted Net Electrical Output” shall mean the electric output of the Facility net of all auxiliary loads as measured during a Net Electrical Output Test and Adjusted from test conditions to Base Conditions by the methods described in Exhibit E-3.

“Affiliate” shall mean, with respect to any Person, any other Person that (a) owns or controls, directly or indirectly, the first Person, (b) is owned or controlled by the first Person, or (c) is under common ownership or control with the first Person, where “own” means ownership of fifty percent (50%) or more of the equity interests or rights to distributions on account of equity of the Person and “control” means the power to direct the management or policies of the Person, whether through the ownership of voting securities, by contract, or otherwise.

“Aggregate Limit” shall have the meaning set forth in Section 14.1.

“Agreement” shall mean this engineering, procurement and construction contract as amended, modified or supplemented from time to time.

“Alternate” shall have the meaning set forth in Section 19.2.

“Arbitrator” shall have the meaning set forth in Section 19.2.

“Availability Guarantee” shall mean the percentage set forth in Exhibit E-1.

“Availability Test” shall mean a test of the availability of the Facility conducted in accordance with the procedures developed pursuant to the guidelines set forth in Exhibit E-3 to demonstrate the availability of the Facility.

“Base Conditions” shall have the meaning set forth in Exhibit E-2.

“Business Day” shall mean any day other than a Saturday, a Sunday, or a day on which banks in [Host Country] or Houston, Texas are authorized or required by law to be closed.

“Change” shall mean a change in the Scope of Work, Specifications, Performance Guarantees, Minimum Performance Guarantees, Contract Price, Guaranteed Completion Date, or Project Schedule, as applicable.

“Change In Law” shall have the meaning specified for such term in Exhibit G-2.

“Change Order” shall mean a written order pursuant to Article 6, signed by Owner and Contractor authorizing a Change.

“Confidential Information” shall have the meaning set forth in Section 20.3.

“Contract Price” shall have the meaning given to such term in Exhibit C-1.

“Contractor” shall have the meaning specified for such term in the Preamble to this Agreement.

“Contractor Indemnitees” means Contractor, Subcontractors and each of their respective Affiliates, successors, assigns, officers, directors and employees.

“Contractor Indemnitor” shall have the meaning set forth in Section 18.1.

“Contractor Insurance” shall have the meaning set forth in Exhibit H-1.

“Contractor Lien” shall have the meaning set forth in Section 3.16.1.

“Contractor’s Equipment” shall mean all appliances or things of whatever nature required for the performance of the Work at the Site, but not including Equipment or other things intended to form or forming part of the Facility.

“Day” or “day” shall mean a calendar day and shall include Saturdays, Sundays and holidays.

“Default Rate” shall mean he lower of (i) the maximum interest rate allowed by law or, (ii) the floating interest rate of (a) three (3) months London Interbank Offered Rate (LIBOR) as published by the Financial Times for USD to be fixed at a rate valid and established on the first day of each month plus (b) two percent (2%) calculated on the basis of a 360-day year and the actual number of days elapsed.

“Delay Limit” shall have the meaning set forth in Section 14.1.

“Delay Liquidated Damages” shall mean any liquidated damages payable pursuant to Section 13.3.1.

“Early Completion Bonus” shall mean any bonus payable to Contractor pursuant to Section 13.3.2.

“Effective Date” shall have the meaning specified for such term in the Preamble to this Agreement.

“Electric Output Guarantee” shall have the value set forth in Exhibit E-1.

“Electrical Output Test” shall mean a test, conducted in accordance with the procedures developed pursuant to the guidelines set forth in Exhibit E-3, to demonstrate the electric output of the Facility.

“Emissions Guarantee” shall have the meaning set forth in Exhibit E-1.

“Emissions Test” shall mean a test, conducted in accordance with the procedures developed pursuant to the guidelines set forth in Exhibit E-3, to determine the emissions into the air of the Facility.

“End Date” shall be the date set forth in Exhibit A.

“Equipment” shall mean all machinery, equipment, computer hardware and software, apparatus, materials, articles, drawings, designs, plans and things of all kinds to be provided by Contractor under this Agreement and incorporated into the Facility other than Contractor’s Equipment.

“Facility” shall mean the plant and certain related facilities described in Exhibit B.

“Fast-Track Arbitrator” shall have the meaning set forth in Section 19.2.

“Final Completion” shall have the meaning set forth in Section 11.3.

“Final Completion Certificate” shall have the meaning set forth in Section 11.3.

“Financial Close” shall mean the execution of all loan agreements, security agreements, promissory notes, equity commitments, and guarantees and other financing agreements by the Lenders and the Owner and its affiliates in connection with the provision of long term project financing of the Facility and the Work in an amount not less than the Contract Price plus a reasonable contingency, [the satisfaction [or waiver]of all conditions precedent to the general availability of funds to Owner for the construction of the Facility under such financing agreements,] and the occurrence of the initial disbursement of funds thereunder by the lenders.  (delete bracketed clause as unnecessary?)

“Force Majeure” shall have the meaning set forth in Section 17.1.

“Good Industry Practice” or “GIP” shall mean the exercise of that degree of skill, diligence and prudence which would reasonably and ordinarily be expected from a skilled and experienced contractor or equipment manufacturer applying the standards generally adopted by contractors and equipment manufacturers in North America in the construction of power generation facilities or the manufacture of equipment therefor, unless the result of such exercise would violate any applicable [Host Country] Law.

“Governmental Authority” shall mean all authorities of any nation or any part of a nation, whether of an executive, legislative, judicial, administrative, military or police nature and any other Person under the direct or indirect control of any of the foregoing, including any ministry, court, tribunal, department, municipality, city, instrumentality, agency or commission and officials of such authorities.

“Governmental Authorizations” shall mean all permits, consents, decisions, licenses, approvals, certificates, confirmations or exemptions from, and all applications and notices filed with any Governmental Authority that are necessary for the design, engineering, procurement, construction, start-up, commissioning, testing, financing, ownership and operation of the Facility.

“Guaranteed Completion Date” shall have the meaning set forth in Exhibit A.

“Hazardous Substances” shall mean any substance or material regulated or governed by any Governmental Authority, or any substance, emission or material now or hereafter deemed by any court or Governmental Authority having jurisdiction to be a “regulated substance”, “hazardous substance”, “toxic substance”, “pesticide”, “hazardous waste”, or any similar classification, including by reason of deleterious properties, ignitability, corrosivity, reactivity, carcinogenicity or reproductive toxicity.

“Heat Rate Guarantee” shall have the meaning set forth in Exhibit E-1.

“Heat Rate Limit” shall have the meaning set forth in Section 14.1.

“Heat Rate Liquidated Damages” shall mean any liquidated damages payable due to Contractor’s failure to cause the Facility to meet the Heat Rate Guarantee pursuant to Exhibit C-4.

“Heat Rate Test” shall mean a test, conducted in accordance with the procedures developed pursuant to the guidelines set forth in Exhibit E-3, to demonstrate the heat rate of the Facility.

“including” shall mean including without limitation.

“Indemnitee” shall have the meaning set forth in Section 18.5.

“Indemnitor” shall have the meaning set forth in Section 18.5.

“Invoice” shall mean Contractor’s monthly request for payment in accordance with Section 7.22, which invoice shall be substantially in the form of Exhibit C-5.

“Job Books” shall have the meaning set forth in Section 10.1.

“kW” shall mean kilowatts.

“kWh” or “Meh” shall mean kilowatt-hours.

“Law”  shall mean any constitution, charter, act, statute, law, ordinance, code, rule, regulation, order, treaty, decree, announcement or published practice or any interpretation thereof, or other legislative or administrative action of any Governmental Authority, or specified standards or objective criteria contained in any applicable Governmental Authorization, or a final decree, judgment or order of a court, or any engineering, construction, safety or electrical generation code applicable to the Work, Facility or any part thereof.

“Lender” shall mean lenders, institutions, noteholders or bondholders providing or guaranteeing, financing or refinancing to Owner for the construction of the Facility, and any agent or trustee therefor.

“Liquidated Limit” shall have the meaning set forth in Section 14.1.

“Major Subcontract” shall mean any Subcontract that is designated as such on Exhibit L.

“Major Subcontractor” shall mean any Subcontractor with whom Contractor enters into a Major Subcontract.

“Mechanical Completion” shall mean, with respect to each unit, system, or component of the Facility, the completion of the Work relating thereto, to include setting of the Equipment on foundations; connecting Equipment to other applicable equipment with piping, wiring, controls, and safety systems; ensuring that such Equipment and such related operating systems are individually cleaned, leak-checked, lubricated, and point-to-point checked to verify that such Equipment and such related operating systems have been correctly installed so as to respond to simulated test signals equivalent to actual signals received during operation; and ensuring that such Equipment and related operating systems are ready for initial operation, adjustment and testing and may be so operated, adjusted and tested without damage thereto or to any other property and without injury to any Person.  Mechanical Completion shall include but not be limited to the following pre-commissioning activities with respect to the applicable unit, system or component: stroking of all control valves, phase rotation of electrical equipment, and continuity of other electrical circuits (including loop checks) and response of controls and control equipment.

“Mechanical Limit” shall have the meaning set forth in Section 14.1.

“Minimum Performance Guarantees” shall mean the Reliability Guarantee, Minimum Performance Output Guarantee, Minimum Performance Heat Rate Guarantee, Sound Level Guarantee and the Emissions Guarantee.

“Minimum Performance Heat Rate Guarantee”  shall have the meaning set forth in Exhibit E-1.

“Minimum Performance Output Guarantee” shall have the meaning set forth in Exhibit E-1.

“Month” or “month” shall mean a calendar month (in accordance with the Gregorian calendar).

“MW”  shall mean megawatts.

“Near Source Sound Level Guarantee” shall have the meaning set forth in Exhibit E-1.

“Notice to Proceed” shall have the meaning set forth in Section 5.1.2.

“Notice to Proceed Effective Date” shall have the meaning set forth in Section 5.1.2.

“Notice to Proceed Issue Date” shall have the meaning set forth in Section 5.1.2.

“Operator” shall mean either the Person under contract to Owner for the operation and maintenance of the Facility, if any, or Owner.

“Out of Scope Construction” shall have the meaning set forth in Section 3.15.

“Output Limit” shall have the meaning set forth in Section 14.1.

“Output Liquidated Damages” shall mean any liquidated damages payable due to Contractor’s failure to cause the Facility to meet the Electrical Output Guarantee pursuant to Exhibit C-4.

“Owner” shall have the meaning set forth in the Preamble to this Agreement.

“Owner Delay” means any delay by Owner in performing its obligations set out in Article 4 and elsewhere in this Agreement, regardless of the reason for such delay.  [Verify this definition in later versions.]

“Owner Indemnitees” means Owner, Lender and each of their respective Affiliates, successors, assigns, officers, directors, employees and agents.

“Owner Indemnitor” shall have the meaning set forth in Section 18.2.

“Owner’s Representative” shall have the meaning set forth in Section 4.8.

“ Payment Schedule” shall mean the payment schedule as set forth in Exhibit C-2.

“Performance Guarantees” shall mean the Electrical Output Guarantee and Heat Rate Guarantee.

“Performance Liquidated Damages” shall mean the Heat Rate Liquidated Damages and Output Liquidated Damages collectively or independently depending upon context of use.

“Performance Test” shall mean any of the Reliability Test, Heat Rate Test, Net Electrical Output Test, Sound Level Test, or Emissions Test.

“Person” shall mean any natural person, corporation, company, partnership (general or limited), limited liability company, business trust, or other entity or association.

“Port of Import” shall mean ____.

“PPA” shall mean the [power offtake agreement between Owner and ____________________], dated the ____ day of _____________, _______.

“Preliminary Notice to Proceed” shall have the meaning set forth in Section 5.1.1.

“Project Agreements” shall mean those agreements set forth on Part I of Exhibit G-1.

“Project Schedule” shall have the meaning set forth in Section 5.2.1.

“Project Schedule Summary” shall mean the summary schedule set forth in Exhibit A.

“Punchlist” shall have the meaning set forth in Section 11.5.

“Punchlist Item” means any uncompleted part of the Facility that (considered individually or in the aggregate of all Punchlist Items) does not and will not adversely affect the performance of the Facility or the ability of Owner to operate the Facility in the ordinary course of business in accordance with GIP.

“Punchlist Withholding” shall have the meaning set forth in Section 11.5.2.

“Reliability Guarantee” shall have the meaning set forth in Exhibit E-1.

“Reliability Test” shall mean a test of the reliability of the Facility, conducted in accordance with the procedures developed pursuant to the guidelines set forth in Exhibit E-3, to demonstrate the reliability of the Facility.

“Replacement Contractor” shall have the meaning set forth in Section 16.1.3.

“Representatives” shall have the meaning set forth in Section 20.1.

“Retainage” shall have the meaning set forth in Section 7.2.4.

“Retention Bond” shall have the meaning set forth in Section 21.1.

“Scope of Work” shall mean the description of Work to be performed by Contractor as set forth in Section 3.1, Section 3.2 and Exhibit B-2.

“Security” shall mean the Retention Bond together with any other security obtained by Owner for any of the obligations of Contractor under this Agreement.

“Site” shall mean the real property described in Exhibit I.

“Sound Level Guarantee” shall mean the sound level limits set forth in Exhibit E-1.

“Sound Level Test” shall mean a test, conducted in accordance with the procedures developed pursuant to the guidelines set forth in Exhibit E-3, to determine the sound levels of the Facility.

“Specifications” shall mean the specifications set forth in Exhibit B.

“Subcontract” shall mean an agreement between Contractor and a Subcontractor or a Subcontractor and any other Subcontractor for the performance of any portion of the Work.

“Subcontractor” shall mean any subcontractor, vendor or supplier of equipment, materials or services to Contractor or any subcontractor or any Person engaged or employed by any such subcontractor, vendor or supplier in connection with the performance of any portion of the Work.

“Substantial Completion” shall have the meaning set forth in Section 11.2.

“Substantial Completion Certificate” shall have the meaning set forth in Section 11.2.

“Technical Limits” shall mean the limits and restrictions relating to the operation and maintenance of the Facility, as set forth in paragraph 4 of the Specifications.

“Utility” shall mean ____.

“USD, U.S. Dollars or $” shall mean lawful currency of the United States of America.

“Warranty Period” shall have the meaning set forth in Section 12.2.

“Work” shall mean all Equipment and other structures, instruments, facilities and materials included or to be included in the Facility and all obligations, duties and responsibilities assigned to or undertaken by Contractor pursuant to this Agreement.

# RELATIONSHIP OF OWNER, CONTRACTOR, SUBCONTRACTORS AND OTHERS

## Status of Contractor.

In performing the Work hereunder, Contractor shall at all times be an independent contractor and shall have sole responsibility for and control over the details and means and methods of performing the Work, subject to the provisions of this Agreement.

## Subcontractors.

Owner acknowledges and agrees that Contractor may have portions of the Work accomplished by Subcontractors.  Contractor shall cause all Subcontractors to perform their work in conformity with all of the provisions of this Agreement.  No contractual relationship shall exist between Owner and any Subcontractor with respect to the Work to be performed pursuant to this Agreement, and no Subcontractor is intended to be or shall be deemed a third-party beneficiary of this Agreement.  No subcontractor, agent, or employee of Contractor shall be deemed to be the agent, subcontractor, representative or employee of Owner. Contractor agrees that it shall be as fully responsible to Owner for the acts and omissions of Subcontractors as it is for its own acts or omissions.  Unless Owner expressly agrees in writing, Owner shall not be obligated to pay or see to the payment of any Subcontractor.  Entry into any Subcontract shall not relieve Contractor of any of its obligations to perform the Work in accordance with this Agreement.

## Subcontract Provisions.

Contractor shall ensure that all of its Subcontracts between Contractor and any its Subcontractors are in writing.  All Major Subcontracts shall provide that all rights, including all warranties, and obligations of Subcontractor under each such Subcontract are assignable to Owner or to Lender, its successors and assigns upon Owner’s written request, without further consent of Subcontractor (other than Owner reasonably demonstrating the financial capability of the assignee), following any termination of this Agreement, provided that Owner assumes all of Contractor’s obligations under such Major Subcontract.

## Major Subcontracts.

Exhibit L contains a list of potential Major Subcontractors which Contractor and Owner have agreed are approved for certain Major Subcontracts.  In the event that Contractor is considering the selection of a Person not listed in Exhibit L for a Major Subcontract, then Contractor shall notify Owner of the proposed Major Subcontractor at the earliest practical point in the selection process and furnish to Owner all information reasonably requested by Owner (which Owner shall identify to Contractor within ten (10) Business Days of Contractor’s initial request) with respect to Contractor’s selection criteria.  Contractor shall request, in writing, Owner’s consent, which shall not be unreasonably withheld, for Contractor to enter into a Major Subcontract with a Person not named on Exhibit L.  Owner must respond to Contractor’s request for its consent within ten (10)  Business Days after receipt of the request and the information described above in this Section 2.4.  If Owner fails to timely respond to Contractor’s request within such ten (10) Business Days period then, Contractor shall have the right to execute such Major Subcontract with the proposed Major Subcontractor.  If Owner has refused to consent to the proposed Subcontractor, then Contractor shall not enter into a Major Subcontract with such proposed Major Subcontractor.

# CONTRACTOR’S RESPONSIBILITIES

## Scope of Work.

### General Description of Work.  Contractor shall design, engineer, procure and construct a complete Facility which complies with the requirements set forth in this Agreement including meeting the requirements of Mechanical Completion, Substantial Completion and Final Completion.  Where this Agreement describes the Scope of Work in general terms, but not in complete detail, it is understood and agreed that the Scope of Work includes any incidental work which can be reasonably inferred as required and necessary to procure and supply the Equipment and complete the Facility in accordance with this Agreement.  In the event of any conflict or inconsistency between the requirements of this Agreement and GIP, the requirements of this Agreement shall prevail.

### Specific Responsibilities.  Without duplication of or limiting the generality of Section 3.1.1 or any other provision of this Agreement, and except as set forth in Article 4, Contractor shall in accordance with the provisions of this Agreement:

#### engineer and design the entire Facility in accordance the Specifications and the Scope of Work which comply with GIP;

#### perform any required improvements to the Site necessary for the completion of the Facility in accordance with this Agreement;

#### procure and supply all Equipment, expedite and transport the Equipment to the Site and ensure the proper handling and storage of same;

#### provide management, Contractor’s Equipment, construction utilities and consumables, including lubricants, chemicals, construction consumables and construction equipment fuel necessary for the construction of the Facility in accordance with this Agreement except for those items to be furnished by Owner as set forth in Section 4.2;

#### manage, supervise and control the commissioning and performance testing of the Facility using operating personnel provided by Owner;

#### conduct the training described in Exhibit O;

#### Subject to the provisions of Exhibit Q and Exhibit M, if necessary, clear all Equipment through customs and take any other actions necessary to import any Equipment;

#### prepare detailed Performance Test and Availability Test procedures in accordance with Exhibit E-3 ; and

#### prepare start-up and commissioning procedures.

## Spare Parts.

### Consumable Spare Parts.  Contractor shall provide, within the Contract Price, all spare parts and special tools necessary for the construction, start-up, commissioning and testing of the Facility prior to Substantial Completion.

### Special Tools and Operating Spare Parts.  Contractor shall provide such services in connection with the procurement of special tools for operation and operating spare parts as are specified in Exhibit N.  Except as specifically provided for in Exhibit N, no special tools for operations or operating spare parts are included in the Contract Price

### Failure During Start-Up.  Should any Equipment fail prior to Final Completion, spare parts may be withdrawn from Owner’s stock of operations and maintenance stores and the Equipment that failed returned to operating condition.  Contractor shall at its cost promptly replace all such withdrawn spare parts with new spare parts of the same type made by the same manufacturer.

## Compliance with Drawings and Review of Drawings and Documents.

### Submission by Contractor.  Contractor shall submit to Owner, throughout the duration of this Agreement, current complete copies of the Facility drawing and document lists for those documents listed in Exhibit R-1, and Contractor shall provide or cause to be provided to Owner, within thirty (30) days following the Notice to Proceed Effective Date, a submittal schedule setting out the anticipated dates of issue of all such drawings.  Contractor shall transmit to Owner in a timely fashion the drawings and documents listed in Exhibit R-1.

### Review by Owner.  Owner shall notify Contractor of any comments or queries within fifteen (15) days of receipt of any drawing or document listed in Exhibit R-1.  If Owner fails to respond within the fifteen (15) day period, then such drawing or document shall be deemed to have been reviewed and approved by Owner without comment thereto.  Contractor shall, within ten (10) days following receipt of any comments or queries on any such drawing or document, amend such drawing or document or otherwise take account of or respond to Owner’s comments or queries and shall resubmit such drawing or document for Owner review.  Owner shall notify Contractor of any comments it may have with respect to such a resubmitted drawing or document within seven (7) days of its receipt.  Subject to Article 6, Contractor shall reasonably endeavor to implement and accommodate, within any such drawing or document submitted for Owner’s review and within the method, manner or sequence of carrying out the Work, Owner’s comments relating to such drawing or document (including comments on matters of safety and ease of operation and maintenance of the Facility) unless such comments are inconsistent with the requirements of this Agreement.  Owner shall not be entitled to comment on any drawing or document not listed in Exhibit R-1 that is submitted to Owner for informational purposes only except on the ground that the drawing or document fails to comply with the requirements of this Agreement.  Otherwise, Owner shall be entitled to request a change to any drawing or document in accordance with Article 6.

### Owner’s Right to Examine.  Owner and its authorized representatives shall also have the right, at any time on reasonable notice, at the premises of Contractor or Subcontractor, to examine drawings or documents which have been or are being prepared by Contractor or any Subcontractor for the purposes of this Agreement, except drawings or documents containing proprietary manufacturing know-how which is confidential to its owner.

### Compliance With Drawings.  Contractor shall perform the Work and ensure that all Equipment is procured and supplied substantially in accordance with the final drawings and documents listed in Exhibit R-1 submitted to Owner.

## Contractor’s Personnel and Labor Relations.

### Site Staff.  Contractor shall ensure that there are at all times at the Site sufficient suitably qualified and experienced personnel to supervise and perform the Work at the Site and to direct the operating and maintenance personnel in the start-up, commissioning and testing of the Facility.

### Key Personnel.  Contractor shall appoint suitably qualified and experienced personnel acceptable to Owner to fill the posts listed in Exhibit S.  Contractor shall maintain such posts in connection with the Work as long as reasonably necessary to fulfil Contractor’s obligations under this Agreement and shall not remove or replace personnel holding such posts prior to substantial completion without the prior written approval of Owner, which approval shall not be unreasonably withheld or delayed.  Contractor shall submit the resumes of the persons nominated to fill the positions listed on Exhibit S to Owner for review, comment or rejection prior to their appointment.  The person holding the post designated on Exhibit S as “Project Manager” shall have full authority to act on behalf of Contractor for all purposes in connection with this Agreement, including the execution of Change Orders, and Contractor shall notify Owner of the normal workplace(s) of the person who holds such post.  Another post designated on Exhibit S shall be held by a person employed at the Site from the commencement of Work on the Site until Substantial Completion to supervise all work done on the Site and to receive all instructions related to Site activities given by or on behalf of Owner; whenever such Person is absent from the Site, Contractor shall nominate a suitable person to act as his or her deputy.

### Objection to Representative.  Owner shall be entitled by notice to Contractor to object to any representative or person employed by Contractor or any Subcontractor in the execution of the Work who shall, in the reasonable opinion of Owner, be incompetent or negligent, or engaged in misconduct.  If the behavior of such person is not corrected to Owners’ reasonable satisfaction within 30 days of such notice, then on second notice from Owner, Contractor shall promptly remove or ensure the removal of such person from the Work and appoint a suitable replacement.

### Labor Relations.  Contractor shall use all reasonable efforts in the employment of labor and Subcontractors (whether directly or indirectly employed) so as not to cause any conflict or interference with relations between the various trades, or any delay in the performance of Contractor’s obligations.  Contractor shall be responsible for all labor relation’s matters of its employees and those of its Subcontractor relating to the Work and shall at all times use and cause its Subcontractors to use reasonable efforts to maintain harmony among their workforces.  Contractor at all times shall use and cause its Subcontractors to use reasonable efforts and judgment as an experienced contractor to adopt and implement policies and practices designed to avoid work stoppages, slowdowns, disputes and strikes.  [Contractor reserves the right to hire nonprevailing wage labor to the extent permitted under applicable laws.]

## Governmental Authorization and Contractor Assistance.

Contractor shall obtain in a timely manner the Governmental Authorizations listed in Exhibit K for which it is designated as responsible for submitting and obtaining, any other local construction Governmental Authorizations related to construction work on the Site which applicable Law requires to be issued in Contractor’s name, and any completion certificates required by applicable Law certifying that the Facility has been built in accordance with all such Governmental Authorizations.  Contractor shall give all notices and pay all fees required to be given or paid to any Governmental Authority in relation to any such Governmental Authorizations which are the responsibility of Contractor.  Contractor shall use reasonable efforts (including, but not limited to, providing documents and information requested by Owner), to assist Owner in its efforts to obtain the Governmental Authorizations which Owner is required to obtain pursuant to Section 4.5 and as indicated in Exhibit K.  Contractor will use reasonable efforts to support Owner in Owner’s coordination and communications with Utility in accordance with Section 4.7.

## Control of the Work.

Except as otherwise provided pursuant to Section 3.8.3 and 3.18, Contractor shall be solely responsible for all construction means, methods, techniques, sequences, procedures in connection with the performance of the Work.

## Cleanup; Non-Interference.

Contractor shall at all times keep the Site reasonably free from waste materials or rubbish caused by its activities.  During the period from Substantial Completion until Final Completion, Contractor shall ensure that the performance of the Work does not unreasonably interfere with the commercial operation of the Facility.  As soon as practicable after Substantial Completion, Contractor shall remove Contractor’s Equipment and all waste material and rubbish from the Site and, to the extent generated by the Work, from the surrounding areas.

## Safety and Emergencies.

### Precautions.  Contractor shall be solely responsible for the safety of its operations and the operations of each Subcontractor.  Contractor shall initiate and maintain reasonable safety precautions and programs designed to promote health and safety and prevent injury to Persons or damage to property on, about or adjacent to the Site.  Contractor shall erect and maintain reasonable safeguards for the protection of workers and the public.  Contractor shall exercise reasonable efforts to eliminate or abate all reasonably foreseeable safety hazards created by or otherwise resulting from performance of the Work.

### Emergencies.  In the event of any emergency endangering life or property, Contractor shall take such action as may be necessary to deal with such emergency in accordance with GIP to prevent, avoid or mitigate injury, damage or loss and shall promptly notify Owner of any such emergency and the actions taken by Contractor.

### Owner Actions.  Whenever Contractor has not complied with its obligations set forth in Section 3.8.1 or 3.8.2, thereby creating an emergency requiring immediate action, then Owner may take reasonable precautions in accordance with GIP to deal with such emergency, but the taking of such action by Owner, or Owner’s failure to do so, shall not limit Contractor’s liability or its obligations under this Agreement.  Contractor shall reimburse Owner for the reasonable costs incurred by Owner in taking such precautions.

## Financing Assistance.

Contractor agrees that it will make available to Owner and Lender (and any independent engineer or other consultants retained by Lender) information relating to the status of the Work, including but not limited to information relating to the design, procurement, engineering, construction, start-up, commissioning and testing of the Facility, and such other matters as Owner may reasonably request.  Contractor shall furnish such usual and customary consents to assignment, certifications and representations and opinions of counsel, addressed to Owner and Lender, as may be reasonably requested by Owner or Lender.

## Compliance with Applicable Laws.

### Compliance and Indemnity.  In the performance of this Agreement and the carrying out of all Work hereunder, Contractor shall, and shall cause its Subcontractors to, ascertain and comply with all Laws applicable to the Work, and Contractor agrees to indemnify, defend and hold harmless Owner and Owner Indemnitees from and against any and all fines, penalties, related costs and expenses, including reasonable legal expenses and costs, attributable to any failure of Contractor or any Subcontractor to comply with such applicable Laws in connection with the performance of the Work.

### Divergences from Applicable Law.  If Contractor becomes aware of any divergence between any Law applicable to the Work and the Specifications, Scope of Work or any other provision of this Agreement, it shall promptly give Owner written notice specifying the divergence and any Change Order Request deemed appropriate for remedying such divergence.  However, Contractor shall not be entitled to any increase in the Contract Price or Project Schedule except as a result of a Change in Law.

### Changes in Law.  If and to the extent that any Change in Law gives rise to the requirement to make a modification to the Facility or to a change in the Work or the schedule, manner or sequence of execution of the Scope of Work as described in the Specifications, such Change in Law shall be deemed to be a Change directed by Owner to which the provisions of Article 6 shall apply.  Each party shall notify the other as soon as it becomes aware that any Change in Law may require a modification to the Facility and shall provide the other party with such further information and assistance as such party may reasonably request in order to enable the parties to comply with their obligations under this Agreement and for Owner to comply with its obligations under the Project Agreements in respect of such modification.

## Books and Records.

Contractor shall keep and shall cause its Subcontractors to keep such full and detailed books, records and accounts as may be necessary for compliance with its obligations under this Agreement until the expiration of the Warranty Period.

## Taxes and Fees.

### Contractor shall be responsible within the Contract Price for those taxes, fees, levies, or other governmental charges identified in Part I of Exhibit C-7.

### Upon the failure of Contractor to promptly pay when due any tax or fee for which Contractor is liable pursuant to this Section 3.12 and if Contractor’s failure to pay such tax will result in an economic loss for Owner, then unless Contractor has filed a written protest regarding the application of such Tax with the relevant Government Authority, Owner may pay such tax or fee and shall be entitled to immediately recover from Contractor the amount paid together with all expenses incurred in connection therewith or set off all such amounts against any sums owed by Owner to Contractor.

### Within a reasonable period of time after a request therefor, Contractor shall provide Owner with any information regarding quantities, descriptions and costs of Equipment installed at the Facility which Owner shall deem necessary in connection with Taxes for which Owner is responsible for under this Agreement in sufficient detail and in such a format as Owner may reasonably request.

## Access and Inspections, Correction of Defects.

### Right to Inspect.  Subject to compliance with Contractor’s safety policies and precautions, and at Owner’s cost, Owner and its authorized representatives, including any Lender or a representative of any Lender, shall have the right to (a) maintain a reasonable presence at the Site and (b) upon reasonable advance notice to Contractor, have access at all reasonable times to any place where Work is being performed by Contractor or any Subcontractor to observe the Work, and upon notice from Owner, Contractor shall make arrangements and provide for such access.  All such Persons shall have the right to be present during the designing, engineering, procuring, construction, start-up, commissioning and testing, whether on or off the Site, and shall, by way of example and not limitation, have access to all test procedures, quality control reports and test reports and data, including all adjustment, installation and alignment data for the Equipment.  In order to allow Owner and its authorized representatives to be present, Contractor shall give Owner reasonable advance notice of any system or equipment check-out or testing with respect to which Owner specifically requests advance notice.

### Correction of Defects.  Before Substantial Completion Contractor shall, at its sole cost and expense, promptly correct any part of the Work which is defective or not in accordance with this Agreement, regardless of the stage of its completion or the time or place of discovery of such errors and regardless of whether Owner has previously accepted it through oversight or otherwise.  In the event that any part of the Work is discovered to be in a defective condition or not conforming to this Agreement after Substantial Completion, correction of such defective condition shall be governed by Article 12 of this Agreement.

### Tear-Out.  Before Substantial Completion Owner may request Contractor to tear out previously covered Work.  In the event Owner requests Contractor to tear out Work to permit Owner to inspect previously covered Work and (i) such tear-out is required as a result of Contractor’s failure to notify Owner that the Work to be torn out was ready for Owner inspection and Owner had notified Contractor of its desire to make such inspection or (ii) such Work inspected is defective, then Contractor shall bear the cost of such tear-out, repair and replacement.  Except in the case of (i) and (ii) in the prior sentence, Contractor shall be entitled, in accordance with Article 6, to recover reasonable additional costs incurred, if any, and to a reasonable extension of the Guaranteed Completion Date and the End Date in respect of any delay suffered as a result of complying with any request from Owner to tear out Work.

### Disclaimer.  No inspection or review by Owner or its representatives shall constitute an approval, endorsement or confirmation of any drawing, plan, specification, proposed Subcontractor, or Work or an acknowledgment by Owner or such other Person that drawing, plan, specification, proposed Subcontractor, or Work satisfies the requirements of this Agreement; nor shall any such inspection or review relieve Contractor of any of its obligations to perform the Work and furnish the Equipment so that the Facility, when complete, satisfies all the requirements of this Agreement.

## Security of  the Site;  Storage and Related Matters.

Contractor shall warehouse or otherwise provide appropriate storage for all Equipment (including, to the extent so specified in Exhibit N, spare parts and special tools) at or in the vicinity of the Site.  Contractor shall be responsible for the proper fencing, guarding, lighting and security of all of the Work and Equipment on the Site and for the proper provision of temporary roadways and footways on the Site as far as may be necessary to secure the Work.  All Equipment that is stored at a location other than on the Site shall be segregated from other goods and Contractor shall be responsible for the security and protection of all Equipment stored or warehoused off the Site.

## Cooperation and Non-interference.

Contractor acknowledges and accepts that Owner may engage other Persons to perform work or provide services in connection with the completion of the Facility which are not part of the Work and which may or may not be performed at or adjacent to the Site (the “Out of Scope Construction”). Contractor agrees to cooperate in good faith and use its reasonable efforts to coordinate performance of the Work so as to enable any Person performing the Out of Scope Construction to complete its work in a timely and efficient manner provided that (a) Contractor shall have no other liability or responsibility with respect to any out of scope construction and (b) Contractor shall be entitled to a Change in accordance with Article 6 if such cooperation increases Contractor’s cost or time to perform the Work or interferes with Contractor’s execution of the Work in accordance with this Agreement and the Project Schedule.

## No Liens.

### Creation of Liens.  Contractor shall not directly or indirectly create, incur, assume or suffer to be created by it or any Subcontractor, employee, laborer, materialman or other supplier of goods or services, any right of retention, claim, lien, charge or encumbrance on the Site, the Facility or any part thereof or interest therein (each a “Contractor Lien”). Contractor shall promptly pay or discharge, and discharge of record, or provide security reasonably acceptable to Owner with respect to, any such Contractor Lien or other charge which, if unpaid, might be or become a Contractor Lien.  Contractor shall immediately notify Owner of the assertion of any Contractor Lien.  [Revise.  We’ll subordinate our liens and indemnify re Subcontractors’ liens.]

### Indemnity from Liens.  Contractor shall indemnify, defend and protect Owner and Owner Indemnitees from and against all Contractor Liens, which indemnity shall survive the termination of this Agreement.  [Revise]

### Discharge of Liens.  Upon the failure of Contractor to promptly pay, discharge or provide security reasonably acceptable to Owner for any Contractor Lien within thirty (30) days of notice of the existence thereof from any source, Owner may pay or discharge such Contractor Lien and, upon the payment or discharge thereof, shall be entitled to immediately recover from Contractor the amount thereof together with all expenses incurred by it in connection with such payment or discharge or to set off all such amounts against any such sums owed by Owner to Contractor.

### No Waiver of Contractor Rights.   Nothing in this Section 3.16 shall be construed as a limitation on or waiver by Contractor of any of its rights to encumber the Facility or the Site as security for any past due payments owed to it by Owner hereunder and Contractor shall not have an obligation under Section 3,16.1, Section 3.16.2 and Section 3.16.3 to the extent of any past due payments; provided that Contractor may only exercise such right after providing Owner with thirty (30) days prior written notice of its intent to do so and provided further that Owner (or Lender on behalf of Owner) shall not have made such payment or provided a bond or other reasonably acceptable provision to secure such payment within such thirty (30) day period.

## Hazardous Substances, Archaeological Discoveries and Ground Risk.

### Existing.  Upon the discovery of any Hazardous Substances that were existing on the Site at or berfore the Effective Date of this Agreement, or of any article of value or antiquity or of archaeological or geotechnical interest, Contractor shall (a) promptly cease work in the affected area and direct its workers and Subcontractors not to remove or further disturb the material or item; (b) promptly notify Owner of such discovery; (c) use all reasonable efforts to mitigate the effects of any such discovery on the Site, any property or Person, and the performance of the Work; and (d) follow any and all directions of Owner or its representatives with respect to such discoveries.  Contractor shall not under any circumstances be required to remediate any existing Hazardous Substances. Owner shall be responsible for the removal from the Site, or for otherwise making the Site safe in accordance with [Host Country] Laws applicable thereto, any Hazardous Substances existing on the Site as of the Effective Date of this Agreement.  Contractor shall be entitled, in accordance with Article 6, to a Change [Order] to recover reasonable additional costs incurred, if any, and to a reasonable extension to the Guaranteed Completion Date and the End Date in respect of any delay suffered by reason of such discovery, Contractor’s compliance with its obligations under this Section 3.17.1, and/or Owner’s directions with respect to such discovery, in each case  other than as a result of Contractor’s breach of its obligations under this Section 3.17.1.  Any item of value or archaeological or geotechnical interest shall, as between Owner and Contractor, be deemed the property of Owner.

### Prior to Substantial Completion, Contractor shall be responsible for the removal from the Site or for otherwise making safe in accordance with applicable Laws any materials brought onto the Site by the Contractor during its construction activities at the Site which are toxic or similarly hazardous to the health or safety of persons or to the environment (excluding any pre-existing toxic or hazardous materials for which the Owner is responsible pursuant to Section 3.17.1). Owner shall notify the Contractor immediately upon the discovery of any such materials and shall provide such assistance as may be reasonably requested by the Contractor to facilitate the measures to be implemented by the Contractor pursuant to this Section 3.17.2.

Contractor shall be liable for and shall indemnify, protect, defend and hold harmless the Owner Indemnitees from and against any and all demands, claims, suits and causes of action and any and all liability, costs, expenses, settlements and judgments incurred in connection therewith (including court costs and attorney’s fees incurred by Owner if and only if Contractor fails to address such claim by its own attorneys, having received notice of the claim) that arise out of such toxic or hazardous materials for which the Contractor is responsible pursuant to this Clause 3.17.2.

### Site Conditions.  If during performance of the Work, Contractor encounters conditions at the Site other than those described in Sections 3.17.1 and 3.17.2 that increase Contractor’s cost or time for performance of the Work, which conditions include geological or geotechnical conditions, manmade underground obstructions, or endangered animals or plants (the “Site Variations”), Contractor shall be entitled to an adjustment to the Contract Price and/or Guaranteed Completion Date pursuant to a Change Order in accordance with the provisions of Article 6; provided, however, that (a) in the case of geotechnical conditions, a Site Variation shall only exist if the conditions vary from those assumptions set out in Exhibit B-2 and (b) no Site Variation shall exist as a result of foreseeable conditions that could have been observed by a qualified contractor during a site visit, such site visit being limited to a visual inspection of the routes to the Site, the Site and the configuration of the Site. Such increase in cost or time for performance shall be reflected in a Change Order under Article 6.

## Traffic and Special Loads.

Contractor shall carry out the Work so as not to interfere unnecessarily or improperly with access to and use of public roads.  Contractor shall liaise with, and ascertain the requirements of, all Governmental Authorities in relation to vehicular access to and use of public roads and shall comply with those requirements.  Contractor shall use all reasonable means to prevent damage to any highway or bridge by any traffic of Contractor or any Subcontractor, and, in particular but without limitation, shall select routes, choose and use vehicles, and restrict and distribute loads so as to avoid damage to public highways and bridges.  Contractor shall be responsible for the routing for delivery of heavy or large loads to the Site.  Contractor shall indemnify Owner for any loss suffered by Owner by reason of any damage to any public highway or bridge to the extent that Owner establishes that such damage was caused by any traffic of Contractor or any Subcontractor during performance of the obligations of Contractor under this Agreement.

## Waterborne Traffic.

Where the nature of the Work is such as to require the use by Contractor of waterborne transport, the provisions of Section 3.18 shall apply mutatis mutando and be construed as though the terms “road”, “bridge” and “highway” include each lock, dock, terminal, sea wall or other structure related to a waterway and the term “vehicle” includes watercraft and shall have effect accordingly.

## PPA Requirements.

Except as specifically noted in Exhibit B-2, Contractor shall carry out its obligations hereunder so as to ensure that the Facility is constructed in a manner that complies with the technical requirements of the PPA set forth on Exhibit ____.  [Owner shall promptly advise Contractor of any amendment to the PPA that imposes technical requirements different those set forth on Exhibit ____.  If and to the extent that such PPA amendment and resulting differences in Exhibit ____ give rise to requirement to make a modification to the Facility or to a change in the Scope of Work or the schedule, manner or sequence of execution of the Work as described in the Specifications, any such modification or change shall be deemed to constitute an Owner Change Request under Article 6.]

# OWNER’S RESPONSIBILITIES

## Owner Assistance to Contractor.

Owner shall be importer of record and shall be responsible for taking the actions set forth in Exhibit Q with respect to the importation of Equipment.  Contractor shall cooperate with and assist Owner in connection with Owner’s complying with the obligations imposed pursuant to this Section 4.1.  Owner shall expeditiously prepare and execute any papers that cannot be prepared or executed by Contractor and are necessary to import any Equipment.

## Owner’s Services.

In addition to its other obligations under this Agreement Owner shall, within the time frame and to the extent specified in Exhibit M, perform the obligations set forth in Exhibit M and elswhere in this Agreement (the “Owner’s Scope of Supply”).

## Payment.

Owner shall timely pay the Contract Price and all other sums, if any, required to be paid by it to Contractor pursuant to the terms of this Agreement, in each case in accordance with the provisions of Article 7.

## Access to Site and Rights of Way.

Owner shall provide at Owner’s expense, commencing not later than the date specified in the Project Schedule Summary, uninterrupted and unrestricted access to the Site and shall continue to provide Contractor and Subcontractors at Owner’s expense with such access to the Site until Substantial Completion.  Owner will arrange for all easements or other rights of way required for such access to the Site and performance of the Work until Substantial Completion.

## Governmental Authorizations.

Owner shall be responsible for obtaining or causing to be obtained, (a) the Governmental Authorizations listed in Exhibit K which shall include, but not be limited to, all environmental permits and authorizations for which it is designated as responsible for submitting and obtaining (b) all other Governmental Authorizations required in order for the Facility to be located and operated at the Site or which applicable Laws require to be issued in Owner’s name. Owner shall promptly deliver to Contractor copies of all such Governmental Authorizations. Owner shall use reasonable efforts (including, but not limited to, providing documents and information requested by Contractor) to assist Contractor in its efforts to obtain the Governmental Authorizations which it is required to submit and obtain pursuant to Section 3.5.

## Operating Personnel.

### Qualified Personnel for Training.  Owner shall supply, or cause to be supplied,  by not later than the date set out in Exhibit A, suitably qualified and, where necessary, licensed operators for training by Contractor as set forth in Exhibit O by no later than the date set out in Exhibit A unless Contractor has given at least sixty (60) days’ prior written notice of an earlier date for such providing such operators.  Owner shall supply, or cause to be supplied, such small tools, classrooms, office equipment and other similar equipment not provided by Contractor hereunder necessary to facilitate on-the-job training of the operations personnel as Contractor shall have notified Owner in adequate time will be required.

### Operators.  Subsequent to such training, Owner shall provide such operators to Contractor for the purpose of start-up, commissioning and performance testing of the Facility until Substantial Completion.  Such operators will work under the control and supervision of the Operator at Contractor’s direction until Substantial Completion.  Contractor shall be responsible for the acts and omissions of the operators while working at the Facility at Contractor’s direction, save to the extent that such acts or omissions constitute willful misconduct or gross negligence by the operators.

## Coordination with Utility.

Owner shall be responsible at all times for coordinating and communicating with Utility with respect to all matters arising under any Project Agreement, including the submission of notices and other documents and the handling and processing of comments and directions given by Utility.  Owner shall arrange for the grid access and  export of electrical energy from the Facility at all reasonable times when the Contractor desires to conduct start-up, commissioning, operation, or testing; provided that the Owner shall not be required to provide for such delivery before the date set forth for first delivery of electrical energy in Exhibit A unless Contractor has given at least sixty (60) days’ prior written notice of an earlier date for such delivery.

## Owner’s Representative.

On or before the Notice to Proceed Effective Date, Owner shall designate a representative (the “Owner’s Representative”), who shall be authorized to act on behalf of Owner, with whom Contractor may consult at all reasonable times, and whose instructions, approvals, requests and decisions shall be binding upon Owner as to all matters pertaining to this Agreement and the performance of Owner hereunder.  Owner’s Representative shall have authority to agree to a Change Order, but shall not have authority to otherwise amend this Agreement unless Owner has given written notice to Contractor of such express authority.  Owner may change Owner’s Representative at any time by written notice to Contractor.

## Divergences from Applicable Law.

If Owner becomes aware of any divergence between any Applicable Law or Governmental Authorization and the Specifications, Scope of Work or any other provision of this Agreement, it shall give Contractor written notice specifying the divergence.

## Owner Delay.

Contractor shall be entitled, in accordance with Section 6.8, to recover reasonable additional costs incurred, if any, and to a reasonable extension to the Guaranteed Completion Date and the End Date in respect of any delay suffered by reason of any Owner Delay.

## Compliance with Laws.

In the performance of its obligations under this Agreement, Owner shall ascertain and comply with all Laws and Government Authorizations that relate to the Owner and the performance of its obligations hereunder.  Owner agrees to indemnify, defend and hold harmless Contractor and Contractor Indemnitees from and against any and all fines, penalties, related costs and expenses, including reasonable legal expenses and costs, attributable to any failure of Owner to comply with such Laws and Governmental Authorizations in connection with the performance of its obligations under this Agreement.

## Taxes and Duties.

Owner shall be responsible for payment of (and such are not included in the Contract Price) those taxes, fees, levies, or other governmental charges identified in Part II of Exhibit C-7.

## Subcontractors.

Owner shall not direct or manage any of the Subcontractors, and shall only communicate with the Subcontractors through, and in coordination with Contractor.

# COMMENCEMENT OF WORK

## Commencement of Work.

### Preliminary Notice to Proceed.

Owner may, prior to issuing a Notice to Proceed, issue a preliminary notice to proceed authorizing Contractor to commence performance of the part of the Scope of Work as set out in Exhibit B-4 (the “Preliminary Notice to Proceed”).  Contractor shall commence with such part of the Scope of Work upon receipt of any Preliminary Notice to Proceed and shall thereafter proceed continuously and diligently to perform such Work. In the event that such Preliminary Notice to Proceed is issued prior to Financial Close, such Preliminary Notice to Proceed shall not be effective until Owner has furnished Contractor with an unconditional guaranty from a guarantor (having a Standard & Poors rating of BBB(-) or better) of Owner’s obligations under the Agreement in form and substance reasonably acceptable to Contractor or otherwise has demonstrated to Contractor’s satisfaction that Owner has access to sufficient financial and other resources to enable it to perform its obligations hereunder until Financial Close.  [What insurance should Owner have in place as a condition to PNTP?]

### Notice to Proceed.

Owner may issue a written notice to proceed (the “Notice to Proceed”) to Contractor at any time after the signing of this Agreement (the “Notice to Proceed Issue Date”); provided that the effective date of the Notice to Proceed (the “Notice to Proceed Effective Date”) shall not be until:

#### the satisfaction or waiver by Contractor of any conditions to the effectiveness of the Notice to Proceed set forth in Exhibit A;

#### the insurance required to be obtained by Owner pursuant to Article 9 shall be in effect and Owner shall have delivered to Contractor the certificates required by Section 9.3.2;

#### a minimum of [  xxx] days have passed since the date of the Preliminary Notice to Proceed, and

#### Financial Close shall have occured and Owner shall have provided Contractor with reasonably satisfactory evidence thereof, or Owner shall have provided Contractor with an unconditional guaranty from a guarantor (having a Standard & Poors rating of BBB(-) or better) of Owner’s obligations under the Agreement or Owner otherwise shall have demonstrated to Contractor’s satisfaction that Owner has access to sufficient financial and other resources to enable it to perform its obligations hereunder.

### Commitments.

Owner shall have no commitment to compensate Contractor for the performance of any Work, and Contractor shall have no obligation to perform any obligaiton or Work under this Agreement or related to the Facility until the earlier of the Notice to Proceed Effective Date or the Preliminary Notice to Proceed.

### Delays in Preliminary Notice to Proceed or Notice to Proceed Effective Date.

The Contract Price and Guaranteed Completion Date are based upon the following assumptions:

(i)	the Preliminary Notice to Proceed is issued by not later than [xxxxxdatexxxxx},

(ii)	the Notice to Proceed Effective Date occurs not later than [xxxxdatexxx].

Delays in meeting such dates shall be deemed to be Owner Delay.   If Owner issues the Preliminary Notice to Proceed but the Notice to Proceed Effective Date has not occurred within [xxxx] days of the Preliminary Notice to Proceed, such failure shall be deemed to constitute a suspension of the Work by Owner pursuant to Section 16.4.1 on the [xx]th day following the issuance of the Preliminary Notice to Proceed.

## Project Schedule.

### Preparation.  Within thirty (30) days following the Notice to Proceed Effective Date, Contractor shall prepare and submit to Owner a detailed construction schedule (the “Project Schedule”), consistent with the Project Schedule Summary, which shall be designed to have the Work completed on a timely basis by the Guaranteed Completion Date.  The Project Schedule shall be complete in all respects, covering engineering, procurement and delivery of Equipment, activities at the Site, and required dates for all items to be furnished by Owner.  In addition, Contractor shall submit a narrative description of its management plan for performing the Work to meet the Project Schedule.

### Revision and Updating.  Contractor shall promptly inform Owner of any proposed material change in the Project Schedule, and shall furnish Owner with a revised schedule and narrative.  The Project Schedule and narrative shall be kept up-to-date, taking into account the actual progress of the Work and shall be revised, if necessary, and included with the progress report required by Section 5.3.

## Progress Reports and Consultation.

### Progress Reports.  Contractor shall submit to Owner, by the sixteenth (16th) day of each month, a written progress report (in form reasonably satisfactory to Owner) that shall include, at a minimum, a description of the progress of the Work, details regarding the completion of any milestones in the Payment Schedule, the status of the supply of goods, materials and Equipment necessary for the completion of the Work, a comparison of the actual schedule of the Work with the Project Schedule, and an evaluation of problems and deficiencies and a description of any planned corrective action with respect thereto.  The monthly progress report shall be delivered to Owner’s Representative.  If Owner so directs, Contractor also shall at reasonable intervals conduct appropriate review meetings at mutually agreeable locations with representatives of Owner to review the status of the Work.  Contractor shall promptly notify Owner in writing if at any time Contractor has reason to believe that a material deviation in the Project Schedule will occur or has occurred which may result in Contractor failing to meet the Guaranteed Completion Date, and Contractor will specify in said notice or within a reasonable time thereafter any corrective action planned to be taken by Contractor.

### Additional Reports.  Should any material problem, emergency, strike, injury, work stoppage or legal problem be anticipated, or should any unanticipated event occur which might adversely affect Contractor’s ability to perform its obligations hereunder in a timely manner, in addition to all other reports required hereunder, Contractor shall promptly prepare a written significant event report detailing all available information and steps being taken to correct such problem or event and shall deliver the significant event report to Owner as soon as reasonably practicable.  Owner may at any time request a significant event report with respect to any event that Owner reasonably regards as significant.

# CHANGES [TO BE REPLACED]

## Changes and Change Orders.

### As used in this Agreement, “Change” shall mean an adjustment to the Contract Price, Project Schedule, Performance Guarantees, Warranties, Guaranteed Completion Date, End Date or other modification to this Agreement granted to Contractor pursuant to this Article 6 and other applicable provisions of this Agreement. Changes shall only result from a Change Order agreed or issued as described in Section 6.1.2.

### As used in this Agreement, “Change Order” means an instrument that is either agreed between and executed by Owner and Contractor or duly issued pursuant an arbitration in accordance with Section 19.2.2 to resolve a dispute regarding a Change Order Request. Each Change Order shall set forth the full particulars of the Changes covered by such instrument and any adjustments of the Contract Price, Project Schedule, Performance Guarantees, Warranties, Guaranteed Completion Date, End Date or other modification to this Agreement in connection with such Changes agreed to by the Parties or determined in accordance with Section 19.2.2.

## Owner Change Direction.

### Owner may from time to time during the performance of the Works issue Owner Change Requests by notice to the Contractor, provided that the Contractor shall be entitled to a Change

### As used herein, “Owner Change Direction” means any:

(a)	Owner requests for alterations of the Owner’s requirements for the Works and the Facility as stated in the Specification, the Scope Book, and any prior Change Order, whether by way of instruction, addition, modification or deletion which gives rise to a change in the Works as described in the Scope Book;

(b)	Owner requests for changes to any drawing or document submitted to the Owner for approval or for information pursuant to Clause 12; and

(c)	Owner instructions to the Contractor to vary the manner or sequence of execution of the Works;

that are within the general scope of the Agreement but excludes, in the case of paragraphs (b) and (c) above, any such alterations, changes or instructions which are necessary in order to ensure that the Facility when completed and the carrying out of the Works are in accordance with the Contract.

### Owner may not issue and Contractor shall not be required to perform any Owner Change Direction (a) that changes the Performance Guarantees, the Minimum Performance Guarantees, the Guaranteed Completion Date, or requires a change in the Works that is not technically feasible,  (b) would impair Contractor’s ability to design and construct the Facility so that, when so designed and constructed in accordance with that design, it will achieve the Performance Guarantees and Minimum Performance Guarantees or (c) cause a violation any applicable Law or Government Authorization.

## Change Order Requests.

### The Contractor shall be entitled to a Change:

(i)	if the Contractor receives an Owner Change Direction and is required to proceed therewith after providing to Owner a Change Order Request and the information required in Section 6.5 in connection with the Owner Change Direction, and

(ii)	upon the occurrence of any event of Owner Delay, Force Majeure, Change in Law, suspension of the Work pursuant to Section 16.4, differing site conditions pursuant to Sections 3.17.1 and 3.17.3, uncovering of Work pursuant to Section 3.13.3, failure to receive permanent electrical power or Feed Gas in accordance with Section 4.7, changes in the Scope of Work or other actions required by PDVSA,  or other event for which this Agreement entitles Contractor to a Change, and

(iii)	any such event or matter referred to in clause (i) or (ii) of this Section 6.3.1 causes an increase in the cost of or time required for performance of its obligations under this Agreement by Contractor or otherwise affect any provision of this Agreement.

### If Contractor believes that it is or will be entitled to a Change under Section 6.3.1, then Contractor shall provide the Owner with written notice requesting a Change Order (each, a “Change Order Request”).   Each Change Order Request from the Contractor must be supported with the information required pursuant with Section 6.5. Contractor shall be entitled to such Change as is commercially and technically reasonably necessary and appropriate in light of the event or matter giving rise to the Change Order Request and the rights and obligations of the Parties under this Agreement with respect to the Work.

### Within ten (10) days of receipt of a Change Order Request and the information required pursuant to Section 6.5, the Owner shall, by notice to Contractor, either: (i) issue a Change Order approving the Change Order Request; (ii) request reasonable additional information, documentation or cost detail to further assess the Change Order Request; or (iii) reject the Change Order Request.

### If Owner rejects the Change Order Request or the Parties are otherwise in dispute over  any Change Order Request or any part thereof, then either Party refer the dispute to  resolution in accordance with the provisions of Article 19.2.2  by providing the other with 30 days notice of its intent to do so.

### If Owner fails to agree to a Contractor request for an extension of the Guaranteed Completion Date to which Contractor is ultimately determined to be entitled, then Contractor, without limitation of any other rights hereunder, is entitled to a Change for any increased cost resulting from extraordinary efforts to meet the Guaranteed Completion Date during resolution of the dispute.

## NOT USED.

## Information Supporting Change Order Request.

Contractor shall prepare and submit to Owner along with each Change Order Request a report indicating in reasonable detail and accompanied where available by supporting documentation, (a) the matter or event giving rise to the Change Order Request, (b) the effect on the Project Schedule, Contract Price, Performance Guarantees, and other aspects of the Work and the Contractor’s ability to perform the Work in accordance with the Agreement resulting from such event, and (c) the Change sought by Contractor as a result of such event.  The price of any Work required to be added or deleted, as the case may be, in connection with a Change Order Request shall be either a lump-sum fixed price mutually agreed to by the parties [or a cost plus price calculated on the basis of Exhibit F,] unless the parties agree otherwise.  The explanation of the basis for any increase or decrease in the Contract Price shall include, as appropriate, relevant cost information regarding the portion of the original cost estimate that is affected by the event giving rise to the Change Order Request, vendor pricing for the cost of Equipment added or deleted as a result of such event, and estimated quantities of Equipment, other materials and labor added or deleted as a result of such event.

## Performance of Owner Change Directions.

### In connection with any Change Order Request based on an Owner Change Direction, the Parties are unable to agree on the Change that is to be granted to the Contractor (including whether any Change is to be granted to Contractor), after the Contractor has provided the information required in Section 6.5, then Contractor shall, if directed so by Owner, nevertheless proceed to perform the Works in accordance with the Owner Change Direction pending the resolution of such dispute, including by means of any proceeding under Section 19.2.2, [provided that the Parties have executed an agreement with respect to the impact on the Project Schedule (and the Guaranteed Completion Date and End Date are extended accordingly) and the Contractor is paid the costs incurred in performing such Change in accordance with Exhibit F subject to final adjustment in accordance with Section 19.2.2][ Does this really work? I know it’s a cash flow issue, but I think it will impeach EECC’s ability to get the lump sum with profit  at the end. Perhaps instead of  going reimburseable then trying to switch to lump sum, why not say all Changes will be at cost plus 10% (or A% for changes less than $X, and B% for changes more than $Y and be done with it all except for agreeing the cost basis? Will that converprofit and contingency?]]

### If, at any time after Contractor has been provided the information required in Section 6.5 with respect to an Owner Change Request, the Owner decides not to proceed with the Owner Change request, then Owner shall pay to Contractor the reasonable cost incurred by Contractor (a) in preparing and submitting such information to Owner and (b) the costs incurred by Contractor as a result of proceeding with the Owner Change Request.

## Other Provisions Unaffected.

Except to the extent a Change specifically amends one or more provisions hereof, all provisions of this Agreement shall apply to all Changes, and no Change shall be implied as a result of any other Change.

## Change in Law , Owner Delay or Force Majeure.

### Notice to Owner.  Contractor shall give timely notice to Owner of any event or circumstance of which Contractor has knowledge which constitutes Owner Delay, Change in Law, or Force Majeure which notice shall include the information required with respect to the associated Change that is required to be provided by Contractor pursuant to Section 6.5.  Such notice shall be issued promptly but in no event later than within ten (10) days following actual knowledge of such condition by Contractor.  If it is impracticable to specify the adjustments that Contractor will claim, then Contractor shall provide Owner with periodic supplemental notices to keep Owner informed of any change, development, progress or other relevant information concerning the event or circumstance.

### Notice to Contractor.  Owner shall give timely notice to Contractor of any event or circumstance which is, or Owner reasonably believes will become, Owner Delay, Change in Law, or Force Majeure (in the case of Force Majeure, Owner’s obligation to notify Contractor is limited to those events of Force Majeure which will effect Owner’s ability to perform its obligations under this Agreement).

### Mitigation of Event.  Contractor shall use reasonable efforts to remove or mitigate the effects of any Owner Delay, Change in Law or Force Majeure event.  Contractor mitigation obligations shall be limited to (I) covering and other reasonable efforts to protect work during any actual or threatened danger, (ii) resequencing of work in such a manner that does not cause significant cost or schedule impact, (iii) or any other reasonable efforts to mitigate the effect of such event, provided however, Contractor shall not be required to take any such actions which will incur substantial costs or impact the Project Schedule.  Should any such actions be required such action will be treated as a Change pursuant to Article 6.

# CONTRACT PRICE; PAYMENTS TO CONTRACTOR

## Contract Price.

### General.  Contractor agrees to perform the Work for the Contract Price.  The Contract Price is not subject to change except in accordance with the terms of this Agreement.

### Escalation.  The Contract Price is not subject to escalation except as set forth in Exhibit C-3.

### Allowances.  The Contract Price includes a budgetary allowance for those items identified as such and set forth on Exhibit C-1, which are included within the Scope of Work.  The amount set forth for each such item does not reflect a price for such item, but rather an allowance to be expended by Owner.  Contractor shall by the date specified in Exhibit C-1 provide a firm price for such item against adequate specification of such item.  If Owner accepts such price, then upon execution of an appropriate Change Order, the allowance shall be deducted from the Contract Price and such price added to the Contract Price.  [If Owner does not accept the price provided by Contractor, the price for such item shall be a cost plus price calculated on the basis of Exhibit F and the allowance shall be deducted from the Contract Price and such price added to the Contract Price.]

## Payment of Contract Price.

### Payment Schedule.  The Contract Price shall be paid to Contractor in the currency specified in accordance with the Payment Schedule, which sets forth the portion of the Contract Price allocable to each milestone.  The Payment Schedule shall be used as the basis for the preparation of progress invoices as described in Section 7.2.2.

### Monthly Invoices.  On or before the Notice to Proceed Effective Date, and thereafter on or before the tenth (10th) day of each month during the performance of the Work, Contractor shall furnish to Owner a detailed invoice for the period ending on the last day of the month preceding such month, setting forth the portion of the Contract Price allocable to the milestone actually completed by Contractor during such period or month, as the case may be, calculated in accordance with the Payment Schedule, and such supporting documentation and additional data as Owner may reasonably require to substantiate Contractor’s right to payment under this Section 7.2.

### Monthly Payments.  On or before the last business day of the month in which Contractor submits an invoice pursuant to Section 7.2.2, Owner shall pay to Contractor the full undisputed amount specified in such invoice.  All payments made by Owner to Contractor hereunder shall be made by wire transfer of immediately available funds to the account of Contractor designated by written notice to Owner.

### Retainage.  The last five percent (5%) of the Contract Price (the “Retainage”) shall be retained by Owner until the earlier of successful completion of the Availability Test or the posting of the Retention Bond pursuant to Section 21.1.

### Final Payment.  Following Substantial Completion, Contractor shall submit to Owner a statement summarizing and reconciling all previous invoices, payments and Change Orders and an affidavit that all payrolls, payroll taxes, liens, charges, claims, demands, judgments, security interests, bills for materials and Equipment and other indebtedness in connection with the Works for which Contractor may in any way be responsible, have been paid or released, as the case may be, accompanied by releases and waivers of liens from Contractor and each of its Subcontractors under a Major Subcontract and such other data as Owner or any Lender may reasonably request establishing payment of or surety for payment of all such obligations.  To the extent there is a bona fide dispute with a Subcontractor, Contractor may post a letter of credit issued by a commercial bank assigned a rating of at least A by Standard & Poor’s or comparable rating from another similarly recognized national rating agency, or in lieu of  letters of credit, an escrow of funds to satisfy any such Subcontractor in lieu of such waiver.  Within thirty (30) days of the receipt of such statements and letters of credit, Owner shall pay Contractor the remaining portion of the Contract Price, but less any Retainage and any Punchlist Withholding not secured pursuant to Section 21.1.

## Payments Not Waiver or Acceptance of Work.

No payment made by Owner under this Agreement shall constitute a waiver of any claim or right Owner may have at that time or thereafter, including claims regarding unsettled liens, warranty rights and indemnification obligations of Contractor.  No payment made by Owner under this Agreement shall be considered or deemed to represent that Owner has inspected the Work or checked the quality or quantity of the Work or that Owner knows or has ascertained how or for what purpose Contractor has used sums previously paid, and no payment shall not be deemed or construed as an approval or acceptance by Owner of any Work or as a waiver of any claim or right Owner may have hereunder.  All payments shall be subject to correction or adjustment in subsequent progress reviews and payments.

## Payment of Subcontractors.

Contractor shall promptly pay, in accordance with the terms and conditions set forth in the respective Subcontract, each Subcontractor the amount to which said Subcontractor is entitled.  Contractor shall, by an appropriate agreement with each Subcontractor, require each Subcontractor to make timely payments to its laborers, suppliers and subcontractors in a similar manner.

## Waiver of Liens.

As a condition precedent to the obligation of Owner to make each payment under this Agreement, Contractor shall supply Owner with a waiver and release of liens to the extent of such payment in substantially the form set forth in Exhibit D or otherwise reasonably acceptable to Owner and any Lender, duly executed and acknowledged by Contractor in order to assure an effective release of mechanics’ or materialmen’s liens to the extent permitted by Law set out in such form only.  [What are last six words intended to do?]

## Interest and Disputed Invoices.

Amounts not paid by either party to the other when due under any provision of this Agreement, including the provisions of this Article 7, shall bear interest from the date payment was originally due to and including the actual date of payment at the Default Rate.  If there is any dispute about any amount invoiced by Contractor, the amount not in dispute shall be promptly paid and any disputed amount which is ultimately determined to have been payable shall be paid with interest at the Default Rate from the date the item was payable to and including the actual date of payment.

# TITLE AND RISK OF LOSS

## Title.

### Warranty of Title.  Contractor warrants good title to all Work and Equipment and warrants and guarantees that title, when it passes to and vests in Owner as described in this Section 8.1, will be free and clear of any and all liens, claims, charges, security interests, encumbrances and rights of other Persons arising as a result of any actions or failure to act of Contractor, its Subcontractors, or their employees or representatives.  [Check precedents re equipment identified to the job.]

### Title to Work.

#### Title to all Work and Equipment performed and sourced in country will pass to Owner upon delivery of such Work or Equipment to the Site.

#### Title to all Work and  Equipment performed and sourced offshore will pass to Owner prior to departure from the port of export, or as otherwise required in accordance with the project import plan.

### Title to Drawings.  Title to drawings, designs, plans, specifications and like materials specifically prepared as part of the Work will remain with Contractor.  Subject to Article 20, Contractor grants to Owner an irrevocable, non-exclusive, royalty-free license to use and reproduce Contractor and Subcontractor drawings, designs, plans, specifications and other design documentation to which Contractor has title or has the right to grant sub-licenses solely for the purposes of constructing, operating, maintaining, rebuilding, or modifying the Facility.  Owner shall have the right to assign the benefit of such license to any Lender in connection with the grant of a security interest in the Facility, to a purchaser of the Facility or to any subsequent assignee of same.  Owner may retain the necessary number of copies of all such documents for the purposes allowed by the license.

### Control of Software and Other Proprietary Material.  Owner recognizes that the software and other proprietary intellectual software and other intellectual property provided by Contractor to Owner as part of the Scope of Work carries with it certain restrictions on use and copying of such software and other intellectual property and that such software and other intellectual property will not be duplicated, used, printed, displayed, modified or disclosed or provided to a third party without Contractor’s express written authorization, provided that Owner shall have the right to assign the benefit of such software and other intellectual property and the license granted below to Lender in connection with granting a security interest in the Facility, to a purchaser of the Facility, or to any subsequent assignee of the same.  Contractor represents and warrants that it has all rights and licenses necessary for it to provide such software and other intellectual property to Owner as contemplated in this Agreement and grants to Owner an irrevocable, non-exclusive and royalty-free license to use and reproduce such software and other intellectual property in connection with the construction and operation of the Facility.  Such license allows Owner only the limited right to use and reproduce the software and other intellectual property as contained herein and shall not convey any title to or ownership in the software and other intellectual property to Owner or any Person to whom Owner is permitted to assign its license.  Owner agrees to indemnify Contractor against any third party claims made against Contractor resulting from unauthorized duplication, use, printing, display, modification or disclosure of such software and other intellectual property by Owner.

## Risk of Loss.

### Prior to Substantial Completion.  Notwithstanding passage of title as provided in Section 8.1, Contractor shall bear the risk of loss of and damage to, and shall be obligated to repair, replace, or reconstruct, all or any portion of the Work which is lost, damaged or destroyed prior to Substantial Completion, unless such loss, damage or destruction is caused by an event of Force Majeure.

### After Substantial Completion.  After Substantial Completion, to the extent Contractor shall continue to perform Work on Punchlist Items, on warranty claims or to conduct the Availability Test, then Contractor shall remain liable, in connection with the performance of such Work, for the risk of loss of and damage to, and shall be obligated to replace, repair or reconstruct, any previously completed and turned over Work to the extent any loss of or damage to such Work is caused by the fault or negligence of Contractor, any of its Subcontractors or any Person acting under the direction and control of Contractor or any Subcontractor provided that such liability of Contractor shall be limited to the deductible under the insurances required under Article 9.  Notwithstanding Sections 8.2.1 and 8.2.2, Contractor shall not be obligated to repair, replace or reconstruct the whole or any part of the Facility which is lost, damaged or destroyed by an event which is covered by insurance obtained by Owner pursuant to Article 9 (including under the maintenance-period-coverage endorsement to the builder’s all risk policy required pursuant to Article 9 but excluding, for the avoidance of doubt, any Delay in Start-Up insurance obtained by Owner) to the extent that Owner is unable to make the proceeds of such insurance in respect of such loss, damage or destruction available to Contractor because such payment would be prohibited by the terms of any financing arrangement entered into by Owner with any Lender.

## Use by Owner.

Owner may, with Contractor’s consent, occupy or use any complete or partially completed portion of the Work (other than the Power Islands or any component thereof) at any stage, provided that such occupancy or use is approved by the builders all risk and property insurer (unless the risk management departments of both Owner and Contractor confirm that such approval is not necessary) and provided further that such occupancy or use is in compliance with applicable Laws and is for the purpose that such portion of the Work was intended.  Such partial occupancy or use may commence prior to Substantial Completion only if Owner and Contractor have agreed in writing to any changes to this Agreement necessitated by such use, including changes with respect to the risk of loss and damage of such completed or partially completed portion of the Work and changes with respect to acceptance of such Work by Owner.  Consent of Contractor to partial occupancy or use shall not be unreasonably withheld or delayed.

# INSURANCE

[REVISE WHEN EECC DATA ARRIVES]

## Contractor’s Insurance.

### Required Coverages.  Prior to the start of the Work and thereafter until the end of the Warranty Period, Contractor will obtain and maintain at its expense the insurance described on Exhibit H-1 with an insurance company or companies licensed to do business as required by applicable Laws and rated “A” or better by Best’s Insurance Guide and Key Ratings or with security otherwise reasonably acceptable to Owner.

### Requirements of Contractor’s Insurance.  The insurance provided by Contractor pursuant to this Section 9.1 shall be primary unless stated otherwise in Exhibits H-1 and/or H-2 as respects Owner, Utility, any Lender and their respective directors, officers, representatives, agents and employees, and any other insurance obtained and maintained by Owner or any Lender shall be excess of and shall not contribute with such insurance except as specifically stated herein.  In addition, all such insurance shall include those provisions set forth on Exhibit H-1.

### Payment of Deductibles.  The insurance provided by Contractor pursuant to this Section 9.1 shall have reasonable deductibles and Contractor shall be solely responsible for the payment of all such deductible amounts, unless the loss or damage is caused in whole or in part by the fault or negligence of Owner, in which case the deductible shall be shared or apportioned as between Contractor and Owner in proportion to the degree of fault of each.

## Owner’s Insurance.

### Required Coverage.  Prior to the start of the Work and thereafter until Substantial Completion, Owner shall obtain and maintain the insurance described in Exhibit H-2 with (a) an insurance company or companies licensed to do business as required by applicable Law and rated “A(-)” or better by Best’s Insurance Guide and Key Ratings or equivalent, (b) an insurance company or companies which is or are not so rated provided that in such case the risk placed with such insurance company or companies is either reinsured with or the subject of contingency liability cover obtained and maintained with an insurance company or companies which is or are so rated, or (c) an insurance company or companies otherwise reasonably acceptable to Contractor.

### Requirements of Owner’s Insurance.  The insurance provided by Owner pursuant to Section 9.2 shall be primary, unless stated otherwise in Exhibit H-2, as respects Contractor, its Subcontractors and their respective directors, officers, representatives, agents and employees, and any other insurance obtained and maintained by Contractor or its Subcontractors shall be excess of and shall not contribute with such insurance.  In addition, all such insurance shall include those provisions set forth in Exhibit H-2.

### Payment of Deductibles.  The insurance provided by Owner pursuant to Section 9.2 shall have the deductibles provided in Exhibit H-2, and Owner shall be solely responsible for the payment of all such deductible amounts, unless the loss or damage is caused in whole or in part by the fault or negligence of Contractor, any Subcontractor or any Person acting under the direction and control of Contractor or any Subcontractor, in which case the deductible shall be shared or apportioned as between Contractor and Owner in proportion to the degree of fault of each.

## Certificates and Cancellations.

### Contractor Certificates.  Contractor shall, on or prior to commencement of activities on the Site, deliver to Owner certificates of insurance evidencing compliance with the requirements of Section 9.1.

### Owner Certificates.  Owner shall, consistent with the timing set out in Section 9.2, deliver to Contractor certificates of insurance evidencing compliance with the requirements of Section 9.2.

### Notice of Cancellation.

#### All policies of insurance to be secured and maintained hereunder shall provide, by endorsement, that the other party and any additional insured, where required in writing, shall be provided forty-five (45) days prior written notice of any material policy changes or cancellations (except two (2) days for non-payment of premium), and that no such cancellation or change shall be effective without such notice.

#### Contractor shall immediately notify Owner regarding the occurrence of any of the following events: (a) any significant loss covered by a policy required to be maintained by this Article 9; (b) any significant dispute with an insurer; (c) the early cancellation of any policy; (d) the failure to pay any premium payment; (e) the failure, for any reason, to maintain any policy required to be maintained by this Article 9; and (f) any significant change in any insurance coverage contracted for by Contractor.

## Failure to Pay.

Irrespective of the requirements for insurance to be secured and maintained hereunder, the insolvency, bankruptcy or failure of any insurance company carrying insurance of any party, the failure of any insurance company to pay claims accruing, shall not affect, negate or waive any of the provisions of this Agreement, including, without exception, the indemnity obligations of any party.

## Miscellaneous.

### Non-waiver.  Failure of either party to comply with the foregoing insurance requirements shall in no way waive its obligations or liabilities under this Agreement or the rights of Owner hereunder against Contractor, or the rights of Contractor hereunder against Owner.

### Right to Insure.  Should either party fail to provide or maintain any of the insurance coverage required under this Article 9, the other party shall have the right to provide or maintain such coverage at the failing party’s expense, either by direct charge or set-off.

### Subcontractor Insurance.  Before permitting any Subcontractor to perform any Work, Contractor shall obtain a certificate of insurance from each such Subcontractor evidencing that such Subcontractor has obtained, from insurance carriers licensed to do business as required by applicable Laws and rated “A” or better by Best’s Insurance Guide and Key Ratings or with security otherwise reasonably acceptable to Owner, insurance in such amounts and against such risks as is prudent in light of the work to be performed by such Subcontractor, and subject to the commercial availability of such insurance and commensurate with normal practices in the location where such Work is performed.

### Compliance with Insurance.  Contractor and its directors, officers, representatives, agents and employees shall comply with all the terms of the policies of insurance referred to in Section 9.2 and in any Delay in Start-Up and Business Interruption insurance obtained by Owner.  Contractor and its directors, officers, representatives, agents and employees shall comply with the procedures for claims notification and administration under the aforesaid insurance policies and shall not do or omit to do anything which might render voidable policies of insurance or entitle insurers to avoid liability thereunder.  Contractor shall ensure that all Major Subcontracts shall include provisions in the same terms as this Section 9.5.4.  [ RELOOK]

### Insurance Surveyor.  The costs of the insurance surveyor shall be paid by Owner.

# DOCUMENTATION

## Delivery of Job Books.

At least sixty (60) days prior to commencement of commissioning of the first major Facility system, Contractor shall deliver to Owner eight (8) copies of the semifinal draft of the job books for the Facility (the “Job Books”) in the format and including the information and materials described in Exhibit R.  Such semifinal draft shall be without as-built drawings, but as reasonably complete as available information will allow, with sufficient information to permit the training of Owner’s operators and the normal operation and maintenance of the Facility by Persons generally familiar with plants similar to the Facility.  [Prior to Final Completion, Contractor shall provide to Owner eight (8) copies of the final Job Books, including complete sets of as-built drawings pursuant to the provisions of Exhibit R.]  For any early start-up of an individual unit or system, Contractor shall provide on a timely basis the appropriate portions of the Job Books containing adequate information to enable proper orientation and training of qualified personnel to permit a safe, efficient and effective start-up of such unit or system.

## Machine Readable Information.

Where any of the information to be provided by Contractor to Owner pursuant to this Article 10 is produced on computer or is otherwise available in magnetic, optical or other digital machine readable form, Contractor shall provide to Owner a copy of such information.  However, because of the possibility that information and data delivered in machine readable form may be altered, whether inadvertently or otherwise, and the automated conversion of information and data from the system and format used by Contractor to an alternate system or format cannot be accomplished without the possibility of inexactitudes, anomalies, and errors, Owner shall use such information in machine readable form at its sole risk, and Contractor shall bear no liability for such use.  Contractor shall retain hard copy originals of all documentation delivered to Owner in machine readable form, which originals shall be referred to and shall govern in the event of any inconsistency between the two.

# COMPLETION [to be revised]

## Notices.

Contractor shall give Owner the notices of testing required by Exhibit E-3.

## Substantial Completion Certificates.

The Facility shall be considered substantially complete (“Substantial Completion”) upon receipt and acceptance by Owner of a certificate from an officer of Contractor substantially in the form of Exhibit J-1 (the “Substantial Completion Certificate”) certifying the following to be true and correct:

### the Facility is substantially complete in accordance with the Scope of Work, the Specifications and all applicable Governmental Authorizations and permits, and can be safely operated for its intended purpose;

### all Work required to be furnished by Contractor for the Facility is substantially complete and all Equipment has been delivered to the Site and properly incorporated into the Facility, except for Punchlist Items;

### the Performance Tests required for Substantial Completion as specified in Exhibit E-3 have been successfully completed and a certificate of the results has been received by Owner;

### any Delay Liquidated Damages due have been paid;

### the Punchlist has been received and accepted by Owner;

### Contractor has sufficiently completed the Facility to allow Owner to enter into commercial operation under the relevant Project Agreements;

### the Facility has met all applicable completion and testing requirements set out in the Project Agreements;

### Mechanical Completion has been achieved;

### the Facility has met the Performance Guarantees which are listed in Part I of Exhibit E-1 as a criteria for Substantial Completion or Contractor has either paid any Performance Liquidated Damages due or has posted bond securing such amount; and

### The Facility has met the Minimum Performance Guarantees which are listed in Part I of Exhibit E-1 as a criteria for Substantial Completion

Together with such certificate, Contractor shall deliver to Owner a written report with respect to the test requirements listed above and the status of the Work in sufficient detail to enable Owner to independently determine whether Substantial Completion has occurred.

## Final Completion.

The Facility will be deemed to be finally complete (“Final Completion”) upon the receipt and acceptance by Owner of a certificate from an officer of Contractor substantially in the form set forth in Exhibit J-2 (the “Final Completion Certificate”) certifying each of the following to be true and correct:

### Substantial Completion has occurred and all Punchlist Items have been completed;

### the Availability Test has been successfully completed and a certificate of the results has been received by Owner;

### Contractor’s obligations under Section 3.7 and Article 10 have been completed;

### Contractor has provided the waiver and release required pursuant to Section 7.5; and

### Contractor has met all its obligations under this Agreement other than the warranty obligations under Article 12 and any obligations that survive the termination of this Agreement.

### the Facility has met the Performance Guarantees which are listed in Part I of Exhibit E-1 as a criteria for Final Completion or Contractor has either paid any Performance Liquidated Damages due or has posted bond securing such amount.

### The Facility has met the Minimum Performance Guarantees which are listed in Part I of Exhibit E-1 as a criteria for Final Completion.

## Owner Acceptance of Completion Certificates.

Within ten (10) days after receipt of either a Substantial Completion Certificate or Final Completion Certificate, Owner shall either (a) notify Contractor of its acceptance of such certificate and acknowledge that Substantial Completion or Final Completion has occurred, or (b) if reasonable cause exists for doing so, notify Contractor in writing that Substantial Completion or Final Completion has not been achieved, stating in detail the reasons therefor.  If Owner notifies Contractor that in Owner’s opinion Substantial Completion or Final Completion has not been achieved, Contractor may at any time immediately refer the matter for resolution in accordance with Section 19.2.2, otherwise Contractor shall promptly take such action or perform such additional Work or other services as will achieve Substantial Completion or Final Completion and then issue to Owner another Certificate pursuant to Section 11.2 or 11.3.  Owner shall respond to any such subsequent certificate from Contractor within seven (7) days following receipt.  Such procedure shall be repeated until such time as Owner has acknowledged Substantial Completion or Final Completion.  The failure of Owner to respond to any certificate submitted by Contractor within the time period required in this Section 11.4 shall be deemed an acceptance of the certificate and acknowledgment of Substantial Completion or Final Completion by Owner. Effective date of Substantial Completion and Final Completion shall be the day on which the requirement for Substantial Completion or Final Completion, as the case may be, have been completed, ______ as certified by the Contractor and accepted by Owner, or otherwise as determined pursuant to Article 19.2.7.

## Punchlist.

### Punchlist Preparation.  Prior to Substantial Completion, Owner and Contractor shall  inspect the Facility and Contractor shall prepare a listing of the outstanding Punchlist Items and provide it to Owner together with an estimate of the cost and time to complete or correct each such Punchlist Item.  In each case, such Punchlist Items shall not be grounds for not accepting the Substantial Completion Certificate.  The draft Punchlist shall be prepared in accordance with Contractor’s quality assurance manual and submitted to Owner for review.  Owner shall review and comment on the Punchlist not later than five (5) days after Owner’s receipt thereof, and Contractor shall issue a revised Punchlist to Owner that takes account of or responds to Owner’s comments not later than five (5) days after Contractor’s receipt of such comments. Any dispute between Owner and Contractor regarding the Punchlist shall be resolved in accordance with the procedure set forth in Section 19.2.

### Punchlist Withholding.  Owner shall withhold (the “Punchlist Withholding”) an amount equal to one hundred fifty percent (150%) of the estimated cost of correcting all outstanding Punchlist Items from the payment due to Contractor and retain such amount until the Punchlist Items are corrected or until a Retention Bond covering such Punchlist Withholding has been provided as set forth in Section 21.1.

### Correction of Punchlist Items.  Promptly after receipt by Owner of the revised Punchlist, Contractor and Owner shall agree upon a schedule for Contractor’s completion of the Punchlist Items that will allow Contractor to complete such Punchlist Items within a reasonable period of time without interfering with the operation of the Facility.  Owner shall provide Contractor reasonable access to the Facility to perform such Work in accordance with such schedule to the extent that such access does not interfere with the operations of the Facility.

### Right of Waiver.

Owner shall have the right, but shall have no obligation, to waive, defer or reduce any of the requirements stated in this Article 11 at any time.  However, Owner’s exercise of any rights hereunder shall apply only to such requirements as Owner may specify in writing and shall in no event relieve Contractor of any requirements or other obligations not so specified.

## Long-Term Obligations.

It is expressly understood and agreed by the parties that nothing in this Article 11 shall in any way modify or alter Contractor’s obligations under Articles 12 and 13.

# WARRANTY [TO BE REVISED]

## General Warranty.

Contractor represents and warrants that it is and will be at all times fully qualified and capable of performing the Work in accordance with the terms of this Agreement. Contractor warrants that all services provided and procedures followed by Contractor hereunder shall be in accordance with the manufacturer or vendors’ warranty requirements, GIP and all requirements of this Agreement.  Contractor warrants that the Facility shall be designed, engineered and constructed to meet the requirements of this Agreement so that the Facility, when operated and maintained in accordance with the Technical Limits, will be capable of operating in accordance with GIP and the technical requirements [of the Project Agreements].  Contractor further warrants that the Work, including each item of Equipment and other items furnished by Contractor, shall be new and of good quality, shall be free from defects in field design and engineering, materials, construction, and workmanship, and shall conform in all respects with all applicable Laws and Governmental Authorizations in effect at Substantial Completion, the Specifications, Scope of Work and all other requirements of this Agreement.  [Exclude Performance Guarantees]

## Warranty Period.

The warranty set forth in Section 12.1 shall extend for a period of twelve (12) months following Substantial Completion of all Work (the “Warranty Period”).  The Warranty Period with respect to any Work or Equipment that is repaired, replaced, modified or otherwise altered or corrected after Substantial Completion shall extend for twelve (12) months from the date of completion of such repair, replacement, modification, correction or alteration, provided that in no event shall the Warranty Period extend beyond twenty-four (24) months from Substantial Completion.

## Remedy.

Owner shall promptly give notice to Contractor of the discovery during the Warranty Period of any breach of Contractor’s warranties under Section 12.1.  Contractor, on an expedited basis if so requested by Owner, shall correct or replace the applicable Work or Equipment at no cost to Owner.  Promptly after receipt by Contractor of such notice, Contractor and Owner shall agree upon a schedule for Contractor’s performance of its warranty obligations which will allow Contractor to complete such work within a reasonable period of time without unreasonably interfering with the operation of the Facility.  Owner shall provide Contractor with full and free access to the Facility to perform such warranty obligations in accordance with such schedule.  Any change to the Work that would alter the Scope of Work or the Specifications may be made only in accordance with the terms of Article 6.  If, after notification of such defect, Contractor shall unreasonably delay in commencing, continuing or completing the remedying of such defect in accordance with the agreed schedule, then Owner may correct such defect and Contractor shall be liable for all reasonable costs, charges and expenses incurred by Owner in connection with such repair or replacement and shall pay to Owner an amount equal to such costs, charges and expenses upon receipt of invoices from Owner.  The remedies of Owner under this Section 12.3 and Section 16.1.2.3 are the exclusive remedies of Owner arising out of the warranties set forth in Section 12.1 and any remedies to which Owner would otherwise be entitled at law arising out of such warranties are hereby excluded.

## Subcontractor Warranties.

Contractor shall use reasonable efforts to obtain standard vendor warranties for the benefit of Contractor and Owner for all Equipment with warranty periods equal to or longer than the Warranty Period.  If such warranties extend beyond the Warranty Period, then they shall be transferred to Owner at the end of the Warranty Period, together with an assignment to Owner, or other acceptable provision for Owner enforcement or Contractor enforcement on behalf of Owner of any security, bond or other performance guarantee with respect to such warranties, and Contractor shall act as liaison for Owner with such vendors in prosecuting any warranty claims.

## Warranty Exclusions.

The duties, liabilities and obligations of Contractor under this Article 12 do not extend to any repairs, adjustments, alterations, replacements or maintenance which may be required as a result of normal wear and tear in the operation of the Facility, normal degradation in the performance of Equipment, or as a result of Owner’s failure to operate or maintain the Facility in accordance with the Technical Limits.

## No Implied Warranties.

THE EXPRESS WARRANTIES SET FORTH IN THIS AGREEMENT ARE EXCLUSIVE AND NO OTHER WARRANTIES OF ANY KIND, WHETHER STATUTORY, WRITTEN, ORAL, EXPRESS OR IMPLIED (INCLUDING WARRANTIES OF FITNESS FOR A PARTICULAR PURPOSE OR MERCHANTABILITY AND IMPLIED WARRANTIES OF CUSTOM OR USAGE) SHALL APPLY.  THE REMEDIES SPECIFIED IN THIS AGREEMENT FOR ANY BREACH OF WARRANTY ARE THE EXCLUSIVE REMEDIES FOR ANY AND ALL SUCH BREACHES, AND NO OTHER REMEDY SHALL APPLY.  OWNER HEREBY WAIVES AND RELEASES, AND AGREES TO INDEMNIFY AND HOLD CONTRACTOR HARMLESS FROM AND AGAINST ANY AND ALL OTHER CLAIMS OF WARRANTY OR FOR REMEDIES FOR BREACH OF WARRANTY OTHER THAN THOSE EXPRESSLY SET FORTH IN THIS AGREEMENT.

## Exclusive Remedies.

OWNER AND CONTRACTOR INTEND THAT THEIR RESPECTIVE RIGHTS, OBLIGATIONS AND LIABILITIES AS PROVIDED FOR IN THIS AGREEMENT SHALL BE EXHAUSTIVE OF THE RIGHTS, OBLIGATIONS AND LIABILITIES OF EACH OF THEM TO THE OTHER ARISING OUT OF, UNDER OR IN CONNECTION WITH THIS AGREEMENT OR THE WORK, WHETHER SUCH RIGHTS, OBLIGATIONS AND LIABILITIES ARISE IN RESPECT OR IN CONSEQUENCE OF AN INDEMNITY OR WARRANTY OR BY REASON OF ANY BREACH OF CONTRACT OR OF STATUTORY DUTY OR BY REASON OF TORT (INCLUDING NEGLIGENCE AND STRICT OR ABSOLUTE LIABILITY) OR OTHERWISE.  ACCORDINGLY, THE REMEDIES EXPRESSLY STATED IN THIS AGREEMENT ARE INTENDED TO BE THE SOLE AND EXCLUSIVE REMEDIES OF THE PARTIES TO THIS CONTRACT FOR THE LIABILITIES OF SUCH PARTIES ARISING OUT OF OR IN CONNECTION WITH THE WORK OR THIS AGREEMENT, NOTWITHSTANDING ANY REMEDY OTHERWISE AVAILABLE AT LAW OR IN EQUITY.

# SCHEDULE GUARANTEES

## Guarantee of Timely Completion.

Time is of the essence in the performance of this Agreement.  Contractor shall administer and perform the Work in accordance with the Project Schedule and guarantees that Substantial Completion shall occur by the Guaranteed Completion Date and Final Completion shall occur by the End Date.

## Completion.

Contractor shall, prior to Substantial Completion, achieve Mechanical Completion.

## Delay Liquidated Damages and Early Completion Bonus.

### In the event Contractor fails to achieve Substantial Completion prior to the Guaranteed Completion Date, Owner may invoice Contractor on a monthly basis for the applicable Delay Liquidated Damages at the rate set forth on Exhibit C-4 with payment due from Contractor within thirty (30) days following submission of such invoice.  Owner may offset any such amounts in whole or in part against amounts due to Contractor under this Agreement.  [Contractor shall, however, be discharged on a day-to-day basis from its obligation to pay Delay Liquidated Damages to the extent that Owner is entitled to receive proceeds under any Delay in Start-Up insurance which Owner may obtain and such proceeds are directly related to an insured loss or damage which caused Contractor to fail to achieve Substantial Completion prior to the Guaranteed Completion Date.]  Such discharge shall not apply to any period of delay that is covered by any deductible under the Delay in Start-Up insurance and shall not include any deductible period under the Delay in Start-Up insurance.

### In the event Contractor causes the Facility to achieve Substantial Completion prior to the Guaranteed Completion Date Owner will pay Contractor an Early Completion Bonus at the rate setout in Exhibit C-4.

## Performance Guarantees and Liquidated Damages.

### Performance Guarantees.

Contractor guarantees that the Facility will meet the Performance Guarantees during the relevant Performance Tests.

### Performance Liquidated Damages.

Contractor agrees to pay Owner the Performance Liquidated Damages, to the extent that the Facility does not meet the Performance Guarantees during the relevant Performance Tests [ which was the basis for declaring Substantial Completion ] and pursuant to Section 13.6.4, on each case at the rates and subject to the limits applicable to the performance CD as set forth in § _____.

### Payment of Performance Liquidated Damages.

Contractor shall pay any Performance Liquidated Damages due to Owner upon Contractor’s submission of the Substantial Completion Certificate.  Owner may offset any such amounts in whole or in part against amounts due to Contractor under this Agreement.  All Performance Liquidated Damages not paid on or before the date due shall accrue interest at the Default Rate from the date due until the date paid.

## Performance Tests.

Contractor is responsible for conducting and supervising the Performance Tests and the Availability Test as part of the Work and such tests may be witnessed by Owner and its designated representatives.  The notices required, the procedures to be followed and the method of evaluation of the results of such tests shall be as provided in Exhibit E-3 and the detailed test procedure to be developed by Contractor.

## Contractor’s Right to Improve Performance.

If Substantial Completion is declared at less than the Performance Guarantees, then from and after Substantial Completion until the End Date, Contractor shall have the right to redesign and repair the Facility to improve the performance so as to meet or exceed the Performance Guarantees as follows:

### [Contractor must notify Owner in the Substantial Completion Certificate that Contractor has elected to attempt to improve the Facility performance and must pay to Owner all Performance Liquidated Damages due under this Agreement.]

### Contractor and Owner shall in good faith negotiate and agree upon the scope of work Contractor shall perform and the schedule for performing such work, including a repetition of the applicable Performance Tests.  If Contractor and Owner are unable to agree upon such matters, then the dispute may be submitted to dispute resolution in accordance with Article 19.  Contractor and Owner shall cooperate in good faith such that Contractor’s work following Substantial Completion shall not interfere with or interrupt the normal operation of the Facility in accordance with the Project Agreements.

### If Contractor is able to repair, redesign or modify the Facility such that the performance of the Facility improves during the repetition of the applicable Performance Test, then it shall be due a refund of an appropriate portion of any Performance Liquidated Damages.  The method for calculating such a refund is set forth in Exhibit __.  Any such refund will be due and payable to Contractor within thirty (30) days of delivery of a certificate to Owner setting forth the values achieved during the repetition of the applicable Performance Test and the calculations supporting such refund.

# LIMITATION OF LIABILITY [to be further revised]

## Maximum Liability.

Contractor’s maximum aggregate liability for damages for nonperformance and/or defective performance shall be [____] percent (__%) of the Contract Price (the “Aggregate Limit”), which limit applies to any and all liabilities of Contractor hereunder, incluiding liability for Delay Liquidated Damages Performance Liquidated Damages, warranty obligations, tort (including negligence and strict liability) and breach of contract (including any breach resulting in termination ckauns based equity).

Contractor’s maximum liability for Delay Liquidated Damages shall be [____] percent (__%) of the Contract Price (the “Delay Limit”).  Contractor’s maximum liability for Heat Rate Liquidated Damages shall be [___] percent (__%) of the Contract Price (the “Heat Rate Limit”) and Contractor’s maximum liability for Output Liquidated Damages shall be [____] percent (__%) of the Contract Price (the “Output Limit”), respectively.  Notwithstanding the Delay Limit, Heat Rate Limit and Output Limit, Contractor’s maximum aggregate liability for Delay Liquidated Damages, Heat Rate Liquidated Damages and Output Liquidated Damages shall be [____] percent (__%) of the Contract Price (the “Liquidated Limit”).

The foregoing limitations of liability shall not apply to Contractor’s liability (a) for failure to achieve Mechanical Completion and (b) for breach of its obligations under Sections 22.4 (FCPA), 3.10 (Compliance with Laws), 3.16 (No Liens), 3.17.2 (Hazardous Materials; New) and Article 18 (Indemnities).  [Contractor expressly acknowledges and agrees that any of its liability provided for by the proceeds of the insurance maintained pursuant to Article 9 shall not reduce or be applied against any of the Aggregate Limit, the Mechanical Limit, the Delay Limit or the Liquidated Limit.]

## Consequential Damages.

Subject to Section 18.6, in no event shall Contractor or Owner be liable to the other, either individually or jointly and irrespective of whether alleged to be by way of indemnity, as a result of breach of contract, breach of warranty, tort, (including negligence), strict liability, or any other legal theory, and whether arising before or after completion of the Facility, for, and each of Contractor and Owner hereby waives any right to, damages that constitute consequential, incidental, special, indirect, or consequential damages of any nature whatsoever, including, but not limited to, losses or damages caused by reason of unavailability of the Facility, shutdowns or service interruptions, loss of use, non-operation of the Facility or any Equipment or Contractor’s Equipment, loss of power or cost of replacement power, loss of opportunity profits or revenue, loss of contracts, cost of capital, inventory or use charges, cost of purchased or replacement power, loss of fuel, interest charges or claims of Owner’s customers, except to the extent such damages are included in Delay Liquidated Damages.

## Releases Valid in All Events.

Releases, disclaimers and limitations on liability expressed herein shall apply even in the event of the negligence, strict liability, fault or breach of contract (including other legal bases of responsibility such as fundamental breach) of the party whose liability is released, disclaimed or limited.

## Liquidated Damages Not Penalty.

Owner and Contractor acknowledge and agree that because of the unique nature of the Facility and the unavailability of a substitute facility, it is difficult or impossible to determine with precision the amount of damages that would or might be incurred by Owner as a result of Contractor’s failure to achieve the Performance Guarantees or the Guaranteed Completion Date.  It is understood and agreed by the parties that (i) Owner shall be damaged by failure of Contractor to meet such obligations, (ii) it would be impracticable or extremely difficult to fix the actual damages resulting therefrom, (iii) any sums which would be payable under this Agreement are in the nature of liquidated damages, and not a penalty, and are fair and reasonable, (iv) such payment represents a reasonable estimate of fair compensation for the losses that may reasonably be anticipated from such failure, and shall, without duplication, be the sole and exclusive measure of damages with respect to any such failure by Contractor, and (v) the Performance Liquidated Damages and the Delay Liquidated Damages have been calculated by reference to the losses which it may reasonably be anticipated will be suffered by Owner in the event that the Facility fails to achieve the Performance Guarantees or Substantial Completion of the Facility is not achieved by the Guaranteed Completion Date.

# REPRESENTATIONS OF CONTRACTOR AND OWNER

## Contractor Representations.

Contractor represents and warrants that:

### Corporate Standing.  It is a corporation duly organized, validly existing and in good standing under the laws of its jurisdiction of incorporation, qualified to do business in all jurisdictions in which the nature of the business conducted by it makes such qualification necessary and where failure so to qualify would have a material adverse effect on its financial condition, operations, prospects or business.

### No Violation of law; Litigation.  It is not in violation of any applicable Law, which violations, individually or in the aggregate, would affect its performance of any obligation under this Agreement.  There are no legal or arbitration proceedings or any proceeding by or before any court or Governmental Authority now pending or (to its best knowledge) threatened against it which, if adversely determined, could reasonably be expected to have a material adverse effect on its financial condition, operations, prospects or business as whole, or ability to perform all its obligations under this Agreement.

### Governmental Authorizations.  It is (or will be prior to performing any Work on the Site) the holder of all Governmental Authorizations required to permit it to operate or conduct its business now and as contemplated by this Agreement.

### No Breach.  None of the execution and delivery of this Agreement, the consummation of the transactions herein contemplated or compliance with the terms and provisions hereof and thereof will conflict with or result in a breach of, or require any consent under, its charter or bylaws or any applicable Law, or any agreement or instrument to which it is a party or by which it is bound or to which it or any of its respective assets are subject, or constitute a default under any such agreement or instrument.

### Corporate Action.  It has all necessary power and authority to execute and deliver and it has all necessary power and authority to perform its respective obligations under this Agreement; and its execution, delivery and performance of this Agreement has been duly authorized by all necessary action on its part; and this Agreement has been duly and validly executed and delivered by it and constitutes its legal, valid and binding obligation, enforceable in accordance with its terms, except as the enforceability thereof may be limited by bankruptcy, insolvency, reorganization or moratorium or other similar laws relating to the enforcement of creditors’ rights generally and by general equitable principles.

### Investigation.  Except as set forth on Exhibit B-1, it has:  (a) the requisite experience and proper qualifications to perform the Work and (b) ascertained the nature and location of the Work, the general character and accessibility of the Site, the nature of the Site geotechnical and soil conditions, including underground obstructions, the existence of obstacles to construction, the location and character of existing or adjacent work or structures, and other general and local conditions and Laws (including labor Laws) applicable to its performance of the Work or the cost thereof and has performed such testing or examined the results of such testing as would normally be conducted by a contractor considering entering into an agreement such as this Agreement and taking into account the available time for such examination.

## Owner Representations.

Owner represents and warrants that:

### Business Organization.  It is a limited liability company duly organized and validly existing under the laws of [Host Country], is qualified to do business in all jurisdictions in which the nature of the business conducted by it makes such qualification necessary and where failure so to qualify would have a material adverse effect on its financial condition, operations, prospects or business.

### No Violation of Law; Litigation.  It is not in violation of any applicable Law, which violations, individually or in the aggregate, would affect its performance of any obligation under this Agreement.  There are no legal or arbitration proceedings or any proceeding by or before any court or Governmental Authority now pending or (to the best knowledge of Owner) threatened against Owner which, if adversely determined, could reasonably be expected to have a material adverse effect on the financial condition, operations, prospects or business, as a whole, of Owner, or its ability to perform all its obligations under this Agreement.

### Governmental Authorizations.  It is the holder of all Governmental Authorizations required to permit it to enter into and perform its obligations under this Agreement.

### No Breach.  None of the execution and delivery of this Agreement, the consummation of the transactions herein contemplated or compliance with the terms and provisions hereof and thereof will conflict with or result in a breach of, or require any consent under, the charter or bylaws of Owner, or any applicable Law, or any agreement or instrument to which Owner is a party or by which it is bound or to which it or its assets are subject, or constitute a default under any such agreement or instrument.

### Corporate Action.  It has all necessary power and authority to execute, deliver and perform its obligations under this Agreement; and the execution, delivery and performance by Owner of this Agreement has been duly authorized by all necessary action on its part; and this Agreement has been duly and validly executed and delivered by Owner and constitutes the legal, valid and binding obligation of Owner enforceable in accordance with its terms, except as the enforceability thereof may be limited by bankruptcy, insolvency, reorganization or moratorium or other similar Laws relating to the enforcement of creditors’ rights generally and by general equitable principles.

# DEFAULT, TERMINATION AND SUSPENSION

## Default by Contractor.

### Termination for Inability to Perform.  If any proceeding is instituted against Contractor seeking to adjudicate Contractor as a bankrupt or insolvent and such proceeding is not dismissed within sixty (60) days of filing, or if Contractor makes a general assignment for the benefit of its creditors, or if a receiver is appointed on account of the insolvency of Contractor, or if Contractor files a petition seeking to take advantage of any other applicable law relating to bankruptcy, insolvency, reorganization, winding up or composition or readjustment of debts, or if Contractor is unable to pay its debts when due or as they mature, then Owner may terminate this Agreement effective immediately upon giving written notice of such termination to Contractor.  Any such termination shall be without prejudice to any existing rights, powers or remedies of either party under this Agreement.

### Termination for Contractor’s Failure to Perform.  If Contractor:

##### has abandoned this Agreement;

##### despite previous warnings in writing from Owner, has wrongfully refused or has materially failed or neglected at any time to execute the Works in accordance with this Agreement, or is failing to proceed with the Works with due diligence or is neglecting to carry out its other obligations under this Agreement in each case so as to affect materially and adversely the carrying out of the Works; or

##### has failed to achieve Final Completion within 240 days of the Guaranteed Completion Date,

then, subject to the provisions of Section 16.1.3, Owner may by notice to Contractor and without prejudice to any other remedy under this Agreement terminate this Agreement and enter the Site and expel Contractor therefrom but without thereby releasing Contractor from any of its obligations or liabilities which have accrued under this Agreement and without affecting the rights and powers conferred by this Agreement on Owner.  Upon such termination, the Owner may itself complete the Works or may employ any other contractor so to do.

### Opportunity to Remedy.  The Owner’s right to terminate this Agreement following the occurrence of the events or circumstances described in Sections 16.1.2.2 and 16.1.2.3 shall be subject to Owner having first given Contractor 21 days’ prior notice of its intention to terminate this Agreement, during which period Contractor shall have failed:

##### in the case of Section 16.1.2.2, to remedy or to take all reasonable steps to commence the remedy of the default; or

##### in the case of Section 16.1.2.3, to achieve Final Completion.

### General Obligations.  If Owner elects to terminate this Agreement pursuant to this Section 16.1, then Contractor shall, at Owner’s request and at Contractor’s expense, perform the following services relative to the Work so affected:

##### cease all further Work, except such Work as Owner may specify in the termination notice for the sole purpose of protecting that part of the Work already executed;

##### assist Owner in preparing an inventory of all Equipment in use or in storage at the Site;

##### terminate all Subcontracts, except those to be assigned to Owner pursuant to Section 16.1.4.(d);

##### assign to Owner, or to any Replacement Contractor designated by Owner or Lender, title to all Work not already owned by Owner, together with all Subcontracts and other contractual agreements (including warranties) as may be designated by Owner, and assign to Owner to the extent assignable all issued Governmental Authorizations, patents and other proprietary rights, if any, then held by Contractor pertaining to the Facility;

#### remove from the Site Contractor’s Equipment and rubbish as Owner may request;

#### deliver to Owner all design and other information as maybe reasonably requested by Owner for the completion and operation of the Facility; and

### Payment Obligations.  If Owner terminates this Agreement pursuant to this Section 16.1, as soon as reasonably practicable after reaching the equivalent of Final Completion, Owner shall determine the total reasonable and necessary expenses incurred and accrued by Owner in connection with the termination of this Agreement (including all legal fees and expenses) and the completion of the Work, including all amounts charged by any Replacement Contractor to finish the Work based on the obligations such Replacement Contractor assumes under this Agreement (including the assumption by such Replacement Contractor of Contractor’s obligations hereunder to pay Delay Liquidated Damages) and under any of Contractor’s Subcontracts or other contractual agreement(s) that Owner elects to have assigned to such Replacement Contractor pursuant to Section 16.1.4.4., and additional reasonable and necessary overhead incurred and accrued by Owner to effect such takeover and to complete the Work.  Contractor shall be entitled to be paid any unpaid portion of the Contract Price attributable to the Work executed by Contractor prior to the date of termination, the value of any unused or partially used materials on the Site furnished by Contractor which are taken over by Owner and have not already been paid for as part of the Contract Price paid to Contractor, and the costs, if any, incurred by Contractor in protecting the Work pursuant to Section 16.1.4.1.  Any sums due to Owner from Contractor accruing prior to the date of termination shall be deducted from the amount to be paid to Contractor pursuant to the foregoing.  If the total expenses incurred by Owner in completing the Facility as set forth above exceed the balance of the Contract Price unpaid at the time of Contractor’s default, then Contractor shall be liable for and shall pay to Owner upon written demand by Owner the amount of such excess.  Any such amount payable by Contractor may be deducted by Owner from any portion of the Contract Price or other amounts due to Contractor under this Section 16.1.5.

## Optional Cancellation by Owner.

### Rights.  Owner may terminate this Agreement at any time by written notice to Contractor.  Upon receipt of any such notice, Contractor shall, unless the notice directs otherwise:

##### immediately discontinue the Work on the date and to the extent specified in such notice;

##### place no further orders or enter into Subcontracts for Equipment;

##### promptly make every reasonable effort to procure cancellation of all orders, Subcontracts and rental agreements upon commercially reasonable terms given all the facts and circumstances, including the amount of notice and ________, if any, _____________ __________ for such termination, Owner shall indemnify Contractor from and against any and all such cancellation costs;

##### deliver to Owner all information prepared hereunder with respect to the Facility as may be reasonably requested by Owner and which has been paid for by Owner, including all drawings, plans, specifications, studies, reports and other information prepared hereunder as of the date of termination; and

##### thereafter execute only that portion of the Work directed by Owner as may be reasonably necessary to preserve and protect Work already in progress and to protect Equipment at the Site or in transit thereto.

### Deemed Cancellation.  If Owner fails to issue the Notice to Proceed on or before the date specified in Exhibit C-6, then Owner shall be deemed to have cancelled this Agreement.  In the event of a deemed cancellation under this Section 16.2.2, Contractor shall act in accordance with  and Sections 16.2.1.1 through 16.2.1.5 and the remedy set out in 16.2.3.1 shall apply.

### Remedies.  Contractor waives any claims for consequential damages, including loss of anticipated profits for uncompleted Work, on account of a termination by Owner pursuant to this Section 16.2.3 and shall accept as its sole remedy the following:

#### In the event that Owner cancels this Agreement in accordance with Section 16.2 after issuing the Preliminary Notice to Proceed but prior to the Notice to Proceed Effective Date, Owner shall only be liable for cancellation fees as set forth in Exhibit C-6.

#### If such cancellation occurs after the Notice to Proceed Effective Date, Contractor shall be entitled to payment of the Contract Price attributable to the Work (including any work in progress, components and other supplies specifically purchased, prepared or fabricated off the Site for the Facility and not returned to vendor’s stock, or Equipment for subsequent incorporation at the Site) properly performed by Contractor and its Subcontractors as of the effective date of cancellation; the costs reasonably incurred by Contractor in removing Contractor’s Equipment from the Site and in the repatriation of Contractor’s and any Subcontractor’s personnel; the costs incurred by Contractor in protecting the Work pursuant to Section 16.2.1.5 and reimbursement for any Subcontractor termination costs; and any other out-of-pocket expenses reasonably incurred by Contractor as a result of such cancellation which, in the circumstances, cannot reasonably be avoided by Contractor and are a direct result of such termination.  Contractor shall use reasonable efforts to minimize any such costs of cancellation.  Owner shall have the option of having all or any Work delivered to the Site or, at Owner’s expense, to such other place as Owner shall reasonably direct.  Payments for cancellation under Section 16.2 shall be due Contractor within fifteen (15) days of Owner’s receipt and acceptance of a substantiated, itemized invoice and the delivery of any such Work.  [Cf. Dahol §44.3]

## Termination by Contractor.

### Termination for Owner’s Inability to Perform.  If any proceeding is instituted against Owner seeking to adjudicate Owner as a bankrupt or insolvent and such proceeding is not dismissed within sixty (60) days of filing, or if Owner makes a general assignment for the benefit of its creditors, or if a receiver is appointed on account of the insolvency of Owner, or if Owner files a petition seeking to take advantage of any other applicable law relating to bankruptcy, insolvency, reorganization, winding up or composition or readjustment of debts, or if Owner admits in writing its inability to pay its debts when due, Contractor may terminate this Agreement effective immediately upon giving written notice of such termination to Owner.

### Termination for Owner’s Failure to Perform.  If:

#### Owner fails to pay Contractor any undisputed amount due under any invoice within thirty (30) days after the amount became payable;

#### Owner fails to observe or perform any of its material covenants or agreements contained in this Agreement;

#### the Work is suspended for more than twelve (12) consecutive months pursuant to Section 16.4;

#### any material representation or warranty of Owner shall have been incorrect as of the date made and shall remain incorrect at the time in question; or

#### any material breach for which Contractor cannot be compensated by menas of a Change Order under Article 6

then, in any such case, if Owner fails to correct such condition with thirty (30) days of receipt of written notice from Contractor stating the nature of the condition and requiring Owner to remedy the same or, if such default is not capable of being remedied within such thirty (30) days, to diligently commence to correct such condition within fifteen (15) days of receipt of such written notice and to complete the correction within forty-five (45) days after receipt of such notice, Contractor may, after giving Owner five (5) Business Days’ notice thereof, terminate this Agreement.  Any such termination shall be without prejudice to any existing rights, powers or remedies of either party under this Agreement.

### Removal of Contractor’s Equipment.  If this Agreement is terminated under Section 16.3.1 or 16.3.2, Contractor shall be entitled to remove immediately Contractor’s Equipment and the temporary work that is on the Site.

### Payment on Termination by Contractor.  If this Agreement is terminated under Section 16.3.1 or 16.3.2, Contractor shall be entitled to payment on the same basis as if the carrying out of the Work had been cancelled under Section 16.2.

## Suspension of Work.

### Suspension of Work by Owner.

#### Owner may, at any time and from time to time and for any reason, by written notice to Contractor, suspend the carrying out of the Work or any part thereof.  Contractor shall, on such written notice of Owner, suspend the carrying out of the Work or any part thereof for such time and in such manner as Owner may require and shall during any such suspension properly protect and secure the Work in such manner as Owner shall reasonably require.  Unless otherwise instructed by Owner, Contractor shall during any such suspension maintain its staff and labor on or near the Site ready to proceed with the Work upon receipt of Owner’s further instructions.

#### Owner may at any time following a suspension give notice to Contractor to proceed with the Work previously suspended.

#### Upon receipt of any such notice to proceed, Contractor shall examine the Equipment delivered to Contractor affected by the suspension and shall, at Owner’s expense, make good any deterioration of or damage to such Equipment that may have occurred during the suspension (unless resulting from any breach by Contractor of its obligations to protect and secure the Work) and shall proceed with the Work previously suspended.

### Suspension of Work by Contractor.

#### Contractor may, by giving fifteen (15) days notice in writing to Owner, suspend the carrying out of the Work or any part thereof if Owner fails to pay Contractor any undisputed amount due under any invoice within thirty (30) days after the amount becomes payable under this Agreement, unless prior to the end of the fifteen (15) days notice period Owner has paid the overdue amount.  During any such suspension Contractor shall properly protect and secure the Work in such manner as Owner shall require.  Unless otherwise instructed by Owner, Contractor shall during any such suspension maintain its staff and labor on or near the Site ready to proceed with the Work immediately upon receipt of the overdue amount.

#### Upon payment by Owner of such overdue amount, Contractor shall examine the Equipment delivered to Contractor affected by the suspension and shall, at Owner’s expense, make good any deterioration or damage to or of such Equipment that may have occurred during the suspension (unless resulting from any breach by Contractor of its obligations to protect and secure the Work) and shall proceed with the Work previously suspended.

### Adjustment and Compensation for Suspension.  In the event of a suspension of the Work pursuant to this Section 16.4, Contractor shall be entitled to a Change Order for reimbursement, on a monthly basis, in accordance with the invoicing and payment provisions set forth in Section 7.2, for all actual direct out-of-pocket costs plus Contractor’s personnel costs (verified to Owner’s reasonable satisfaction) which are reasonably incurred by Contractor as a result of such suspension and any increase in cost or delays resulting from such suspension.  In the event of a suspension pursuant to Section 16.4.2. 1 (ii) only, Contractor shall be entitled to a Change Order which, in addition to providing for reimbursement for costs incurred, also provides for a reasonable extension to the Project Schedule in respect of any delay suffered by reason of the suspension.

# FORCE MAJEURE

## Force Majeure

“Force Majeure” shall mean any of the following events or circumstances, or any combination of such events or circumstances, which are beyond the reasonable control of the affected party, which could not have been prevented by the exercise of reasonable skill and care, and which, or any consequences of which, have a material and adverse effect upon the performance by the affected party of its obligations under this Agreement:

- Strikes: Strikes, lock-outs or other industrial action or labor disputes, including those involving either party or their respective Subcontractors, servants or agents, in any such case employed on the execution of the Works within [Host Country] and those occurring in [Host Country] that are not primarily motivated by the desire to influence the actions of an enterprise so as to preserve or improve conditions of employment.

- Political Force Majeure:  Any of the following that occur inside or involve [Host Country]:

(i)	act of war (whether declared or undeclared), invasion, armed conflict or act of foreign enemy, blockade, embargo, revolution, riot, bombs, religious strife or civil commotion;

(ii)	sabotage, terrorism or the threat of such acts, general or organized objections, protests or unrest relating to the Works;

(iii)	except to the extent that they constitute remedies or sanctions lawfully exercised by a Governmental Authority of [Host Country] as a result of a breach by the affected party, its Subcontractors, servants or agents of the Laws of [Host Country], any act of state or other exercise of a sovereign or executive prerogative by Government of [Host Country] or any Governmental Authority thereof, including expropriation, nationalization or compulsory acquisition and acts claimed to be justified by executive necessity [but excluding any Change of Law];

(iv)	explosions, chemical or radioactive contamination or ionizing radiation (excluding circumstances where the source or cause of the explosion or contamination or radiation is brought or has been brought onto or near the Site by the affected party or those employed or engaged by the affected party unless it is or was essential for the construction or operation of any part of the Facility); and

(v)	any event or circumstances of a nature analogous to the foregoing.

- Other Force Majeure:  Any of the following that are not included in subparagraph (b) above:  [this subparagraph should be (c)]

(i)	lightning, earthquake, tempest, flooding, fire, cyclone, hurricane, typhoon, tidal waves, whirlwind, storm, drought or lack of water and other unusual or extremely adverse weather or environmental conditions or action of the elements, meteorites, aircraft or objects falling from aircraft or other aerial devices, the occurrence of pressure waves caused by aircraft or other aerial devices travelling at supersonic speeds;

(ii)	act of war (whether declared or undeclared), invasion, armed conflict or act of foreign enemy, blockade, embargo, revolution, riot, bombs, religious strife, insurrection or civil commotion;

(iii)	sabotage, terrorism or the threat of such acts;

(iv)	loss of or damage to Materials while in transit to the Site;

(v)	epidemic or plague;

(vi)	Act of God;

(vii)	the imposition after the Effective Date of export controls affecting the export of goods, materials, equipment or technical data for incorporation in the Facility and for which the country of origin, if not the United States, a member state of the European Union or Japan, is specified in the Scope Book and Execution Plan; and

(viii)	any event or circumstances of a nature analogous to the foregoing.

## Excused Performance.

Except for the obligation to timely pay money for Work actually performed or for other monetary liabilities incurred hereunder, either party shall be excused from the performance or delay in performance of its obligations hereunder (and shall not be considered to be in default with respect thereto) if and to the extent that its failure to perform or delay in the performance of each such obligation  is due to Force Majeure or the consequences thereof, provided, that:

##### the affected party gives the other party written notice describing in reasonable detail, to the extent then available, the Force Majeure as soon as is reasonably practicable, but in no event later than fifteen (15) days after such party first becomes aware of the occurrence or commencement of such Force Majeure; and

##### the suspension of performance is of no greater scope and of no longer duration than is reasonably required by the Force Majeure or consequences thereof, including a reasonable recovery period within which to restart performance.

## Performance Continuation.

Upon the occurrence of any circumstances of Force Majeure, Contractor shall use reasonable efforts to continue to perform its obligations under this Agreement and to minimize the adverse effects of such circumstances.  Contractor shall notify Owner of the steps it proposes to take, including any reasonable alternative means for performance.

## Financial Consequences of Force Majeure.

### If  Contractor reasonably incurs additional costs in complying with its obligation under Section 17.3 in respect of the occurrence of events of Force Majeure, Contractor shall be entitled to a Change Order under Article 6 adding the amount of such additional costs to the Contract Price, which amount shall be paid to the Contractor by Owner within ten days after the date of such Change Order.  The parties shall use all reasonable efforts, wherever practicable, to negotiate and agree on a fixed lump sum adjustment to the Contract Price and an appropriate Change Order in respect of the additional costs incurred or to be incurred by Contractor in complying with Section 17.3.

### If the occurrence of any events of Force Majeure has caused Contractor to suspend the performance of any part of the Work, then such suspension shall be treated as if it were a suspension instructed by Owner under Section 16.4.1.1 and Contractor shall be entitled to a Change Order pursuant to Section 16.4.3.

## Owner Self-Help.

If, within a reasonable time after an event of Force Majeure has caused Contractor to suspend or delay performance of the Work, reasonable action that Contractor could lawfully and reasonably initiate to remove or relieve either the Force Majeure or its direct or indirect effects has been identified and recommended to Contractor by Owner, and Contractor has failed to take such action, then Owner may, in its sole discretion and after seven (7) days’ written notice to Contractor, at Contractor’s expense, initiate such reasonable measures as will remove or relieve such Force Majeure or its direct or indirect effects and thereafter require Contractor to resume full or partial performance of the Work in accordance with the provisions of this Agreement.

## Resumption of Performance.

When a party whose performance has been suspended due to Force Majeure becomes able to resume performance of its obligations under this Agreement, such party shall give the other party written notice to that effect and shall promptly resume performance hereunder.

## Burden of Proof.

In the event that the parties are unable in good faith to agree that an event of Force Majeure has occurred, the parties shall submit the dispute for resolution pursuant to Article 19 and the party claiming a Force Majeure shall have the burden of proof as to whether such Force Majeure (a) has occurred, (b) was not a result of such party’s or its Subcontractor’s fault or negligence and (c) could not have been avoided by due diligence or the use of reasonable efforts by such party or its Subcontractors.

## Termination for Force Majeure.

Notwithstanding that Contractor may have become entitle to an extension of time in which to perform its obligations hereunder due to Force Majeure, if by virtue of Section 17.2 either party shall have been  excused from the performance of any material obligation under this Agreement for a continuous period of twelve (12) months, then either party may at any time thereafter, and provided such performance or punctual performance is still excused, by notice to the other terminate this Agreement.

## Payment on Termination.

If the Contract is terminated under Section 17.8, Owner shall pay to Contractor, to the extent the same has not already been paid by Owner, such part of the Contract Price, adjusted to give effect to any  additions or deductions previously provided by the terms of this Agreement, as is properly apportionable to the Work executed before the date of termination, taking into account the state, condition and topographical location of the Materials, the amount of work done and all other relevant circumstances.

Contractor also shall be entitled to be paid:

(a)	the cost of materials or goods reasonably ordered for the Work, or for use in connection with the Work, that have been delivered to the Contractor or of which the Contractor is legally liable to accept delivery.  Such materials or goods shall become the property of the Owner when paid for by the Owner.  Owner shall be entitled to withhold payment in respect thereof until such goods or materials have been delivered to or to the order of the Owner;

(b)	the amount of any other expenditures that in the circumstances were reasonably incurred by Contractor in the expectation of completing the whole of the Work;

(c)	the reasonable cost of removal of Contractor's Equipment and of the return thereof to the Contractor's works in its country or to any other destination at no greater cost than would have been incurred to return the Contractor's Equipment to such works ; and

(d)	the reasonable cost of repatriation of all staff and workers employed at the Site by Contractor on or in connection with the Work at the date of such termination.

# INDEMNITIES

## Contractor Indemnity.

Contractor, on behalf of itself, its Affiliates, successors, assigns, officers, directors, employees, Subcontractors and agents (each an “Contractor Indemnitor”), agrees to indemnify, defend and hold harmless Owner Indemnitees from and against any and all claims, demands, losses, damages, causes of action, suits, and liabilities (including all expenses of litigation, court costs and reasonable attorneys’ fees) (a) attributable to bodily injury (including death) or property damage of third parties to the extent caused by the negligence or willful misconduct of any Contractor Indemnitor, or (b) attributable to any bodily injury (including death) or property damage (including property of Contractor or Owner) caused by any spill or release of Hazardous Substances by any Contractor Indemnitor or a breach of Section 3.17.2 by Contractor, its Subcontractors or any of their respective agents..

## Owner Indemnity.

Owner, on behalf of itself, its Affiliates, successors, assigns, officers, directors, employees, and agents (each an “Owner Indemnitor”), agrees to indemnify, defend and hold harmless Contractor Indemnitees from and against any and all claims, demands, losses, damages, causes of action, suits, and liabilities (including all expenses of litigation, court costs and reasonable attorneys’ fees) (a) attributable to bodily injury (including death) or property damage of third parties to the extent caused by the negligence or willful misconduct of an Owner Indemnitor, or (b) attributable to bodily injury (including death) or property damage (including property of Contractor or Owner) caused by any Hazardous Substances existing at the Site on the Effective Date, except to the extent of any such injury or damage resulting from any action or inaction of any Contractor Indemnitor in connection with the performance of its obligations under Section 3.17.

## Patent Indemnity.

Contractor expressly warrants and represents that it shall indemnify, defend and save Owner, Lender and each of their respective Affiliates, successors, assigns, officers, directors, employees and agents harmless from and against any and all claims whatsoever arising from or in any manner related to an infringement of patents or the improper use of other proprietary rights which may occur in connection with Contractor’s or any Subcontractor’s performance of the Work pursuant to this Agreement and the ownership or use of the Facility or any part thereof provided by Contractor or any Subcontractor (including, without limitation, the use of any such part in conjunction with, or as modified, supplemented or otherwise affected by, any Equipment); provided that Contractor shall have no indemnity obligations hereunder with respect to any claim arising out of (i) use of Equipment in combination with devices or products not supplied by Contractor or any of their respective Subcontractors or  (ii) use of Equipment in an application or environment for which they were not designed.  Should any such claim materially impair Contractor’s performance of the Work or continued operations of the Facility, then Contractor shall, at its own expense, timely procure the right to continue its performance of the Work so as not to materially impair the Project Schedule or such continued operations of the Facility.  This Article 18 states the entire liability of Contractor for patent infringement in connection with the performance of the Work and ownership and use of the Facility or any part thereof provided by Contractor or any Subcontractor.

## Notice.

Each party shall promptly notify the other in writing of any claims from any third party, which may be covered by the indemnities set forth in this Article 18.  Without limiting the generality of the foregoing, Owner shall notify Contractor in writing as soon as Owner shall receive notice of any claims of infringement of patents or other proprietary rights occurring in connection with Contractor’s performance of the Work.  In turn, Contractor shall timely notify Owner in writing of any claims which Contractor may receive alleging infringement of patents or other proprietary rights which may affect Contractor’s performance of the Work.

## Defense of Claims.

The indemnifying party, under Section 18.1, 18.2, or 18.3 (the “Indemnitor”) shall have sole charge and direction of the defense of any suit or proceeding based on any claim, demand, loss, damage, cause of action, suit on liability for which Indemnitor is responsible under any such Section.  The indemnified party (the “Indemnitee”) shall give the Indemnitor such assistance as the Indemnitor may reasonably require in such defense, and shall have the right to be represented in such defense by counsel of its own choice at its own expense.  [If the Indemnitor fails to defend diligently such suit or proceeding, the Indemnitee may, in its reasonable discretion, either defend such suit or proceeding or settle the claim which is the basis thereof, without the consent of the Indemnitor, without relieving the Indemnitor of its obligation under Section 18.1, 18.2, or 18.3, and in either case the Indemnitor shall reimburse the Indemnitee for its expenses, court costs and reasonable attorneys’ fees.]  If any claim described in Section 18.3 is held to constitute an infringement of any patent or other proprietary rights and use of any Equipment or process included in the Work is enjoined, Contractor shall at its own expense and at Contractor’s option (i) procure for Owner the right to continue to use the infringing Equipment or process, (ii) replace such Equipment or process with non-infringing equipment or process of equivalent utility and efficiency, or (iii) modify such Equipment or process so that it becomes non-infringing without affecting its utility or efficiency.

# DISPUTE RESOLUTION [to be revised]

## Arbitration Resolution.

[Except as provided for in Section 20.4], any claim, dispute or controversy arising out of or relating to this Agreement or the breach or termination thereof, other than a dispute to which the Fast-Track Arbitration provisions of Section 19.2 apply, shall be submitted to binding arbitration in the Borough of Manhattan, New York, in accordance with the Rules of Conciliation and Arbitration of the International Chamber of Commerce (“ICC”) then in effect.  There shall be three independent arbitrators, with each party selecting one; the third arbitrator, who shall be the chairman of the panel, shall be selected by the two arbitrators appointed by the parties.  The claimant shall name its arbitrator in the demand for arbitration and the responding party shall name its arbitrator within thirty (30) days after receipt of the demand for arbitration.  The third arbitrator shall be named within thirty (30) days after the appointment of the second arbitrator.  The ICC shall be empowered to appoint any arbitrator not named in accordance with the procedure set forth herein.  Each arbitrator will be qualified by at least ten (10) years’ experience in construction, engineering, or the electric utility industry.  The decision of the arbitrators shall be based upon principles of law and shall be final and binding upon the parties without the right of appeal to the courts.  The award rendered by the arbitration shall be final and judgment thereon may be entered by any court having jurisdiction thereof.  The costs and expenses of the arbitration (including reasonable attorney’s fees) will be borne by the losing party, unless the arbitrators determine that it would be manifestly unfair to honor this agreement of the parties and determine a different allocation of costs.

## Fast-Track Arbitration.

Within thirty (30) days after the Notice to Proceed is issued, the parties shall agree upon an independent third party (the “Fast-Track Arbitrator”) and an alternate third party (the “Alternate”) to decide disputes to be referred to the Fast-Track Arbitrator as provided in within this Agreement.  The Fast-Track Arbitrator and the Alternate each must have at least ten (10) years’ experience in the construction and engineering of power generation facilities.  Either party may refer disputes as described in this Agreement as may be so referred or as mutually agreed by both parties to the Fast-Track Arbitrator by providing written notice to the Fast-Track Arbitrator and the other party.  If a party has given written notice of its intent to refer such a dispute, the other party shall be bound to fast-track arbitration as provided in this Section 19.2 and may not resort to the procedures of Section 19.1.  In the event that the Fast-Track Arbitrator is unavailable to resolve the dispute within the time period stated in this section, the dispute shall be referred to the Alternate. The Fast-Track Arbitrator or the Alternate, as the case may be (the “Arbitrator”), shall be directed to resolve the dispute within fifteen (15) days of referral.  The parties shall cooperate in good faith in providing to the Arbitrator any information reasonably needed to resolve the dispute.  The decision of the Arbitrator shall be final, binding and non-appealable.  The costs and expenses of the arbitration will be borne by the losing party, unless the Arbitrator finds that it would be manifestly unfair to honor this agreement of the parties and determines a different allocation of costs.

## Applicable Law and Arbitration Act.

Any arbitral award hereunder shall be enforceable in either the United States District Court for the Southern District of New York or, if such court refuses jurisdiction, any court of the State of New York sitting in the Borough of Manhattan, and Contractor each consent to the nonexclusive jurisdiction of, and to the laying of venue in, such court for such purpose.  All procedural aspects of this agreement to arbitrate, including, but not limited to, the construction and interpretation of this agreement to arbitrate, the scope of the arbitrable issues, allegations of waiver, delay or defenses as to arbitrability, and the rules governing the conduct of the arbitration, shall be governed by and construed pursuant to the United States Arbitration Act, 9 U. S.C. § § 1-16.  In deciding the substance of any such claim, dispute or disagreement, the arbitrators shall apply the substantive laws of the State of New York; provided, however, that the arbitrators shall have no authority to award punitive damages under any circumstances (whether it be exemplary damages, treble damages, or any other penalty or punitive type of damages) regardless of whether such damages may be available under New York law, the parties hereby waiving their right, if any, to recover punitive damages in connection with any such claims, disputes or disagreements.

## Continuation of Services.

Pending final resolution of any dispute, whether or not submitted to arbitration hereunder, Contractor shall continue to fulfill its respective obligations hereunder unless the dispute involves a Change Order under Section 6.6 (i.e., change in schedule, cost or performance).

# CONFIDENTIAL INFORMATION

## Confidential Information.

Subject to Article 16, for a period of two years following Substantial Completion, neither Contractor, Owner nor any licensee of Owner pursuant to Section 8.1.3 shall disclose the Confidential Information other than to its Representatives.  “Representatives,” as used in this Agreement, shall include directors, officers, employees, auditors, counsel, Lenders, [any party to a Project Agreement] and Affiliates and such Affiliate’s directors, officers, employees, auditors, and counsel. It is understood (i) that any Representative receiving Confidential Information shall be informed of the obligation of nondisclosure pursuant to this Agreement and (ii) Owner and Contractor shall each be responsible for any breach of this Agreement by its Representatives.

## Notice Preceding Compelled Disclosure.

If Contractor or Owner or any Representative of either is requested or required (by oral question, interrogatory, request for information or documents, subpoena, civil investigative demand or other law or legal process) to disclose any Confidential Information, such party will promptly notify the other party of such request or requirement so that the other party may seek an injunction, appropriate protective order or grant a waiver of compliance with the provisions of this Agreement.  If, in the absence of an injunction, protective order or the receipt of a waiver hereunder, such party is, in the opinion of counsel, compelled by such law or legal process to disclose the Confidential Information, then such party may disclose only such of the Confidential Information as is required and, provided that it exercises reasonable efforts to obtain an order or other reliable assurance that confidential treatment will be accorded to the disclosed Confidential Information, there shall be no liability for the disclosure of Confidential Information pursuant to this sentence.

## Definition of “Confidential Information”.

The term “Confidential Information” shall mean all written information marked confidential furnished by one party to the other subsequent to the date of this Agreement relating to the Facility. Confidential Information shall also include all written information generated by a party or its Representatives that contains, reflects or is derived from furnished Confidential Information.  The term “written information” shall include information recorded or stored in a digital format on electronic, magnetic or optical media.  The following will not constitute Confidential Information for purposes of this Agreement: (a) information which is or becomes publicly available other than as a result of a disclosure in violation of this Agreement, (b) information which was already known to the recipient prior to being furnished pursuant to this Agreement, and (c) information which becomes available on a non-confidential basis from a source other than the disclosing party if such source was not subject to any prohibition against transmitting the information to the recipient.

## Remedies.

Money damages would not be a sufficient remedy for any breach of the above provisions of this Article 20 and the disclosing party shall be entitled to seek specific performance and injunctive relief as remedies for any such breach.  Such remedies shall not be deemed to be the exclusive remedies for any such breach, but shall be in addition to all other remedies available at law or in equity.

# SECURITY

## Retention Bond.

Contractor may provide Owner one or more letters of credit or bank guarantees in a form reasonably acceptable to Owner, issued by a financial institution rated at least “A” by Standard & Poor’s Corporation and at least “A2” by Moody’s Investors Service (the “Retention Bond”) in an amount equal to the Retainage plus, at the option of Contractor, any Punchlist Withholding.  The Retention Bond (or a replacement Retention Bond provided to Owner prior to the expiration or termination of the Retention Bond) shall be in full force and effect from the date provided to Owner and shall remain in full force and effect in respect of an amount equal to the Retainage until Substantial Completion.  If, at the option of Contractor, the Retention Bond includes an amount equal to any Punchlist Withholding, the Retention Bond shall, in addition, remain in full force and effect in an amount equal to the Punchlist Withholding in relation to any Punchlist Items that remain outstanding.  The Retention Bond may be drawn upon by Owner in U.S. Dollars in the United States of America from time to time for Contractor’s failure to perform any of its material obligations under this Agreement.

# MISCELLANEOUS PROVISIONS

## Governing Law.

THIS AGREEMENT SHALL BE GOVERNED BY, CONSTRUED AND ENFORCED IN ACCORDANCE WITH, THE LAWS OF THE STATE OF NEW YORK (WITHOUT GIVING EFFECT TO THE PRINCIPLES THEREOF RELATING TO CONFLICTS OF LAWS EXCEPT SECTION 5-1401 OF THE NEW YORK GENERAL OBLIGATIONS LAW).

## Notice.

Any notice, demand, offer, or other written instrument required or permitted to be given pursuant to this Agreement shall be in writing signed by the party giving such notice and shall be hand delivered or sent by registered letter or telefax (subject to confirmation of receipt) to the address or telefax number set forth below.

To Owner:

With Copy To:

To Contractor:

Enron

333 Clay Street, Suite 400

Houston, Texas 77002

Attention: Project Manager

Telefax: (713) 646-7202

Each party to this Agreement shall have the right to change the place to which notice shall be sent or delivered by similar notice sent in like manner to the other party.  The effective date of an notice issued pursuant to this Agreement shall be as of the addressee’s receipt of such notice.

## Assignment.

Except as set forth below in this Section 22.3, this Agreement may be assigned only with the prior written consent of the other party to this Agreement.  Owner may assign this Agreement and any rights or obligations hereunder to any Lender or any trustee or agent of any Lender as collateral security (and in connection therewith, Contractor shall execute and deliver to Lender a consent agreement in a form reasonably requested by Lender).  Owner may assign this Agreement to any Affiliate of Owner; provided that Owner unconditionally guarantees the performance of such Affiliate’s obligations under this Agreement.  Any purported assignment not in compliance with this Section 22.3 shall be void and without force or effect.

## Corrupt Practices.

[text to come]

## Miscellaneous.

### Entire Agreement.  This Agreement contains the entire understanding of the parties with respect to the subject matter hereof and reflects the prior agreements and commitments with respect thereto.  There are no other oral understandings, terms or conditions and neither party has relied upon any representation, express or implied, not contained in this Agreement.

### Amendments.  No change, amendment or modification of this Agreement shall be valid or binding upon the parties hereto unless such change, amendment or modification shall be in writing and duly executed by both parties hereto.

### Joint Effort.  Preparation of this Agreement has been a joint effort of the parties and the resulting document shall not be construed more severely against one of the parties than against the other.

### Captions.  The captions contained in this Agreement are for convenience and reference only and in no way define, describe, extend or limit the scope of intent of this Agreement or the intent of any provision contained herein.

### Severability.  The invalidity of one or more phrases, sentences, clauses, sections or articles contained in this Agreement shall not affect the validity of the remaining portions of the Agreement so long as the material purposes of this Agreement can be determined and effectuated.

### No Waiver.  Any failure of any party to enforce any of the provisions of this Agreement or to require compliance with any of its terms at any time during the pendency of this Agreement shall in no way affect the validity of this Agreement, or any part hereof, and shall not be deemed a waiver of the right of such party thereafter to enforce such provisions or require compliance with such terms.

### Successors and Assigns.  This Agreement shall be binding upon and shall inure to the benefit of the parties hereto and their successors and permitted assigns.

### Exhibits.  All exhibits referenced in this Agreement shall be incorporated into this Agreement by such reference and shall be deemed to be an integral part of this Agreement.

### Obligations.  Nothing contained in this Agreement shall be construed as constituting a joint venture or partnership between Contractor and Owner.

### Further Assurances.  Contractor and Owner agree to provide such information, execute and deliver any instruments and documents and to take such other actions as may be necessary or reasonably requested by the other party which are not inconsistent with the provisions of this Agreement and which do not involve the assumptions of obligations other than those provided for in this Agreement, in order to give full effect to this Agreement and to carry out the intent of this Agreement.

### Priority.  In the event of any conflict or inconsistency between this Agreement and the Exhibits or other incorporated or associated documentation, the terms and conditions of this Agreement shall control.

### Counterparts.  This Agreement may be signed in any number of counterparts and each counterpart shall represent a fully executed original as if signed by both parties.

### Survival.  The indemnities set forth in this Agreement shall survive the completion of the Work, the payment of all portions of the Contract Price, and any termination of this Agreement.

### Performance of Obligations.  If an obligation to be performed under this Agreement falls due on a day other than a Business Day, the obligation will be due on the next Business Day.

IN WITNESS WHEREOF, Owner and Contractor executed this Agreement as of the date first written above.

Owner:

[_____________________]

By:___________________

Name:_________________

Title:__________________

Contractor:

[________________________]

By:_______________________

Name:_____________________

Title:______________________

EXHIBIT A
PROJECT SCHEDULE SUMMARY

Part I	In addition to the conditions precedent set out in Section  {xxxx]  the following conditions must be met to achieve the Notice to Proceed Effective Date:

[Add criteria]

a.	Payment of first payment in Exhibit C [xx]

b.	[ Minimum number of days between PRE-NTP and NTP- if applicable]

Part II  Guaranteed Completion Date and End Date.

Subject to Part III below, the “ Guaranteed Completion Date” is  [  #days ]  after the Notice to Proceed Effective Date, as may be extended in accordance with this Agreement.

[Note: The Guaranteed Completion Date may be expressed as a calendar date if signature of contract occurs after the NTP Date]

The “End Date” shall be [180] days after the Guaranteed Completion Date.

Part III   Seasonal Adjustments to the Guaranteed Completion Date.

[ Note: add in any provisions that will after the number of  days in Part II, and adjustment to the Contract Milestone Summary Schedule and Payment Schedule that are agreed relating to timing of the year when the NTP Effective Date occurs for items such as cold weather, monsoons,  equipment availability etc.]

Part IV  Contract Milestone Summary Schedule

The Contract Milestone Summary Schedule is  [ as follows// contained on the following [xx] pages.]

[Note:  The Contract Milestone Summary Schedule may be a 2 to 3 page GANT chart or a table similar to that as as shown below]

| Event | Time Elapsed From Notice to Proceed Effective Date (unless otherwise indicated) |
| --- | --- |
| Notice to Proceed Effective Date |  |
| Unlimited Access to Site |  |
| Mobilization Notice |  |
| Mobilize Site Office |  |
| Unlimited Access to Right-of-Way for Transmission Line |  |
| Access to the [____] Switchyard (periods of access to be agreed between Owner and Contractor) |  |
| Start erection of HRSGs |  |
| Set Auxiliary Boiler |  |
| Energize substation |  |
| Natural Gas Available at Site |  |
| Combustion Turbine Synchronization |  |
| Mechanical Completion |  |
| Steam Turbine Synchronization |  |
| Start Performance Test |  |
| Commercial Operation |  |
| Start Availability Test |  |
| Submit Availability Test Report |  |
| End Date |  |
| Guaranteed Completion Dates: |  |
| Guaranteed Completion Date |  |

EXHIBIT B- SPECIFICATIONS

[Note1  The Specification will provide a description of the Facility.

Note 2  The following is the EECC template Specification, to be modified by Engineering as required, or replace by a comparable specification.

Note 3  The following specification is intended only for EECC to its Clients.]

ENRON ENGINEERING & CONSTRUCTION CO.

ENGINEERING DEPARTMENT

| SPECIFICATION: EP-ED-001 DESCRIPTION: Design Base for [Standard] Combined Cycle Power Plant PROJECT: [STANDARD] POWER PROJECT [NAME OF] FACILITY THIS PAGE IS A RECORD OF REVISIONS OF THE SPECIFICATION. EACH TIME THE SPECIFICATION IS CHANGED EITHER THE ENTIRE SPECIFICATION IS ISSUED OR ONLY THE NEW OR REVISED PAGES ARE ISSUED. FOR CONVENIENCE THE NATURE OF THE REVISION IS BRIEFLY NOTED UNDER REMARKS; BUT THESE REMARKS ARE NOT PART OF THE SPECIFICATION. THE REVISED PAGES ARE PART OF THE SPECIFICATION AND SHALL BE COMPLIED WITH IN THEIR ENTIRETY. |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | REMARKS | PAGE No’s. | BY | DATE |
| 00 | Initial Issue |  | MR | June 11, 1998 |
| REV | PROJECT ENGINEER APPROVAL | DATE | ENGINEERING DEPT. APPROVAL | DATE |

Table of Contents

1.	OVERVIEW	64

2.	DESIGN BASE	64

2.1.	Project Description	64

2.2.	Design Conditions	64

2.3.	Plant Parameters	65

2.4.	Codes and Standards:	65

3.	SITE DEVELOPMENT	65

3.1.	Interface Points	65

4.	MAJOR POWER GENERATION EQUIPMENT	66

4.1.	Gas Turbine	66

4.2.	Heat Recovery Steam Generators (HRSG)	66

4.3.	Steam Turbine	67

4.4.	Generator	67

5.	NATURAL GAS FUEL SYSTEM	67

6.	LIQUID FUEL SYSTEM	67

7.	LUBE OIL STORAGE	67

8.	WATER SUPPLY, TREATMENT, AND TANKS	68

9.	MAIN COOLING SYSTEMS	68

10.	WASTEWATER TREATMENT SYSTEM	68

11.	FIRE PROTECTION SYSTEMS	68

12.	PLANT SUBSTATION / UTILITY INTERCONNECTION	69

12.1.	High Voltage Substation	69

13.	POWER PLANT ELECTRICAL SYSTEMS	71

13.1.	Generator Leads / Step-Up Transformers	71

13.2.	Frequency Limits	72

13.3.	Voltage Limits	72

13.4.	Plant Auxiliary System (Medium Voltage)	72

13.5.	Low Voltage System	73

13.6.	Emergency Power System	74

13.7.	Uninterruptable Power Supply (UPS)	74

13.8.	Instrument Electrical System	75

13.9.	DC Power Supplies	75

13.10.	Lighting	76

13.11.	Grounding Systems and Lightning Protection	77

13.12.	Motors	77

14.	INSTRUMENTATION AND CONTROL SYSTEMS	77

14.1.	Plant Control System	77

14.2.	Turbine Generator Control	78

14.3.	Interface and Compatibility with Local Utility System	79

14.4.	Control and Monitoring of Balance of Plant Equipment	79

14.5.	Data Acquisition	79

14.6.	Annunciator System	79

15.	COMMUNICATION SYSTEMS	80

15.1.	Public Address System	80

15.2.	Public Telephone System	80

15.3.	Two-Way Radio System	80

15.4.	Local Area Network (LAN)	80

16.	CATHODIC PROTECTION SYSTEMS	80

17.	FREEZE PROTECTION / HEAT TRACING SYSTEMS	81

18.	SEcurity	81

19.	CIVIL	81

19.1.	Earthwork	81

19.2.	Roads and Paved Areas	81

19.3.	Drainage	81

19.4.	Fencing	81

19.5.	Sanitary Facilities	81

19.6.	Major Foundations	82

20.	STRUCTURAL STEEL	82

20.1.	Piping Support and Miscellaneous Structures	82

20.2.	Platforms	82

20.3.	Embedments and Anchors	82

21.	BUILDINGS AND ENCLOSURES	82

21.1.	Buildings	82

21.2.	Enclosures	83

22.	Noise	83

23.	PLANT OPERATIONAL CHARACTERISTICS	83

23.1.	Cold Start-up Requirements	83

23.2.	Hot Start-up Requirements	83

23.3.	Warm Start-up Requirements	83

23.4.	Dispatch Rates	83

23.5.	Part Load Operation	83

- OVERVIEW

The facility is based on [one {Manufacturer, Type or Model} gas turbine generator (GTG) used in combined cycle with one {Manufacturer, Type or Model} steam turbine generator (STG), one {Manufacturer, Type or Model} gas turbine on single shaft combined cycle configuration with a {Manufacturer, Type or Model} steam turbine and an electric generator].  The balance of the plant equipment, facilities, processes, and performance data described herein is reasonably representative of what the final project configuration will be.  Plant components and systems shall be provided with adequate instrumentation to monitor control alarm and record significant plant/equipment parameters and functions to insure proper and safe plant operation. The exact type of plant facilities, equipment sizes, quantities, and processes will vary according to final technical design to meet required plant output and performance agreements, including schedule.

- DESIGN BASE

The design Base of the [Standard] Power Project at [Location] will be based upon the specifications, capacities, parameters, and site conditions that are described in this document.

  - Project Description

The proposed power project is a nominally rated [XXX] MW combined cycle plant using [X] [Manufacture, Type or Model] gas turbine[s] and [X] [Manufacture, Type or Model] steam turbine[s].  [Each, The] steam turbine/gas turbine combination shall normally power one generator [each, combined]. The primary fuel will be [natural gas].  The secondary fuel will be [Number 2 fuel oil].

  - Design Conditions

| Design Base Conditions |  |  |  |  |
| --- | --- | --- | --- | --- |
| Elevation (site) | XXX | Meters above MSL |  |  |
| Air Temperature (Annual Average) |  |  | Coincident Relative Humidity |  |
| Average | XX | °C | XX | % |
| Absolute Maximum | XX | °C | XX | % |
| High Average | XX | °C | XX | % |
| Low Average | XX | °C | XX | % |
| Absolute Minimum | XX | °C | XX | % |
| Precipitation |  |  |  |  |
| Yearly Average | XX |  |  |  |
| 24 Hour Maximum | XX |  |  |  |
| Maximum Wind Velocity | XX | Meters/sec |  |  |
| Average Wind Velocity | XX | Meters/sec |  |  |
| Seismicity | UBC |  |  |  |

  - Plant Parameters

| Performance Design Base |  |  |
| --- | --- | --- |
| Elevation | XXX | Meters above MSL |
| Operating Temperature Range |  |  |
| High Average | XX | C |
| Average (Base) | XX | C |
| Low Average | XX | °C |
| Fuel, Primary | [Natural gas] | Maximum total Sulfur & Sodium |
| Fuel, Secondary | [Number Fuel Oil] | Maximum total Sulfur & Sodium |
| Approx. Plot Plan Dimensions | XXX x XXX | M |
| Total Plant Power, Net | XXX | MW |
| NOx Emissions | XX | Ppmvd |
| CO Emissions | XX | Ppmvd |
| SOx Emissions | XX | Ppmvd |
| Design Life | XX | Years of Operation |

  - Codes and Standards:

[US Standards]

ANSI		AMERICAN NATIONAL STANDARDS INSTITUTE

ASME		AMERICAN SOCIETY OF MECHANICAL ENGINEERS

ASTM		AMERICAN SOCIETY FOR TESTING AND MATERIALS

NEMA	NATIONAL ELECTRICAL MANUFACTURER’S ASSOCIATION

IEEE	INSTITUTE OF ELECTRICAL AND ELECTRONIC ENGINEERS

NEC		NATIONAL ELECTRICAL CODE

NESC		NATIONAL ELECTRICAL SAFETY CODE

OSHA		OCCUPATIONAL SAFETY AND HEALTH ADMINISTRATION

NFPA		NATIONAL FIRE PROTECTION ASSOCIATION

AISC		AMERICAN INSTITUTE OF STEEL CONSTRUCTION

ASHRAE	AMERICAN SOCIETY OF HEATING, REFRIGERATION AND AIR CONDITIONING ENGINEERS

NACE		NATIONAL ASSOCIATION OF CORROSION ENGINEERS

[International Standards]

IEC		INTERNATIONAL ELECTROTECHNICAL COMMISSION

- SITE DEVELOPMENT

The power project will be located [plant site] in [City], [State], [Country]. The Plant will be sited and designed to meet [the draft 1995 World Bank] requirements for noise and emissions.  Site development is based on a flat and level land.  No soil remediation for toxic inclusions are considered and no removal of solid inclusions that would require other than earth moving equipment.  No blasting or similar operations are anticipated.

  - Interface Points

Various services by others or interconnections with others will be required for construction and operation of the proposed facilities. Some of these requirements and the interface points are defined in this section.

a)	Road Access: Access to the plant will be via the existing public roads. Some allowance has been made for intra-plant access roads.

b)	Plant make up water will be from a [lake, river, municipal supply, adjacent facility] and is estimated to be [XX tons per hour, gallons per minute]. This water requirement is based on the project’s operating at [XX %] average availability.  It is assumed potable water will be delivered to the site in a water main at the battery limit of the new facility.

c)	Raw water will be stored in a raw water storage tank with a [3-day] supply capacity.  Balance of plant water and firewater shall be taken from this storage tank.  A portion of the storage tank shall be dedicated for fire fighting by elevating the outlet of other services above the storage volume required for firewater.

d)	Treated clean wastewater will be discharged to the existing plant storm water system. Storm water runoff will be discharged to normal surface discharge at the plant boundary.  The oil separated from the oily wastewater shall be collected and disposed off site by truck.

e)	Construction power will be provided from [local utility, local generation site, existing facility, by customer].  Step down transformers shall be provided if required.

f)	The owner will obtain local environmental and other operational permits. The owner will provide best efforts to assist in obtaining other permits that are required for implementation of the project.

g)	The interface point for electrical power generated from the plant will be the high voltage side of the substation dead end structures.  Metering will be included at the high side of the main step-up transformer[s].

h)	The interface point for natural gas fuel is the gas pipeline at the plant boundary. Number 2 fuel oil will be delivered by [road tanker, pipeline, barge].  Custody transfer quality meters shall be included for both fuels.

i)	Black-Start capability is not included in the scope of supply.

- MAJOR POWER GENERATION EQUIPMENT

  - Gas Turbine

The system shall be comprised of [XX] [Manufacture, Type or Model] gas turbine [s], nominally ISO rated at [XXX] MW, complete with a [natural gas dry low NOx/ conventional combustors, dual fuel, naphtha, LNG] firing system [water injection system for NOx control while burning liquid fuel], inlet air plenum w/silencer, inlet air filter, [chiller, evaporative cooler] lube oil cooler, exhaust plenum with silencer, and on-line, off-line compressor cleaning system.  The gas turbine package will include a complete control system.

  - Heat Recovery Steam Generators (HRSG)

A [XX] pressure, [reheat, non-reheat], [unfired, supplementary fired with {natural gas, number 2 fuel oil}] HRSG[s] will be furnished. [The, Each] HRSG will be equipped with a [100 m] exhaust stack. The HRSG will be modular and shipped shop-assembled to the maximum extent practical. A [deaerating condenser, vacuum deaerator, integral deaerator, stand alone deaerator] shall be used to provide deaerated water to the HRSG.] The gas turbine exhaust flow shall be [horizontal with vertical heat transfer surfaces].  No allowance will be made for a bypass stack.

  - Steam Turbine

The steam turbine will be a [Manufacturer] single shaft, axial flow, [reheat, non-reheat], [double expansion, single expansion] [extraction, induction] condensing machine.  The steam turbine package will include the main steam stop and control valves, control system, and turbine supervisory instrumentation.

The steam turbine will exhaust to a steam surface condenser.  [A blanking plate will be provided.]  The condenser will have 100 % steam dump capabilities in order to permit the gas turbines and HRSG’s to operate unfired during steam turbine outages.

  - Generator

The [Gas Turbine Generator (GTG), Steam Turbine Generator (STG), Gas Turbine/Steam Turbine combined generator] shall be a [totally enclosed water to air cooled (TEWAC), hydrogen cooled] synchronous machine with power factor range of [0.85] lag to [0.95] lead.  The generator shall be directly coupled to the [gas turbine, steam turbine, gas turbine and provided with a mechanical clutch on the steam turbine side manufactured by SSS].  The generators will have a Class F insulation system and be limited to Class B temperature rise.

- NATURAL GAS FUEL SYSTEM

Filtered, super-heated natural gas will be supplied to the gas turbine. The fuel treatment system will be designed to ensure that the manufacturer’s requirements for minimum contaminant requirements are met, given the worst case fuel that may be delivered to the facility. The natural gas fuel system will include:

An actuated emergency shutdown (isolation) valve;

A filter separator skid with duplex filter system;

Fuel heating system to provide the required gas superheat;

A pressure regulating station;

A custody transfer meter;

A final filter at the connection to the gas turbine skid;

S/S piping downstream of the final filter separator.

- LIQUID FUEL SYSTEM

Treated fuel oil will be supplied to the gas turbine. The fuel treatment system will be designed to ensure that the manufacturer’s requirements for minimum contaminant requirements are met, given the worst case fuel that may be delivered to the facility. The liquid fuel system will include:

A fuel unloading skid complete with breakaway connections;

A fuel oil storage tank for storing [XX] days supply of fuel oil

A filter separator skid with [duplex filter system, centrifuge];

A fuel forwarding station;

A day tank for storing treated liquid fuel;

A final filter at the connection to the gas turbine skid.

- LUBE OIL STORAGE

The gas turbine/steam turbine/generator(s) lube oil storage system will include:

[XXX] gal lube oil storage tank;

Lube oil transfer pump;

Lube oil filter;

Lube oil treatment skid.

- WATER SUPPLY, TREATMENT, AND TANKS

Raw water shall be stored in a [XX] gallon storage tank that includes [XX] gallons dedicated to fire fighting.  The following components will also be included:

[Reverse-osmosis unit];

Demineralizer system (2 - 100% trains);

[Condensate polisher];

Demin water storage tank – [volume];

Acid and caustic storage tanks;

Potable water distribution system;

Raw water pumps;

Complete control system.

- MAIN COOLING SYSTEMS

[XXXX] gpm design circulation cooling tower;

Steam surface condenser, [XXX] duty;

Main cooling water circulation pumps [2x50 %, 1x100 %, 3x50 %];

Auxiliary circulation pumps [2x100 %, 3x100 %, 4x100 %];

Two (2) 100% plate & frame heat exchangers;

Closed loop-cooling system including two (2) 100% pumps.

- WASTEWATER TREATMENT SYSTEM

Plant liquid effluent discharge to the environment shall meet [World Bank Standards, Local Regulations].  The system will incorporate as a minimum the following components:

Neutralization system w/pumps;

Waste water treatment tank;

API oil water separator;

[automatic, manual] analyzer system;

Complete control system.

- FIRE PROTECTION SYSTEMS

The Fire Protection System shall be designed to meet the requirements of the [City, Country] Fire Code and the NFPA.  Further, the design will meet the minimum requirements of the insurer’s underwriter for insurance.

Fire water pumps [AC motor, diesel engine, AC jockey];

Main system loop with hydrants;

Centralized control panel;

Local water hose reels as required;

Deluge system for turbine auxiliaries, auxiliary transformer and step-up transformer;

[Fuel tanks foam system];

[Portable systems];

A total flooding automatic fire protection system shall be provided for the gas turbine enclosures, complete with an approved fire-extinguishing agent.  A manually operated system shall be provided for the CCR.

Raw water capacity for the fire water system will be available from the existing supply.  No additional tankage has been considered.

- PLANT SUBSTATION / UTILITY INTERCONNECTION

Plant power output will be metered at the high voltage side of the generator step-up transformer and sold to the [utility, customer].  The metering system shall be of revenue quality, consisting of solid state meters, CTs, and PTs, with the total metering system inaccuracy less than 0.5% over a plant output range of 5 % to 120 %.  The revenue metering system shall have primary and backup bi-directional meters for dependability.

  - High Voltage Substation

The interface between the Power Station and the [utility’s, customer’s] electrical grid shall be at the terminating structures located in the high voltage substation.  Coordination with the [utility, customer] shall be performed at an early stage to determine all relevant construction and operating parameters (e.g. nominal voltage, frequency, allowable voltage variation and available system short circuit current).  These parameters shall then be used to finalize the electrical design base as follows:

The high voltage switchyard configuration shall be governed by the Utility’s requirements, and shall be optimized based on the plant configuration, size and number of outgoing transmission lines.

| Main Substation Design Base |  |
| --- | --- |
| Substation Design Type | Outdoor/open air |
| Grid Voltage | KV +/- 5% |
| Grid Frequency | HZ +/- 3% |
| Utility System Short Circuit Contribution | KA |
| Number of Transmission Lines (positions) |  |
| Nominal Equipment Rating | KV |
| Maximum Operating Voltage | KV |
| BIL Rating | KV |
| Busbar Configuration | [Double Bus] [Ring out] [Breaker and a Half] |
| Number of SF6 Circuit Breakers |  |
| Substation Rated Current | Amp |
| Type of Substation Protection | Solid state relaying |
| Type of Revenue Metering | Bi-directional, solid state |
| DC Systems | 1 battery/dual chargers - ____VDC |
| Substation Yard Lighting Type | HP sodium vapor |
| Teleprotection and Communication Relaying System | Distance, overcurrent and power line carrier |

The plant switchyard will be [an Air Insulated Substation (AIS), Gas Insulated Substation (GIS)].  The power generated from the power facility will be transformed from ____ kV to ____ kV by means of generator step-up transformers.  The switchyard will have ___ SF6 breakers, with isolating switches, grounding switches and will tie directly to ______.  The switchyard will be configured in a _____ breaker ____ bus system.

The switchyard, substation and generating facilities will be protected by solid-state relaying systems including line distance, differential, busbar overcurrent, and breaker failure protection.  The protection system will be coordinated with the existing grid and utility requirements. If required, a SCADA system will be provided and will be compatible with the existing system.

The switchyard will have a building to house all control and protection equipment associated with the ______ kV system.  The building will be a prefabricated, air-conditioned metal building designed for unmanned operation.

Communications with the utility will be achieved by _________________.  The communication system will be an extension of the existing system and will be installed in the central control room (CCR) and the switchyard control building.

A switchyard DC system will be provided and will consist of a station battery that is sized based on a load profile of consumers in the _______ kV system, and two 100% redundant battery chargers.

The switchyard will have two redundant _______VAC feeders from the generating facility. Either of the two power supplies will serve all ac loads in the switchyard and will be equipped with a transfer switch to automatically transfer the load to the secondary supply upon loss of the primary supply.

| Electrical Design Base |  |
| --- | --- |
| Generation Voltage | [XXX] kV |
| Medium Voltage Level | [XXX] kV |
| Low Voltage Level | [XXX] V |
| DC Voltage Level | [XXX] VDC |
| System Frequency (Nominal) | [XXX] Hz |
| System Power Factor (@ gen. Terminals) | 0.85 lagging to 0.95 leading |
| Generator Breaker/PT Cubicles [XX.XX kV] | 1 |
| Generator Short Circuit Ratio | >0.56 |

- POWER PLANT ELECTRICAL SYSTEMS

  - Generator Leads / Step-Up Transformers

[Each, The] generator shall deliver power to the step-up transformer through [an isolated phase bus, a segregated phase bus] duct.  This bus shall consist of suitably rated [aluminum or copper, copper] conductors with each of the three phases insulated from, but surrounded by an aluminum enclosure.

The generator shall be connected to the grid by means of a generator step-up transformer.  The generator step-up transformer shall have an [on-load, off-load] tap changer. The [GTG, gas turbine and steam turbine combined generator] shall be synchronized to the grid through a [generator circuit breaker located on the low voltage side of the step-up transformer, H. V. circuit breaker located in the switchyard].  Provision shall be made to allow the GT’s to be synchronized to the grid via a H.V. circuit breaker in the switchyard.  The STG shall be synchronized to the grid via a H.V. circuit breaker located in the switchyard.

[Note: repeat table below as necessary for each unique GSU transformer].

| [GTG, STG, Combined Generator] Step-Up Transformer |  |
| --- | --- |
| Quantity | [XX] |
| Transformer Rating | [XXX] / [XXX] / [XXX] MVA |
| Type | Oil-Filled |
| Cooling Stages | OA / FA / FA |
| Nominal Primary Voltage (Generator Voltage) | [XXX] kV – Delta |
| Nominal Secondary Voltage (High Voltage) | [XXX] kV Grnd-Wye |
| Tap Changers (on load/off load) | On load |
| Tap Change | [5/8%, 1.25%] each |
| Number of Tap Changes Up | [16, 8] |
| Number of Tap Changes Down | [16, 8] |
| Generator Connections | 1 |
| Generator Connection Type | Isolated Phase Bus, Segregated Phase Bus |
| Generator Connection Rating | [XXXX] Amp |

The GSU shall be provided with a cooling class of OA/FA/FA.  The fans in each cooling stage shall be separated into two circuits to reduce the possibility of losing all fans in any single cooling stage.  The two fan circuits shall be fed from either redundant or automatic throw-over supplied power sources.  Each cooling stage shall increase the base rating by no more than 33 1/3%.

In order to insure the transformer is not the limiting component for any site temperature condition, the transformer shall be sized such that the maximum FA rating is greater than or equal to 16 percent more than the maximum capability of the driver.  This margin shall consider both the winter and summer ambient extremes.

  - Frequency Limits

The plant shall be capable of operation within the frequency ranges of the [XXX] kV Grid System, as listed in the table below, for the indicated duration’s and return to the continuous operation range without a trip. Frequency excursions of the [XXX] kV Grid System beyond the limits of the table below may cause a trip of the plant.

Frequency Range			Duration of Excursion

[XX.X] to [XX.X] Hz			Continuous Operation

[XX.X] to [XX.X] Hz			Twenty (20) minutes

[XX.X] to [XX.X] Hz			Ten (10) Seconds

[XX.X] to [XX.X] Hz			Ten (10) Seconds

at [XX.X]  Hz				Immediate Trip

at [XX.X]  Hz				Immediate Trip

  - Voltage Limits

The plant shall be capable of continuous operation when the voltage on the [XXX] kV Grid system (as measured on the high side of the main step-up transformer) is [XXX] kV to [XXX] kV.  Voltage less than [XXX] kV or greater than [XXX] kV may cause an immediate trip of the plant.

  - Plant Auxiliary System (Medium Voltage)

[One, X] unit auxiliary transformer[s] (UAT) shall supply the plant medium voltage system at [X.X] kV.  Each UAT shall be capable of supplying the auxiliary load of the entire facility.

The plant medium voltage switchgear shall be located in the switchgear building.  The switchgear will feed the medium voltage plant auxiliaries (large pumps, etc.) and will supply power to the plant low voltage distribution system by means of station service transformers.

All bus shall be made of copper.  Vacuum type circuit breaker shall be used for the main and tiebreakers, and feeder breaker supplying L.V. substation transformers, and motor starters.  Medium voltage motor starters may be vacuum contactor with fuse, if approved.

The plant auxiliary power distribution system shall consist of area substations, which are comprised of switchgear, motor control centers, bus ducts, lighting panels, and power transformers shall be located for convenient distribution to loads.

The secondary of auxiliary transformers shall be routed to the switchgear using cable feeders, cable bus or metal enclosed, non-segregated, rigid bus duct.

| Unit Auxiliary Transformer (UAT) |  |
| --- | --- |
| Quantity | [X] |
| Rating | [XX.X /X.X] MVA |
| Type | Oil-Filled |
| Cooling Stages | OA / FA |
| Nominal Primary Voltage | [XX.X] kV-Delta |
| Nominal Secondary Voltage | [X.X] kV Wye |
| Type of Tap Changers | [on-load, off load] |
| Tap Change | % Each |
| Number of Taps | ___Up and __Down |

| Medium Voltage Connections |  |
| --- | --- |
| Medium Voltage Switchgear Continuous Rating | [XXXX] Amp |
| Number of MV Main Circuit Breakers | [X] |
| Number of MV Tie Circuit Breakers | [X] |
| Number of MV Feeder Breakers | [X] |

Switchgear and motor control centers shall be installed indoors and, when applicable, shall be installed in modularized factory assembled switchgear buildings.

Switchgear buildings shall be temperature and humidity controlled.  (Tropicalyzed switchgear shall be provided.)

At the completion of construction, there shall be a minimum of ten percent (10%) spare capacity in the number of medium voltage motor starters remaining.

  - Low Voltage System

The plant low voltage system at [XXX] V shall be fed from [X] secondary unit substation transformers.  The turbine auxiliaries and other balance of plant AC loads will be served from the motor control centers.  All bus shall be made of copper.

| Secondary Unit Substation Transformer (SUS) |  |
| --- | --- |
| Quantity | [X] |
| Rating | [XXXX/XXXX]kV |
| Type (oil filled/dry-type) | dry-type |
| Cooling Stages | AA / FA |
| Nominal Primary Voltage | [X.X] kV |
| Nominal Secondary Voltage | [XXXX] kV |
| Type of Tap Changers | Off-Load |
| Capacity as % of Total Load Rating | 100% |

| Low Voltage Connections |  |
| --- | --- |
| Low Voltage Connection | [cable, bus] |
| Low Voltage Switchgear Rating | [XXXX] Amp |
| Number of LV Main Circuit Breakers | 1 |
| Number of LV Tie Circuit Breakers | [X] |
| Number of Low Voltage MCC Sections | [X] |
| Number of Spare LV Breakers | [X] |

The basic method of construction shall be cable in cable tray for power, control, lighting, and instrument circuits.  Where previously approved, secondary distribution cable systems may be installed in rigid steel conduit.  When multi-conductor instrumentation cable is used, the cable shall be run overhead in ladder type cable trays.  Cable insulation shall be of flame retardant, low smoke construction.  Above ground distribution shall be used when pipe racks or sleepers are available or when otherwise feasible.

Conduit installed below ground in duct banks shall be encased in red-colored concrete reinforced with rebar.  Conduits to be installed in underground duct banks shall be schedule 40 PVC and shall slope toward a manhole for drainage.

  - Emergency Power System

Critical loads required to operate during and following a loss of power or plant shutdown shall be fed from an essential bus.  The essential bus shall have a normal power source and an emergency power source.  The emergency power shall be provided by a dedicated stand-by diesel generator, which shall be connected to the essential bus by a synchronizing circuit breaker.  The stand-by generator system shall be capable of periodic full load operation for test purposes, without jeopardizing normal plant operation.

| Stand-by Diesel Generator |  |
| --- | --- |
| Number | 1 |
| Minimum Rating | XXX]kW |
| Voltage | [XXX] V |
| Power Factor | 0.80 PF lag |

Circuit breakers that will automatically switch the essential load from the normal to the emergency source shall be provided at the essential bus.  The circuit breaker shall include a delay in original transfer to avoid unnecessary operation due to momentary voltage dips.  In addition, transfer back to the normal source shall be manually operated.

Loads that are typically powered from the essential bus are:

UPS Main Supply;

One Battery Charger per DC System;

Aviation Obstruction Lighting;

Emergency Lighting;

Instrument Power;

Turbine emergency lube oil pumps.

  - Uninterruptable Power Supply (UPS)

Systems critical for plant operation and shutdown require an uninterruptible power source.  The uninterruptable power supply (UPS) shall be a single-phase, redundant, system complete with static transfer and manual bypass switches to furnish power to the emergency shutdown system and the distributed control system.  The system shall have batteries sized for the load based on a load profile for the unit and a minimum thirty (30) minute operating period.  The UPS output shall be regulated to  1 Hz.  The UPS shall normally received power from a low voltage MCC connected to the essential bus.  A regulating transformer shall provide an alternate low-voltage source for the UPS load for operation in bypass mode. .  Additional UPS systems shall be supplied for larger stations (a minimum of 1 system per block of 2 GTG and 1 STG).

The list of suggested loads related to process and plant safety that shall be power from the UPS is as follows:

Distributed Control System (DCS);

Control Room Operator’s CRT Terminals and Annunciators;

Printers, Disk Drives and Plotters in the Control Room;

Plant Shutdown DCS and Critical Programmable Logic Controller (PLC) Systems;

Fire Alarm and Detecting Systems;

Continuous Emission  Monitoring System (CEMS);

Critical Safety Related Analyzers;

Process Package Units Computer Systems;

Large Rotating Equipment Local Control Panels;

Public Address/Warning System.

Computer Local Area Network (LAN)

| UPS Systems |  |
| --- | --- |
| Number | 1 |
| Voltage | [120, 230] VAC |
| Rating | [XXX] kVA |
| No. of UPS Battery Systems | 1 |
| UPS Battery Systems Rating | By Vendor |

  - Instrument Electrical System

The instrument electrical power system shall be serviced from the plant low voltage, three-phase, instrument power distribution panel board.  The instrument power transformer shall be supplied from a low voltage essential bus.  The electrical system shall service the instrument power control panel and all instrument circuits requiring separate power feed, clocks, analyzers, relays, and solenoid valves.

  - DC Power Supplies

A separate DC power supply system shall be provided for each gas turbine, steam turbine, balance of plant, and the high voltage substation.

The DC power supply system shall provide a reliable source of power for the GT and ST DC power loads and balance of plant (BOP) control and power functions during normal and emergency plant operating modes.  Each system shall consist of the following major components:

Lead-acid/calcium batteries sized for the plant emergency DC load profile and a minimum of 2 hours;

Two full-capacity redundant filtered silicon controlled rectifiers (chargers) with load sharing capability and a recharge time of 8 to 12 hours;

DC distribution panels (two distribution panels, with fused disconnect switches).

| Battery Systems |  |
| --- | --- |
| Quantity of DC Panel Boards | [X] |
| No. of Station Service Battery Systems | [X] battery/dual charger |
| Type of Station Battery Systems | Lead-Acid/Calcium |
| Voltage | [XXX] VDC |
| Station Battery Systems Rating | By Vendor |

  - Lighting

Three levels of lighting shall be provided.  During normal operation, lighting shall be powered from the normal AC power system.  Upon a loss of the normal AC power system, emergency lighting for the Central Control Room (CCR) and other critical operating areas shall be powered from the station battery or the stand-by diesel generator.  Egress lighting fixtures shall be provided with battery packs to assure safe egress on a loss of the normal lighting power system.

Indoor areas shall be provided with lighting.  In addition, the following outdoor areas shall be lighted:

Unloading Areas;

Transformer;

Parking Lots;

Operating Areas;

Pump Areas;

Utility Areas;

Valve Manifolds;

Tank Farms;

Fuel / Waste Oil Treatment;

Perimeter Roads;

Boilers and Stacks, including Aircraft Warning Lights, if necessary;

Water Treatment Plant;

Substation;

Fuel Gas Treatment area;

Secured or monitored areas.

Outdoor lighting shall be photocell controlled with “on-off-auto” selector switch.

Outdoor area lighting and indoor high bay areas such as maintenance shop/warehouse building shall employ color corrected high-pressure sodium (HPS) lamps with enclosed fixtures and integral ballasts.  Fluorescent fixtures shall be provided for instrument control rooms, offices, laboratories, switchgear rooms, gatehouse, and similar facilities.  Street lighting shall be HPS fixtures mounted on poles.  Outdoor lighting in the process areas, around equipment and on platforms shall utilize fixtures with globe reflector and guard covers.  General illumination of outdoor areas shall be provided by floodlights mounted on poles, buildings or structures as required.

Fixtures located in selected areas of the plant will be equipped with an “instant re-strike” feature and powered from the essential bus to provide for egress in case of a blackout condition.

  - Grounding Systems and Lightning Protection

A grounding system shall be designed according to the IEEE Standard 80, 142, and 665.  The grounding system shall be rated to meet the short circuit fault level current for 30 seconds or the short circuit rating of the circuit breaker whichever is higher.  The design of the grounding system will be considered with the existing grounding system at site.  Equipment and structural steel shall be connected to the grounding system.  The conduit system is considered grounded by the equipment to which it is connected.  Ground rods, if used, shall be zinc or copper-clad steel rods. In general, the total resistance to remote ground of the grounding system shall not exceed 5 Ohms for the general plant area, and 1 Ohm for the high voltage substation.

Lightning protection for all structures such as buildings, towers and stacks shall be provided. Ground rods or ground mats connected to the grounding system shall be located at the base of each structure.  The connections between the ground rods and structures shall be with minimum copper conductors #2/0 AWG, and in accordance with NFPA 780, Lightning Protection Code.  The design of the grounding system will be coordinated with the [utility, customer] and the existing facility fault currents.

  - Motors

All insulated windings shall have a minimum of a Class F insulation system and the temperature rise shall be limited to Class B rise only.

- INSTRUMENTATION AND CONTROL SYSTEMS

  - Plant Control System

The design of the plant control system shall be based on the centralized control of the “power island” and auxiliary mechanical and electrical systems from a single central control room (CCR) together with facilities for combined control and variable load sharing; and for system monitoring and historical data storage and interrogation.

Control and monitoring of the Plant services, utilities and safety systems shall also be normally executed from the CCR.

The main control system shall be a microprocessor based, functionally distributed, digital control monitoring and information system (DCS).  The DCS will consist of functionally distributed CPU’s, I/O termination cards, cabinets, power suppliers, interface devices, operator/ engineer/ supervisor stations, etc., necessary to provide control, protection, monitoring, annunciation, and data acquisition of the plant.  The DCS shall have the capability to link with field databuses for connection to smart instruments (transmitters, valves, etc.) if the design requires.

Multi-function controllers will be used to perform continuous control, interlocking, discrete control and sequencing, logical and arithmetic calculations, and communication with devices which are not part of the DCS (PLC’s, SCADA, etc.).  Control processors will be provided with redundancy feature such that, on failure of a primary controller, the back up will automatically take over the functions of the primary controller, without any system interruption.  The DCS will communicate within the system using a redundant data highway routed in two segregated paths.

The power supply units will have a back-up power supply, which will automatically take over, if the primary power supply fails.

The plant operators shall have the ability to monitor and execute the control functions of the processes from the main control room using the operator stations, equipped with CRT’s and keyboards.

The Plant’s central control system as a minimum will contain the following equipment:

Control Console with CRT based operator stations for control and monitoring of GT, ST, HRSG, BOP and switchyard/ electrical systems.

Sequence of Events Recording (SER) function (1 ms resolution).

Control desk with hard wired trip push buttons and dedicated drum level indicators. (Signaled by conductivity type of sensors).

Peripherals including printers and video copier

Engineer Station with CRT, keyboard, and laser printer for programming.

Supervisor Station with CRT, keyboard, and printer for overall monitoring.

Data Server Station for data storage (historian), with short (35-day) and long-term (1-year) data storage medium, including optical disc medium.

Control processors and process I/O hardware.

Redundant Data Highway (Information & Control) networks.

Auto synchronized master time keeping system.

Gateways (communication data links for interfacing with SCADA and packaged control systems).

Control and termination cabinets.

The GTG(s), STG(s) will be furnished with stand alone control systems with control monitors and control interface facilities to integrate with the plant DCS at the central control room.

A Continuous Emissions Monitoring System (CEMS) of the type necessary will be provided, if required by applicable Law, to monitor the gaseous emissions of the unit.  CEM measuring points will be located in the stack and the CEM cabinets will be located in an enclosure at the base of the stack.  The system will sample and analyze combustion gases.  Suitable remote monitoring through the DCS will be provided to keep the plant operator properly informed.

The DCS shall include a 20% wired spare capacity for I/O.  20% spare capacity is also required for termination, system memory/ display capability, etc. to cover the entire system.

The DCS shall have capability to interface with a PC based Plant Performance Monitoring System with remote access facility.

The DCS shall also include facilities for remote access by DCS vendor’s Technical Center to facilitate system help/ diagnostics, if required by the Plant.

  - Turbine Generator Control

Primary control, monitoring, alarming and protection of the GT, ST, and generators will be accomplished using these controls systems and remote plant DCS CRT based control stations.  The local control system for the GT, ST & generators will be located in an enclosure next to its associated unit.

The system vendor supplied remote CRT based control stations will also be located in the CCR.  Each control system will be integrated with the plant DCS (through redundant communications links) that will allow monitoring and alarming at the CCR.  Automatic or manual synchronizing of the generator with the system will be executed from the central control room.  Generator Synchronization Controls, as provided by the System vendor will be provided in the control room.  The plant DCS shall also have the capability to execute the functions through the operator stations.

  - Interface and Compatibility with Local Utility System

The DCS shall have the capability to communicate with the local utility load dispatch center through SCADA or gateway with data link.  The utility will have access to selected data, which will allow the utility to monitor and auto load dispatch the plant.  The Coordinating Committee will establish which data will be exchanged.

  - Control and Monitoring of Balance of Plant Equipment

Control and monitoring of the balance of plant systems will be accomplished using the plant DCS.

Controls of packaged systems, which are furnished with the systems, will be interfaced with the plant DCS through communication data links and/or hard I/O.  Such systems may include but will not necessarily be limited to the following:

1.	Water Treatment Systems (Demineralizer, etc.);

2.	Air Compressors;

3.	Waste water treatment system;

4.	Switchyard/ Electrical Controls;

5.	HRSG – Fuel Trip & BMS (if firing is required).

Controls for systems, which do not have a pre-packaged control system, will be configured in the plant DCS.  Some of these systems, but not necessarily all, are listed below:

1.	HRSG controls including drum level controls;

2.	[Fuel Oil Transfer systems];

3.	[Fuel gas handling and treatment systems];

4.	Condensate, feedwater, and steam systems;

5.	Cooling water systems;

6.	BOP Controls.

  - Data Acquisition

The plant DCS will include a Data Historian (Data Acquisition) function to allow storage (short and long term) and retrieval of data, event recording and trending of selected points.  Any point in the DCS could be included in the trend.  The report generation shall be programmable so that the plant can format reports in ‘Excel.’

  - Annunciator System

The plant DCS will be capable of annunciating any point to which it has access.  Sequence of Event Recording (SER) will be provided for post trip analysis, with 1 ms input resolution.  SER function will be an integral part of the Plant DCS, and capable for about 100-point capacity.

- COMMUNICATION SYSTEMS

  - Public Address System

A public address system to provide one-way communication, such as emergency warnings or general announcements, throughout the plant operating areas will be provided.

A multi-channel, public address, plant paging system shall be provided  The system shall consist of desk top stations, control panel, field mounted loudspeakers and field mounted call stations with channel selection controls and telephone type hand-sets throughout the process units, utilities and off-site locations.

Call stations shall be located throughout the plant areas and be of suitable construction for the area classification.

  - Public Telephone System

A plant telephone system is to be utilized as a primary means of communications within the plant, and service to outside premises shall be supplied if requested.

The system shall consist of a PABX system (Private Automatic Branch Exchange) with capacity for fifty (50) extensions, multiple trunks for outside connection (10) and multiple internal connecting paths.  Approximately twenty (20) telephone sets will be furnished and strategically located around the plant.  Provision for fax modem connections to outside lines will also be available.

A switchboard to assist direct access lines in making long distance calls and to connect indirect access lines to a trunk shall be furnished.

  - Two-Way Radio System

An in-plant, two-way radio system consisting of a base station and portable hand-held radios shall be provided for communications between operating and/ or maintenance personnel.  The radio base station will be located in the control building complete with desk microphone.  The antenna will be mounted outdoors.  There will be two open channels communicating between five two-way portable radios with carrying belts, and chargers.  Communications will be inter radio and monitored by the base station, which can over-ride if necessary.

  - Local Area Network (LAN)

A Local Area Network (LAN) shall be installed that connects the administrative offices of the power plant and any associated support facilities.  The Plant DCS shall have the interface capability including suitable security provisions so that if desired, DCS can be linked to the Corporate LAN.

- CATHODIC PROTECTION SYSTEMS

A cathodic protection system shall be furnished for corrosion protection of underground and / or submerged metallic structures such as buried, pressurized steel piping systems and the underside of vessels or tanks in accordance with NACE standards.

For the protection of underground structures such as isolated pipe and similar equipment of relatively small surface area, sacrificial galvanic anodes of magnesium, zinc, or aluminum shall be distributed along the structure to be protected.

For the protection of underground structures, extensive piping systems, and in locations where soil resistivity is high, an impressed current system consisting of anode beds and rectifiers shall be furnished.

- FREEZE PROTECTION / HEAT TRACING SYSTEMS

The plant shall be supplied with a main generation building which shall be insulated and heated in order to prevent freezing of any indoor system during normal operation, start-up, shutdown or plant outage at any site ambient temperature and weather condition.  For items outside the main generation building, a heat tracing system shall be provided for freeze protection at any site ambient temperature and weather condition.  The heat tracing system shall supply a controlled amount of heat to maintain the temperature above the freezing point or, in the case of process protection, maintain proper viscosity, temperature or other parameters required for process operation.  Lines requiring freeze protection normally include (but shall not be limited to) water lines, instrument air lines, instrument housings so identified, safety showers, eyewash stations, and condensate lines.

- SEcurity

The main plant entrance and site perimeter shall be monitored from the CCR through use of a closed circuit television (CCTV) system.

In addition, the HRSG drum level shall also be monitored from the CCR through the use of the CCTV system.

- CIVIL

  - Earthwork

Clearing and grubbing will be limited to that required to construct the plant.  All material from clearing and grubbing operations will, if possible, be disposed of on the plant site.  Topsoil will be removed and stockpiled for reuse.  Surplus topsoil will be placed and contoured to enhance plant appearance.  Contours and slopes will be based upon the geo-technical report.

  - Roads and Paved Areas

The main entrance road will enter the plant site from the exterior road system.  Inside the plant, a ring road will be provided from the main entrance for access to the plant major equipment and control building.

The power block equipment will have a concrete slab surface.  Yard areas not requiring frequent road access will be surfaced with crushed rock.  Other non-traffic areas will be seeded.

  - Drainage

The storm water will be managed through a combination of open trenches, swales, ditches, and underground piping.  Surface drainage will be maximized and ditches having a grade of not more that 1% and normal minimum grade of not less than 0.25% will be routed to outfall structures near the shoreline.   Soil erosion and sediment control plans will be developed as required.

  - Fencing

The plant perimeter will be enclosed with a 2.5-m high aluminum or hot dip galvanized coated steel wire fence, coated posts and rails, and accessories as required with a barbed wire overhang.  The main entrance will be secured by a chain link slide gate.  Additional gates will be provided as necessary.  Grounding of the fence will be considered as part of the grounding study.

  - Sanitary Facilities

Plant sewage will be collected and routed to a packaged sewage treatment plant with effluent discharged to the discharge system.

  - Major Foundations

The Estimated Scope of Work shall include the foundations that are necessary for the power station, including but not limited to:

Gas turbine and auxiliary systems;

Steam turbine and auxiliary systems;

Generator(s);

Heat Recovery Steam Generator stack;

Transformers;

Buildings, steel support structures, and enclosures;

Tanks;

Condensers.

Other support structures for the power station, including but not limited to:

Balance of plant mechanical and electrical equipment foundation;

Slab on grade;

Underground trenches, drains, conduits;

Transformer fire walls;

Walkways and roadside drains and curbing.

In addition to the foundations, hard standing areas and permanent roadwork as necessary for the power station, including but not limited to:

Roadways;

Paved concrete hard standing areas for turbine maintenance and removal.

- STRUCTURAL STEEL

  - Piping Support and Miscellaneous Structures

Piping will be supported on either sleepers at grade or elevated pipe racks within the plant boundaries.  Pipe racks will be constructed of structural steel conforming to ASTM and will also provide support for cable tray and conduit runs where accessible.

  - Platforms

The plant will be furnished with necessary steel access platforms, with ladders, stairs, handrails, and grating in accordance with the requirements generally accepted international engineering practices (GIP).  Access will be provided for normal operation and maintenance of plant.

  - Embedments and Anchors

Miscellaneous embedments for support and anchorage of equipment and structures against concrete will be provided in such a manner as to provide proper field alignment.

- BUILDINGS AND ENCLOSURES

Buildings and enclosures shall be provided with [heating] ventilation and air conditioning considering local climatic conditions, building habitation and housing function.

  - Buildings

This project description assumes buildings will be prefabricated and shipped to site.  Equipment enclosures are assumed to be prefabricated and shipped to site for installation for the following:

Control buildings, including maintenance shops

Warehouse

Water treatment system building

[Chiller building]

[Powerhouse]

  - Enclosures

MCC module

Substation control module

Local control modules

Steam turbine bay

Gas turbine bay

Fire water pumps

Guard house

- Noise

The plant shall meet the following noise criteria:

- PLANT OPERATIONAL CHARACTERISTICS

  - Cold Start-up Requirements

Initial Start-up to synchronous speed to full GTG load:	165 minutes

Synchronous speed to full plant load:			180 minutes

  - Hot Start-up Requirements

Initial Start-up to synchronous speed to full GTG load:	50 minutes

Synchronous speed to full plant load:			60 minutes

  - Warm Start-up Requirements

Initial Start-up to synchronous speed to full GTG load:	100 minutes

Synchronous speed to full plant load:			120 minutes

  - Dispatch Rates

Maximum ramping rate (up or down) between 50% and 100% load, under normal operational conditions will be 9 MW/minute.

  - Part Load Operation

The plant shall be capable of continuous part load operation down to [XX%] load (net) at any ambient temperature, while meeting NOx emissions requirements with either natural gas or No. 2 fuel oil.

EXHIBIT B-2
SCOPE CLARIFICATIONS AND EXCEPTIONS

[Note- This Exhibits sets Scope Clarifications and Exceptions for categories such as follows:

-	Site Risk- Goetechnical  See Section 3.17.3 and 15.1.6

-	Existing Facilities

-	Management of known pre-existing hazardous materials

-	Site Preparation  (see Section 3.1.2.20)  [no such Section]

-	Project Agreement exceptions  (See Section 15.1.6) [no such Section]

EXHIBIT B-2
SCOPE OF WORK

[Note:  The following Exhibits B-2 are an indicative split of work between Onshore and Offshore Contractors, and such listing is to be modified as appropriate]

1.	Purpose

The purpose of this Exhibit B-2 is to further delineate the Scope of Work of the Contractor with respect to the Facility and with respect to work performed by others.

2.	Specifications

The Specifications, as provided in Exhibit B, contain the overall requirements of the Facility.  The  Contractor shall perform all Work required by this Agreement in such a manner as to ensure that the completed Facility conforms to the Specifications.  To the extent necessary to ensure that this conformance with the Specifications,  Contractor shall coordinate its efforts with those of other contractors of Owner and their subcontractors and supply information and materials in a timely fashion as required.

3.	Responsibilities of  Contractor

Contractor shall supply all labor, tools, equipment, materials, services, management and supervision to complete the following work:

Initial site preparation including site surveying, clearing, grubbing, deforestation, erosion control and fencing.

--	 Installation of Major Foundations including:

Gas turbine generator

Steam turbine generator

HRSG

Auxiliary Boiler

Cooling Tower Basin

Building Foundations

-	Installation of the storm water containment system.

-	Installation of major underground facilities including fire water distribution system and raw water supply lines.

-	Buildings erection and finishing.

-	Installation of the fuel oil tank containment area.

-	Foundation for the balance of plant equipment and construction materials required for the above activities.

-	“As-built” drawings are to be developed.

-	Monthly progress reports.

-	Receipt at the Delivery Point, transportation to site, unloading and installation of  Equipment

-	Completion, commissioning and testing of the Facility

-	Installation of Switchyard

-	Procurement, transportation to Site, and installation of Equipment and construction materials necessary for completion of the Facility

-	Monthly progress reports

-	Erection of all shop fabrication and field erected tanks

-	Completion of all electrical and controls installation

-	Installation of Facility security systems

-	Installation of the transmission and distribution system including communications, interconnection of the [____] switchyard, upgrades to the [____] switchyard, sixth bay in the Facility switchyard and third line out of the switchyard connecting to the [____] switchyard

-	Final grade and landscaping

-	Notify Owner, in writing, of the anticipated schedule of deliveries of the Commissioning Power (as defined in the Power Delivery Agreement) in sufficient time to enable Owner to notify [____] and [____] in accordance with section 5.3.4 of the Power Delivery Agreement and shall confirm such schedule to Owner in sufficient time to enable Owner to confirm the same in accordance with Section 5.3.4 of the Power Delivery Agreement

engineering provided by others.

EXHIBIT B-2 SCOPE OF WORK (Supply Contract)

l.	Purpose

The purpose of this Exhibit B-2 is to further delineate the Scope of Work of Supplier with respect to the Facility and with respect to work performed by others.

2.	Specification

The Specifications, as provided in Exhibit B, contain the overall requirements of the Facility. Supplier shall perform all Work required by this Agreement in such a manner as to ensure that the completed Facility conforms to the Specifications.  To the extent necessary to ensure this conformance with the Specifications, Supplier shall coordinate its efforts with those of other contractors of Owner and their subcontractors and supply information and materials in a timely fashion as required.

3.	Responsibilities of Supplier

Supplier shall supply all labor, material, services, management and supervision necessary to complete the following work:

-Basic engineering and detailed design of the Facility and procurement of the Supplier Equipment in conformance with the Specifications

-Specification, procurement, inspection and delivery of the Supplier Equipment to the Delivery Point

-

-The detailed Performance Test and Availability Test procedures

-Monthly progress reports

-Preparation of O&M manuals and Operator Training Manuals

-As required, spare parts, vendor quotations

-Finalization of “as built” drawings

-All software and other intellectual property required to operate and maintain the Facility

EXHIBIT B-3  EQUIPMENT

[Note: For the purpose of Onshore/Offshore contracts itemized listing of equipment to be supplied in the onshore/offhore contracts may be required for import duty and other tax reasons.  The following Exhibits B-2 are intended to provide a sample of listings]Used in creating offshore contract - to list Equipment to be imported.]

Valves					Pipes and fittings

Power wiring				Conduit

Disconnect switches, as required	Transmission towers, as required

Control wiring				Breakers

Miscellaneous structural steel		Communication system

Rebar					Cement

Structural Steel				Sand

Wood					Paint

Manhold covers				Fencing

Overhead cranes			Concrete vaults

EXHIBIT B-3 SUPPLIER EQUIPMENT

Condensate Preheater

Gland Steam Condenser

Condenser

Mechanical Draft Cooling Tower

Intercooling System Heat Plate Type Exchanger

Heat Recovery Steam Generator

Auxiliary Steam Boiler

Natural Gas Heater

Gas Turbine

Stem Turbine

Air Compressor

Distillate Fuel Generator Set

Demin Installation

Chlorination Unit

HP-IP Reducer Desuperheater Station

HP-LP Reducer Desuperheater Station

LP Bypass Station

Distillate Fuel Unloading Pump

Distillate Fuel Forwarding Pump

LP BFW Pump

HP BFW Pump

Condensate Pump

Vacuum Pump

Main Cooling Water Pump

Circulation Pump Intercooling System

Raw Water Pump

Demin Water Supply Pump

Demin Water Regeneration Pump

Distillate Fuel Storage Tank

Fuel Gas Knock-out Dmm

Deaerator/Accumulator

Electrical Installation Complete

Transformers

Batteries

HV Equipment

MV-Switch Gear

LV-Switch Gear

Power Control Cables

DCS Equipment

Water Treatment

Fire Protecting Systems

Piping & Valves

Condenser

Electrical breakers

Electrical disconnect switches

Steel building structures and cladding

EXHIBIT B-4  PRELIMINARY NOTICE TO PROCEED SCOPE OF WORK

EXHIBIT C-1  CONTRACT PRICE

Contract Price

The Contract Price is [$XXXXXXXXX].____ United States Dollars, including the following allowances

[Note: the Contract Price may need to broken out into sub categories such as design, supply, equipment etc for tax mitigation purposes.  Project specific  Tax advice will be required for such]

Allowances

| Item | Allowance (US$) | Date for Contractor to provide firm price |
| --- | --- | --- |

t

EXHIBIT C-2 PAYMENT SCHEDULE

| Milestones | Amount | Monthly Percentage | Cumulative Percentage |
| --- | --- | --- | --- |

The Milestone Payments comprise payments made by Owner to Contractor upon completion of each Milestone in advance of Substantial Completion and do not constitute acceptance by Owner of the Work and Equipment which is the subject of each Milestone.  Contractor shall issue an invoice for each Milestone Payment, and Owner then shall pay in full the amount of each invoice to Contractor within ten (10) days after receipt of said invoice.

EXHIBIT C-3  CONTRACT PRICE ESCALATION

The Contract Price is not subject to escalation unless the Notice to Proceed Effective Date occurs after ___.  If the Notice to Proceed Effective Date occurs after such date, then the Contract Price will be escalated  [  insert the dealxxx]

The Allowances referred to in Exhibit C-1 are/ are not subject to escalation.

EXHIBIT C-4 LIQUIDATED DAMAGES

{NOTE:  Modify accordingly for any multiple phase or multiple fuels impacts

1.	Output Liquidated Damages

Owner shall assess, and Contractor agrees to pay to Owner, liquidated damages at a rate of $______ per kW for each kW by which the Adjusted Electrical Output on gas during the Performance Test upon which Contractor based Substantial Completion is less than the Output Guarantee but is greater than the Minimum Performance Output Guarantee

2.	Heat Rate Liquidated Damages

Owner shall assess, and Contractor agrees to pay to Owner, liquidated damages at a rate of $_________ per BTU/kWh ([HHV/LHV]) for each BTU/kWh (LHV) by which the Adjusted Heat Rate on gas during the Performance Test upon which Contractor based Substantial Completion exceeds the Heat Rate Guarantee).

3.	Delay Liquidated Damages

For each day that Substantial Completion occurs after the Guaranteed Completion Date Owner may assess $_______ per day a delay liquidated damages (the “Delay Liquidated Damages”).

4.	Maximums

The maximum amount of liquidated damages payable for Contractor’s failure to meet the Guaranteed Completion Date shall be limited to [____] percent (__%) of the Contract Price.

The maximum amount of liquidated damages payable for Contractor’s failure to meet the Guaranteed Heat Rate shall be limited to [____] percent (__%) of the Contract Price.

The maximum amount of liquidated damages payable for Contractor’s failure to meet the Guaranteed Electrical Output shall be limited to [____] percent (__%) of the Contract Price.

The aggregate amount of liquidated damages payable under the Agreement for failure to meet the Guaranteed Heat Rate, Guaranteed Electrical Output or Guaranteed Completion Date shall not exceed [____] percent (__%) of the Contract Price.

[Note: If the caps on LD’s remain in Section 14.1 then Clause 4 can be deleted]

EXHIBIT C-5 FORM OF INVOICE ¹/

[LETTERHEAD OF  CONTRACTOR]

[NOTE:  Modify the form of invoice as necessary for the country and tax implications]

[Name of Owner]

333 Clay Street, Suite 1400

Houston, Texas 77002

Attention:

Telefax: (713) 646-7202

Your VAT Identification Number:					Date of Issue:

Our VAT Identification Number:

ORIGINAL

Dear Sirs:

VAT INVOICE NO. __________

Re:	 Contract dated as of [____] between [____] (“Owner”) and [____] (“ Contractor”) (the “ Contract”)

We set out below our invoice in respect of milestones achieved during the month of [____] in relation to the  Contract.

Milestones				Amount (US$)

Net Amount

VAT @ [__]

Gross Amount

_________________________________

¹/	 Contractor shall submit its invoices in such a form as will enable Owner to claim any refund of [Host Country] value added taxes to which it may be entitled.

Gross Amounts in Words:

Equivalent in PLN:

Net Amount

Equivalent of VAT

Gross Amount

Exchange rate for 1 USD

amounts in PLN according

to the table no. [_____] of

exchange rates by National

Bank of Poland dated

[__________]:	   1US$ =

[__________]   PLN²

We enclose the documentation and data listed below which demonstrates that the milestones referred to above were achieved during the month of [______________].

[List of documentation and data enclosed]

Payment of the Gross Amount is due on or before [____________] and should be made by wire transfer of immediately available funds to our account at [____________] as notified to you previously in accordance with Section 7.2.3 of the  Contract. [You are, however, entitled to deduct [__________] from the Gross Amount as Retainage (such Retainage amount as calculated in accordance with Section 7.2.4 of the  Contract) until the earlier of successful completion of the Availability Test (as defined in the  Contract) or the posting by us of a Retention Bond in accordance with Section 21.2 of the  Contract.]¹/

We confirm that the amount payable under this Invoice, together with the amounts payable under our previous invoices, do not exceed the applicable cumulative monthly payment limitation set forth in Exhibit C-2 to the  Contract.

Yours faithfully,

_______________________________

¹/	Applicable to the last five percent (5%) of the  Contract Price only.

Full name and signature of

person authorized to issue

VAT invoice

Received:

_________________________________

Signature of person authorized

to receive VAT invoice

With Copy To:

EXHIBIT C-6 CANCELLATION FEES

The following fees apply to a cancellation following the Preliminary Notice to Proceed and the Notice to Proceed:

| Month following NTP | % | Cumulative % |
| --- | --- | --- |

[Add Notes Relating to prorating the cancellation fee and how month is measure from NTP

EXHIBIT C-7 TAXES AND FEES

Part I.    Contractor Taxes

Contractor shall be responsible for the following taxes:

1.	[ Host Country]  corporate income taxes and taxes on Contractor’s personnel.

2.	Non [Host Country] taxes arising out the performance of the Work.

Part II.   Owner shall be responsible for all [Host Country ] taxes except for those set out in Part I above.

[NOTES:   Following is a non-exclusive listing of taxes that may need to be considered]

(A)	 The following taxes should be excluded from the Contract Price:

-[Host Country] value added taxes

- Import Duties

(B)	Details pertaining to any special tax considerations and  procedures to include Owner responsiblities..

(C)	Add any provisions pertaining to Owner making payment direct to Subcontractors on behalf of Contractor.  {Typically done in South America]

(D)	Add provisions related to CEFTA/NAFTA or other comparable tax exemptions.

(E)	Following is a non exhaustive listing of Taxes that have been found in various jurisdictions. [ List any assumptions related to applicability and rates of taxes]

Income Tax / Surtaxes

Branch Profits / Remittance Taxes

Capital Gains Tax

Withholding Taxes (Dividends; Interest; Royalties; Technical Service Fees, Contractors and Subcontractors, etc.)

Value Added Tax / Sales Taxes

Consumption Taxes

Municipal Taxes

Excise Taxes

Import Duties

Stamp Taxes

Assets Tax / Capital Tax

Superintendency or equivalent Registration Taxes (including taxes on Capital Registration)

Franchise Taxes / Business License Taxes

Property Taxes / Ad Valorem Taxes

Taxes on Movement of Goods (e.g., Indian Octroi)

Wealth Taxes

Taxes resulting from Inflation Accounting

Profit Sharing (not really a tax, but often viewed as such)

Profession Taxes

Works Contract Tax

Water Tax

Other Country-Specific Taxes

EXHIBIT C-9 SUSPENSION COSTS

This Exhibit would apply if Owner issues a PRE-NTP  with the understanding that an NTP will be issued within a range of time after the PRE-NTP and if Owner fails to do so, Contractor will incur material suspension costs, particularly if the PRE-NTP authorizes equipment purchases.  Implementing language will need to be placed in the Contract if this applies.

| At any time during the month following PRE-NTP | % for the Month See Note 1 | Cumulative % |
| --- | --- | --- |
| 1 | 5% |  |
| 2 | 10% |  |
| 3 |  |  |

[

EXHIBIT D FORM OF LIEN WAIVER

[LETTERHEAD OF CONTRACT]

DATE: [to be inserted]

TO:

[Name of Owner]

c/o Enron International

333 Clay Street, Suite 1400

Houston, Texas 77002

Attention: General Counsel

Telefax: (713) 646-7202

With Copy To:

WHEREAS:

1	[____] (“Owner”) and [____] (“Contractor”) have entered into a Contract dated as of [____]  (the “ Contract”), pursuant to which Contractor is to provide design, engineering and procurement services in connection with a [nominal 116 megawatt, combined cycle, cogeneration power plant capable of operating on natural gas with No. 2 diesel as a backup fuel] to be located [____], to be developed on behalf of Owner (as more fully defined in the Contract, the “Facility”).

2.	Section 7.5 of the Supply Contract provides that it is a condition precedent of the obligation of Owner to make each payment under the Supply Contract that Contractor supplies Owner with a waiver and release of liens and security interests to the extent of such payment and Contractor provides this Waiver of Liens in order to satisfy the aforesaid condition precedent in relation to its invoice no. [to be inserted] dated [to be inserted] (the “Invoice”).

NOW THEREFORE:

1.	Capitalized terms used and not defined herein shall have the meaning assigned to them in the Supply Contract.

2.	Upon payment by Owner to Contractor of the sum of [___________], which sum represents the full [undisputed]¹ amount due to Contractor under the Invoice, Contractor irrevocably waives, releases or relinquishes [to the extent of such payment]¹ any lien, security interest or claim (whether for breach of contract, pursuant to applicable Law or otherwise) relating to the Work, the Contractor Equipment, the Facility or the Site arising under or out of or in connection with the Invoice.

3.	Contractor certifies that:

3.1	all amounts that were due and payable in connection with the Work or Equipment have been paid as of the date of payment and as of the last advance applicable to Contractor [save in relation to the amounts of [___________] under Invoice Nos. [__________], which Contractor acknowledges and accepts that Owner was and remains entitled to withhold in accordance with Section 7.4 of the Supply Contract]²;

3.2	it has not directly or indirectly created, incurred, assumed or suffered to be created by it or any Subcontractor, employee, laborer, mechanic, materialman or other supplier of goods or services any Contractor Lien relating to the Work, the Equipment, the Facility, the Site or any part thereof or interest therein;

3.3	it has promptly paid and discharged any Contractor Liens which, notwithstanding paragraph 3.2 hereof it has directly or indirectly created or suffered to be created by it or any Subcontractor, employee, laborer, mechanic, materialman or other supplier of goods or services relating to the Work, the Equipment, the Facility, the Site or any part thereof or interest therein; and

3.4	title to all Work and Equipment is free and clear of any and all liens, claims, charges, security interests, encumbrances and rights of other persons arising as a result of any actions or failure to act of Contractor, its Subcontractors, or their employees or representatives.

IN WITNESS WHEREOF, Contractor has duly executed and acknowledges this Waiver of Liens on the day and year first written above.

By:_______________________

Name:_____________________

Title:______________________

_____________________________

¹To be included if Owner has withheld payment under any previous invoice or under the Invoice

²To be included if owner intends to make partial payment under the Invoice

EXHIBIT E-1GUARANTEES

PART I   Criteria for Substantial Completion and Final Completion

1.0	The following Performance Guarantees and Minimum Performance Guarantees are a criteria for Substantial Completion:

a.	Electrical Output Guarantee

b.	Heat Rate Guarantee

c.	Minimum Performance Electrical Output Guaranteed

d.	Minimum Performance Heat Rate Guarantee

e.	Near Source Sound Level Guarantee

f.	Emissions Guarantee

g.	Reliability Guarantee

[Note:  Modify listing as applicable and match with the listing tests in Part I of  Exhibit E-3

2.0	The following Performance Guarantees and Minimum Performance Guarantees are a criteria for Final Completion

a.	Availability Guarantee

Part II   Performance Guarantees  and Minimum Performance Guarantees

1.0  Reliability Guarantee

As a Specific Performance obligation Contractor guarantees that the Facility will achieve a reliability equal to [ninety percent (90%)] during a Reliability Test (the “Reliability Guarantee”).

2.0 Electric Output Guarantees

Minimum Performance Output Guarantees

As a Minimum Performance obligation, Contractor guarantees that the Adjusted Electrical Output of the Facility when operating on gas, shall be equal to or greater than [ ------------ ] kWh (the “Minimum Performance Output Guarantee”), and

Electrical Output Guarantee

Contractor guarantees that the Adjusted Electrical Output of the Facility when operated on waste coal shall be equal to or greater than [------------ ] kWh (the “Electrical Output Guarantee”)

3.0 Heat Rate Guarantees

Minimum Performance Heat Rate Guarantees

As a Minimum Performance Guarantee obligation, Contractor guarantees that the Adjusted Heat Rate of the Facility when operated on waste coal shall not be more than [ ------------ ] BTU/kWh (LHV/HHV) (the “Minimum Performance Heat Rate Guarantee”).

Heat Rate Guarantees

Contractor guarantees that the Adjusted Heat Rate of the Facility when operated on waste coal shall not be more than [ ------------ ] BTU/kWh (LHV/HHV) (the “Heat Rate Guarantee”).

Near Source Sound Level Guarantee

As a Minimum Performance obligation, Contractor guarantees that the average of the near field A weighted sound power levels of the Facility equipmentshall not exceed [85 dBA] referenced to 20 micropascals (the “Near Source Sound Level Guarantee”).  The Near Source Sound Level Guarantee is limited to normal continuous sound sources within the Facility.

Emissions Guarantee

As a Minimum Performance obligation, Contractor guarantees that the Emissions of the Facility as measured during an Emission Test shall not exceed the following values (the “Emissions Guarantee”):

| Category | Level | Unit of Measure |
| --- | --- | --- |
| Nox |  | Ppmvd @ 15% O2 |
| CO |  | Ppmvd |
| SO2 |  | Lb/hr(max per fuel specification in Base Conditions) |
| PM10 |  | Lb/hr |
| UHC |  | Ppmvw |
| VOC |  | Lb/hr |

Contractor guarantees that the availability of the Facility as measured during an Availability Test shall meet or exceed [ ------------ ] % availability (the “Availability Guarantee”).

EXHIBIT E-2 BASE CONDITIONS

PART 1	OPERATING PARAMETERS

[Following is an example set of Base Conditions to be modified as appropriate]

| Conditions | Standard |
| --- | --- |
| Ambient air temperature | 6º C |
| Relative humidity | 76% |
| Barometric Pressure | 993 millibar |
| Fuel – Natural Gas | See Part II, Below, Expected Values |
| Fuel – Oil | See Part II, Below |
| Fuel Condition (Natural Gas Only) | Min 24 bar g 28º C Superheat @ gas turbines |
| Plant Operating Level | Full Load |
| Export Power Voltage | 110 kV |
| Frequency | 50 Hz. |
| Power Factor | 0.85 Lagging |
| Stack Exhaust Temperature no lower than | 108º C |
| Emissions | In compliance with applicable Law and this Agreement |

EXHIBIT E-2  (Continued)

2.0	FUEL GAS SPECIFICATION

| Fuel Gas Analysis | Parameter | Maximum | Expected |
| --- | --- | --- | --- |
| Minimum | Methane (CH4) % |  | 97.33% |
| 92.0% | Ethane (C2H6) % | 4.0% | 0.81% |
| 0.0 | Propane (C3H8)% | 15% | 0.455 |
| 0.0 | Iso & N-Butane (IC4)% |  | 0.17% |
|  | C4 + paraffins % | 10% |  |
| 0.0 | Pentane (NC5) & higher % |  | 0.09% |
|  | Nitrogen (N2) % | 30% | 0.86% |
| 0.0 | Carbon Dioxide (CO2) % | 15% | 0.28% |
| 0.0 | Carbon Monoxide (CO) % | 15% | 0.0% |
| 0.0 | Hydrogen (H2) % | 10% | 0.0% |
| 0.0 | Oxygen (of) % | 10% | 0.0% |
| 0.0 | Hydrogen Sulfide (H2S) mg/Nm³ | 20.0 | 0.0 |
| 0.0 | Total Sulfur mg Nm³ | 40.0 | 20.0 |
| 0.0 | Calorific Value HHV kJ/Nm³ |  |  |
|  | 40,066 |  | Calorific Value LHV kJ/Nm³ |
|  | 36,132 |  | Specific Gravity |
|  | 0.573 |  |  |

Note:	Nm³ is defined at 0º C and 1.013 bara.

In addition to the above, the fuel gas supply must be in conformance with the technical limits given in Exhibit B, Section 4.1.

Performance Guarantees and Minimum Performance Guarantees relating to NG are based upon a NG fuel consumption as shown in the “Expected” column

[Note: As an alternative to referring to an particular column in the fuel specification range table,  two tables may be used, one for max/min parameters for operational capability and one solely for Base Conditions].

EXHIBIT E-2  (Continued)

3.0	FUEL OIL SPECIFICATION

| Distillate No. 2 Fuel Oil Analysis | Relative Density, @ 20º C |
| --- | --- |
| 0.880 max | Flash Point, º C |
| 56 º C min | Kinematic Viscosity @ 20 º C, mm²/s |
| 4.0 – 8.0 | Fractions |
|  | - distillation up to 250 º C, % (V/V) |
| 65 max | - distillation up to 350 º C, % (V/V) |
| 80 min | Sulfur, % |
| 0.3 % max | Carbon Residue, % (10% Bottoms) |
| 0.25 % max | Ash, % |
| 0.01 % max | Water, % vol |
| 0.1 % max | Filterable Dirt, % |
| 0.05 % max | Calorific Value, MJ/kg |
| 41.5 max (LHV) | Solidification Point, º C |
| -20 º C max | Cprrpsopm Test pm Cu plate @ 100 º C |
| Resistant | Lithium + Sodium + Potassium, ppm max |
| 0.1 ppm | Sodium + Potassium, ppm max |
| 0.1 ppm | Lead + Zinc, ppm max |
| 1.0 ppm | Lead, ppm max |
| 1.0 ppm | Vanadium, ppm max |
| 0.5 ppm | Calcium, ppm max |
| 2.0 ppm | Nickel, ppm max |
| 1.0 ppm | Barium + Manganese + Phosphorus, ppm max |
| 2.0 ppm | Fuel Bound Nitrogen % by Weight |
| 0.015% |  |

EXHIBIT E-3 PERFORMANCE TESTING GUIDELINE

This Exhibit consists of the following major sections:

1.	General Description of Tests

2.	Performance Tests and Availability Test Guidelines

3.	Corrections to Base Conditions and Allowance for Test Tolerance

1.	General Description of Tests

1.1	Tests for Substantial Completion

The following tests  (the “Performance Tests”) shall be conducted prior to Substantial Completion:

Electrical Output Test

Heat Rate Test

Reliability Test

Emissions Test

Sound Level Test

[Steam Output Test] [If applicable]

1.2	Tests for Final Completion

The following tests shall be conducted prior to Final Completion:

Availability Test

Fuel Oil Demonstration Test [If Applicable]

1.3	Detailed Test Procedure Submission.

Contractor will prepare the detailed Performance Test and Availability Test procedures for review and approval by Owner. or which have been determined as applicable in any dispute resolution pursuant to Article 19 of the Contract.

1.4	Purpose of Performance and Availability Tests

The Performance Tests and Availability Test are intended to be conducted by Contractor to demonstrate that the Facility can meet the Performance Guarantee, Minimum Performance Guarantee, Reliability Guarantee and Availability Guarantee obligations of Contractor.

1.5 Test Reports and Review and Approval

Following completion of each Performance Test, Reliability Test and the Availability Test, Contractor will prepare and submit a preliminary test report in an agreed format including the measured and corrected results, a description of the Facility and the test, calculations and instrument calibrations, correction curves, and all test agreements.  The preliminary test report shall contain sufficient detail for Owner to be able to make a reasonable determination of whether the applicable Performance Test indicates that the Facility has achieved the applicable Performance Guarantee/Minimum Performance Guarantee.  Owner shall respond to such preliminary report within three (3) Business Days indicating its concurrence or non-concurrence (with reasonable detail stating the grounds for its non-concurrence) with the findings of the report.  In the event that Owner fails to respond to such report within three (3) Business Days the report shall be deemed to be approved and concurred with.  This preliminary report shall be the basis for the results stated in  Contractor’s Substantial Completion Certificate.

Within forty-five (45) days after the completion of the Performance Test,  Contractor shall submit the final test report to Owner.

For the purposes of the Contract including Exhibits E-1 and E-3 the “Adjusted Heat Rate” and “Adjusted Electrical Output” of the Facility is the Electrical Output and Heat Rate of the Facility as observed during the Performance Test adjusted to Base Conditions and test tolerance in accordance with the detailed performance test procedures which shall be based on the principles set out in Exhibit E-3 including adjustment for test tolerance as described in paragraph 3.0 of this Exhibit E-3.

2.0	Performance Tests and Availability Test Guidelines

The following guidelines are relevant to each of the Performance Tests:

2.1.1	Notification

Contractor shall submit to Owner a written advance notification thirty (30) days, and a written confirmation notification ten (10) days, prior to the anticipated date of the first of the Performance Tests.

2.1.2	Measurements

All test measurements will be taken under steady-state conditions.  Steady-state conditions are assumed to exist when the variation in the Facility output (kW) reaches stability for a period of sixty (60) minutes.  Stability has been reached when the fluctuation in the Facility output is < 2%/hr.

When the following fluctuations are exceeded the test results shall be considered by Owner and  Contractor to determine whether they are acceptable or not.  The term “fluctuation” is intended to mean the difference between the maximum or minimum value of a variable during a single one (1) hour test and the average of the values recorded for that variable during the one (1) hour test.

Maximum fluctuation for the following variables during the Electrical Output Test and during the Heat Rate Test shall be:

Maximum Fluctuation

Ambient air temperature				2 deg C/hr.

Wet Bulb Temperature				2 deg C/hr.

Barometric Pressure				2.0 Millibar/hr.

System frequency				1 %/hr.

Measured load or output in kW			2%/hr.

2.1.3	Conversion Factors

All conversion factors needed will be taken from ASTM E380-93.  The precision of conversion factors will be sufficient not to reduce the accuracy of the converted value to less than the accuracy of the original value.

2.1.4	Steam

The ASME Steam Tables, THERMODYNAMIC AND TRANSPORT PROPERTIES OF STEAM, Calculated Using THE 1967 IFC FORMULATION FOR INDUSTRIAL USE, will be used for the properties of steam and water, when needed.

2.1.5	Personnel

During the Performance Tests and Availability Test the Facility will be operated by Owner or Operator’s personnel under the supervision and control of Contractor.   Contractor will appoint a qualified test director for each Performance Test who shall have authority over the conduct of such test.

2.1.6-	Test Codes

The Electrical Output Test and Heat Rate Test procedures will be based upon ASME PTC 46 and the following guidelines

2.2	Electrical Output Test.

Objective:	To determine the Adjusted Electrical Output of the Facility at Base Conditions while operating on natural gas .

Timing:	The Electrical Output Test shall be conducted prior to Substantial Completion and shall be conducted simultaneously with the Heat Rate Test.

Duration:	The Electrical Output Test will have a six (6) hour duration.  After the initial hour of stable operations, three (3) test runs of one (1) hour each will be conducted.  The test runs will be separated by a nominal hour long period of stable operation.  Data will be recorded no less frequently than at five (5) minute intervals.  The corrected results of the test runs will be averaged to obtain the corrected results to compute the Adjusted Electrical Output value.

Procedures:	Electrical Output for the Facility will be measured at the high voltage side of the main step-up transformers, net of all auxiliary loads required to operate the Facility.  Fuel supplied during the Electrical Output Test will be within the limits of the fuel specification as set out in Exhibit [E-2].

Instrumentation:	Facility instrumentation will be used for the test.  Portable test instruments may also be required for specialized data gathering.

Correction Curves:	Contractor will supply for Owner review and approval correction curves and procedures to be used for analysis of the test run data. Electrical Output will be corrected to Base Conditions for each one (1) hour test run using these correction curves and procedures.  The allowed corrections are for inlet temperature and humidity, atmospheric pressure, fuel supply conditions and composition, thermal export, generator power factor, grid frequency and voltage and firing level difference between test conditions and Base Conditions output.  The calculation procedures will be based on sound engineering and thermodynamic theory and practice.

2.3	Heat Rate Test

Objective:	To determine the Adjusted Heat Rate of the Facility at Base Conditions while operating on natural gas.

Timing:	The Heat Rate Test shall be conducted prior to Substantial Completion and shall be conducted simultaneously with the Electrical Output Test.

Duration:	The Heat Rate Test will have a six (6) hour duration.   After the initial hour of stable operations, three (3) test runs of one (1) hour each will be conducted.  After the initial hour of stable operations, three (3) test runs of one (1) hour each will be conducted.   The test runs will be separated by a nominal hour long period of stable operation.  Data will be recorded no less frequently than at five (5) minute intervals.  The corrected results of the test runs will be averaged to obtain the corrected results to compute the Adjusted Net Heat Rate value.

Procedures:	Electrical Output for the Facility will be measured at the high voltage side of the main step-up transformers, and is net of all auxiliary loads required to operate the Facility.  Fuel consumed during the Heat Rate Test will be measured at the billing meter in the gas metering station.  The Net Heat Rate for each test run will be the ratio of the fuel consumed to the Electrical Output.  Fuel supplied during the Heat Rate Test will be within the limits of the fuel specification as set out in Exhibit B.  Fuel heating value, composition and properties, will be determined by a properly qualified laboratory, mutually agreed to by  Contractor and Owner, using no less than three (3) samples during the test.

Instrumentation:	Facility instrumentation will be used for the test.  Portable test instruments may also be required for specialized data gathering.

Correction Curves:	Contractor will supply for Owner review and approval correction curves and procedures to be used for analysis of the test run data. These correction curves, and procedures will be used to correct each one (1) hour test heat rate to Base Conditions.  The allowed corrections are for inlet temperature and humidity, atmospheric pressure, fuel supply conditions and composition, thermal export, generator power factor, grid frequency and voltage, and firing level differences between test conditions and Base Conditions.  The calculation procedures will be based on sound engineering and thermodynamic theory and practice.

2.4	Reliability Test

Objective:	The objective of the Reliability Test is to demonstrate the reliable operation of the Facility under normal operating conditions (i.e., within permitted Utility dispatch parameters).  Fuel supplied during the Reliability Test will be within the limits of the fuel specification as set out in Exhibit B.

Timing:	The Reliability Test shall be conducted prior to Substantial Completion and may run concurrently with the Electrical Output Test, the Heat Rate Test and the Utility Capacity Test.

Duration:			The Reliability Test will be of a seventy-two (72) hour duration.

Procedures:	(i)	the Reliability Test period will be for seventy-two (72) continuous hours plus any additional consecutive hours added as a result of forced outages not caused by  Contractor or the Facility (such delays shall be the basis for a Change Order to extend the Guaranteed Completion Date).

(ii)	the Facility will respond to the dispatch instructions from Utility within the Technical Limits of the Facility.

(iii)	no nuisance trips will be allowed during all seventy-two (72) hours, (the Reliability Test will be restarted each time a nuisance trip is experienced).  For the purpose of this condition a nuisance trip shall mean a trip caused by something within the Facility or which should be preventable by the Facility protection devices.  Should an outage occur which is not the cause of  Contractor or the Facility, the test will continue when the cause of the outage has been removed.

(iv)	 Contractor will record all outages, identify their causes, recommend corrections and provide such record to Owner within twelve (12) hours of each outage.

(v)	 Contractor shall have the right at any time during the performance of the Reliability Test to stop the test and to restart the test.   Contractor shall notify Owner in writing upon halting the test and of the date on which the test is to be recommenced.   Contractor may immediately recommence the test.

(vi)	The Reliability Test will be deemed successfully completed when the test period has been completed with no trips or outages which are attributable to  Contractor or the Facility.

Instrumentation:		Facility instrumentation will be used for the Reliability Test.

2.5	Emissions Test

Objective:	To determine the NOx emissions of the Facility while operating on natural gas.

Timing:	The Emissions Test will be conducted prior to Substantial Completion.

Procedures:	The test will be performed according to the following [Host Country] standards: [____].

Instrumentation:	Specialized instrumentation will be used for the Emissions Test.  The NOx instrumentation will be limited to a chemiluminescent type which meets the requirements of 40CFR60 Appendix A, Method 7E. The span of the NOx analyzer will be set for the appropriate spread of the expected NOx readings.

2.6	Sound Level Test

Objective:	To determine the sound levels of the Facility in normal operations.

Timing:	The Sound Level Test will be conducted prior to Substantial Completion.

Duration:	Each reading will be taken over a period of at least twenty (20) seconds if there are no large fluctuations in the readings of the meter, or for longer periods until the readings are stable enough.  The reading will be recorded.  If the wind velocity is higher than seven (7) mph at the instrument elevation as measured by a calibrated three-cup anemometer or if precipitation is evident, the taking of readings will be postponed.

	Procedures:	Testing methodology shall be based on the latest version of ANSI/ASME PTC 36.  The final result shall be the arithmetic average of the sound power levels (“SPLs”) (sound power levels) measured around the equipment after background and other corrections have been applied.  The Facility shall be deemed to be in compliance with the Near Source Sound Level Guarantee if the final result (as derived in accordance with the previous sentence) does not exceed the Near Source Sound Level Guarantee.

	All access compartments, doors, panels and other temporary openings shall be fully closed; all silencing hardware shall be fully installed; all systems designed to be airtight shall be sealed.

	The corrections to the measured SPL shall be made per ANSI/ASME PTC 36 procedures.  Background noise is defined as the noise measured with all equipment from the surrounding facilities on and the Facility off.

	Intermittent noises such as steam safety blow off valves and filter pulse noise are not included in the above guarantee.

	Measurements shall be taken 3 feet (1 meter) away from the outermost surfaces of equipment, including piping, conduit, framework, barriers, Equipment enclosures and personnel protection devices if provided.

	Measurements shall not be taken in any location where there is an airflow velocity greater than 5 feet per second (1.5 meters per second), including nearby air intakes or exhausts.

Free field conditions must be prevalent at measurement locations.  Testing and corrections to a free field shall be per ANSI/ASME PTC 36.

2.7        Reliability Test

.

Timing:	The Reliability Test shall be conducted prior to Substantial Completion

Duration:	The Availability Test will have a 72 hour duration test.

Procedures:	[To follow]

2.8	Availability Test

Objective:	To demonstrate the availability of the Facility while operating on natural gas.

Timing:	The Availability Test shall be conducted prior to Final Completion but after Substantial Completion.

Duration:	The Availability Test will have a fifteen (15) continuous day duration.

Procedures:	(i)	During the test period, the Facility electrical output will be in accordance with Utility’s dispatch instructions and system requirements.

(ii)	The Availability Test period will be for fifteen (15) continuous days, including forced outages caused by Utility, Owner, or Force Majeure.

(iii)	After the initiation of the Availability Test,  Contractor may continue conducting such testing as long as Contractor deems it necessary to accumulate sufficient performance data to demonstrate successful completion of the test.   Contractor may restart the test as long as  Contractor deems it necessary to accumulate sufficient performance data.  Contractor may at any time look back over test data to designate which fifteen (15) continuous day period during the duration of the Availability Test shall be used by  Contractor as the contractual fifteen (15) day period required for the Availability Test.

(iv)	 Contractor will record all outages, identify their causes, recommend corrections and provide such record to Owner within twelve (12) hours of each outage.

(v)	 Contractor will record all corrective actions implemented and provide such record to Owner within twelve (12) hours of its completion or corrections.

(vi)	During the Availability Test maintenance may be performed on Facility Equipment at any time.  Such maintenance shall be performed in accordance with manufacturer’s instructions and Good Utility Practice.

(vii)	The Facility shall be operated within the contractual and technical limits during the Availability Test period.

(viii)	 Contractor shall have the right at any time during the performance of the Availability Test to stop the test and to restart the test.   Contractor shall notify Owner in writing upon halting the test and of the date on which the test is to be restarted.

(ix)	For calculating Test Availability, the following definitions will be used:

FLCH =The Facility capacity in MW for hour H if the plant is 100%

operational.

FOCH =Forced Outage Capacity is the unscheduled reduction in capacity in MW in hour H due to Contractor or Facility cause.

SOCH =Scheduled Outage Capacity, is the reduction in MW in hour H due to outage of Facility equipment scheduled by Contractor.

(x)	For the Availability Test period the Test Availability, TA, is calculated by

360

TA = 100 x S	 FLCH - (FOCH + SOCH )

H=l			FLCH

(xi)	The Availability Test will be deemed successfully completed when the Facility responds to the dispatch instructions and electrical demands from Utility for fifteen (15) continuous days; and TA > 95%.

Instrumentation:		Facility instrumentation will be used for the Availability Test.

[2.10	Steam Output Tests

Objective:	To demonstrate the capability of the Facility to deliver total steam requirements independent of capacity and heat rate requirements.

Timing:	The Steam Output Tests shall be conducted prior to Substantial Completion.

Duration:			Duration of the test will be for no less than ten (10) minutes.

Procedures:	(i)	Subject to steam host being capable of receiving full flow of 100 tons/hr., the Facility shall be operated to provide full flow to the interconnection point with the steam host at a temperature and pressure within Steam Sales Agreement contract requirements.

(ii)	Should steam host not be capable of receiving full flow at time of test,  Contractor may deliver a reduced steam flow.   Contractor must simultaneously be producing sufficient steam to have delivered 100 tons/hr.  In this event measurements shall be taken and calculations shall be made to demonstrate that the system is capable of delivering the required capacity within required steam conditions.

(iii)	 Contractor shall separately fire the auxiliary boilers to demonstrate their capability to supply 75 tons/hr. of low pressure steam and 10 tons/hr. of high pressure steam.  Any steam not accepted by the steam host shall be condensed in the steam turbine condenser.]

2.11	Fuel-Oil Demonstration Tests

[If the Facility is dual fuele these tests will be conducted after Final Completion-]

3.0	Correction to Base Conditions and Adjustment for the Allowance for Test Tolerance

3.1	Adjusted Electrical Output and Adjusted Heat Rate.

The observed Electrical Output and observed Heat Rate exhibited during each test or retest will be corrected to Base Conditions The corrections will be based upon the combustion turbine vendor correction curves and detailed correction procedures as set out in the detailed Performance Test procedures. These values will be further adjusted to account for test tolerance where such value shall be equal to test uncertainty as allowed in Paragraph 3.2 below. The resulting values shall be known as the “Adjusted Electrical Output” and “Adjusted Heat Rate” and computed as follows:

Defined Terms:

AEO		=   Adjusted Electrical Output

AHR		=   Adjusted Heat Rate

EOATBC	=   observed electrical output corrected to Base Conditions

HRATBC	=   observed heat rate corrected to Base Conditions

TOL		=   test tolerance expressed in decimal form

Calculation of Adjusted Electrical Output and Adjusted Heat Rate:

AEO		=   (EOATBC)  X  (1  + TOL)

AHR		=     (HRACTBC)  X  ( 1- TOL)

3.2	Instrument Uncertainty and Test Tolerance

Alternative 1

The test tolerance shall be calculated in accordance with the procedures set out in ASME PTC 1, PTC 19.1, PTC 22, PTC 46 and as further set out in the detailed Performance Test procedures

Alternative 2

The test tolerance for  output shall be [xx%]  and [xx%) for heat rate.

EXHIBIT F CHANGE ORDER PRICING

Formula for Calculation of Contract Price Change

Contract Change Orders for all Changes will be priced in accordance with the following formulas:

I.	Engineering/Project Management Costs:

Formula:

Estimated or actual man hours X direct salary costs X 2.2.

Categories (includes but not limited to):

(i)	Contractor in-house engineering to design and review proposed changes;

(ii)	Contractor main office and field project management personnel involvement in preparing, and negotiating necessary changes with subcontractors and vendors; and

(iii)	Contractor engineering and project management personnel involvement in preparation of the change order estimates that are accepted by Owner.

II.	Contractor’s subcontractor/vendor costs:

Formula:	Quoted estimated or actual costs by vendors and contractors X 1.10.

Categories (includes but not limited to):

(i)	Site construction subcontractors; and

(ii)	Contractor  Equipment.

III.	Contractor’s subcontracted engineering:

Formula:	As invoices X 1.05

(i)	Estimate preparation; and

(ii)	preparation of Change Order alternatives and design of accepted Change Order(s).

IV.	Out of pocket costs:

Formula:	Actual costs X 1.05.

(i)	travel;

(ii)	subsistence;

(iii)	unusual postage; and

(iv)	photocopying and printing.

V.	Fee

Formula:	(I + II + III + IV X 0.05

VI.	Total Change Order Costs

Formula:	Sum I through V.

(Note:	Direct salary cost is employee’s gross salary subject to Income tax).

EXHIBIT G-1 PROJECT AGREEMENTS

[OPEN ITEMS][List relevant agreements here, e.g., PPA, etc.]

EXHIBIT G-2 CHANGE IN LAW

[Note: Modify as necessary to match project requirements]

A “Change-in-Law” shall mean:

1.	repeal, amendment, modification or supplementation of any existing Governmental Authorization or Law affecting the Facility, Contractor or any Affiliate of  Contractor in relation to the Facility, or

2.	enactment or making of a new Governmental Authorization or Law affecting the Facility,  Contractor or any Affiliate of  Contractor in relation to the Facility, or

3.	cancellation or non-renewal or a change in the conditions applicable to any Governmental Authorization, or

4.	commencement of any Law affecting the Facility,  Contractor or any Affiliate of  Contractor in relation to the Facility or imposition of a requirement for a Governmental Authorization that has not yet entered into effect or is not required as of the date hereof, or

5.	change in the manner in which a Law or Governmental Authorization is applied to the Facility,  Contractor or any Affiliate of  Contractor in relation to the Facility, or in the application or interpretation thereof, or

6	change in the tax rates relating to the Facility, or a change in the application of such tax rates with respect to the Facility,  Contractor or any Affiliate of  Contractor;

provided, however, that any of the events listed in clauses (1) through (6) occur after the date of this Agreement as a result of, or in connection with, any action or inaction by any Governmental Authority and not as a result of any action or inaction by  Contractor or any Affiliate of  Contractor after [xxx enter date xx typically the date that the Specification is preparedxxx].

.

EXHIBIT G-3 FORCE MAJEURE

[Note: Modify as required to fit project]

“Force Majeure” shall mean any event or circumstance or combination of events or circumstances beyond the reasonable control of a party that materially and adversely affect the performance by that party of its obligations under or pursuant to this Agreement; provided, however, that the material and adverse effect could not have been prevented, overcome, or remedied in whole or in part by the affected party through the exercise of due diligence and expenditure of reasonable sums of money, the expenditure of which, in the case of expenditure by  Contractor, shall be deemed to be included in the  Contract Price.

Subject to the definition and requirements of the general definition of Force Majeure above, the following shall also be Force Majeure:

1.	riot, public disorder, demonstrations, civil commotion and sabotage;

2.	strikes, lockouts, work stoppage, labor disputes and other such actions by workers other than actions arising at the Facility;

3.	expropriation of the Facility or the Site; or

4.	a Change-in-Law or any act or failure to act without justifiable cause on the part of any Governmental Authority that results in an inability to perform under this Agreement.

EXHIBIT H-1  CONTRACTOR INSURANCE

1.	 Contractor’s Insurance.	Prior to the start of the Work,  Contractor will provide a certificate of insurance and thereafter will maintain the following insurance with a [Host Country] insurance company of recognized solvency which is acceptable to Owner.  Said insurance company must be reinsured by reinsurance companies of recognized solvency and reasonably acceptable to Owner.

1.1	Workmen’s Compensation.	 Contractor shall provide Workmen’s Compensation Insurance as required by applicable Law where the Work is performed and Employer’s Liability Insurance with a limit of liability of $1,000,000 for each accident.

1.2	Comprehensive General Liability.	 Contractor shall provide Comprehensive General Liability Insurance on a broad form with a $2,000,000 combined single limit for bodily injury and property damage for each occurrence, including broader Contractual Liability Insurance, broader form property damage, Personal Injury, Products and Completed Operations Insurance for one (1) year after completion of the Work, and coverage for Collapse, Explosion and Underground Hazards or insurance providing substantially similar coverage where all Work is performed.

1.3	Automobile Liability.	 Contractor shall provide Business Auto Liability Insurance covering owned, non-owned and hired automobiles in the amount of $1,000,000 combined single limit for bodily injury and property damage for each accident where any auto is used in performing the Work.

1.4	Excess Liability.	 Contractor shall provide Excess Liability Insurance covering Employer’s Liability, Comprehensive General Liability, and Business Auto Liability to a limit of $10,000,000 combined single limit for bodily injury and property damage where all Work is performed.

1.5	Requirements of  Contractor’s Insurance.	 Contractor shall be responsible for the payment of all deductible amounts with respect to the insurance required to be maintained by it under this Section 1 (such insurance hereinafter referred to as “ Contractor Insurance”) unless such loss is caused in part or in whole by Owner and Owner is, pursuant to Section 18.2, liable with respect to such loss and then in such case Owner shall be responsible for a portion of the deductible that is equal to the portion of the related third-party claim for which Owner is liable pursuant to Section 18.2.  All  Contractor Insurance shall:

(i)	except for Workmen’s Compensation Insurance, specify Owner and Lender as additional insureds;

(ii)	provide that Owner and Lender shall have the right, but not any obligation, to pay premiums if  Contractor shall fail to do so; and

(iii)	waive any right of subrogation against Owner or Lender and waive any other right of the insurers to any offset or counterclaim or any other deduction, whether by attachment or otherwise, in respect of any liability of Utility, Owner or Lender.

1.6	Watercraft.	 Contractor shall ensure that if any owned or non-owned watercraft of any kind is used for performance of the Scope of Work, Hull and Protection and Indemnity insurance shall be provided for the vessels in the amounts as follows:

Hull	Full replacement cost of the watercraft.

P&I	$5,000,000 each occurrence or the full value of the vessel, whichever is greater.

Such insurance may be provided by the watercraft operator, by the watercraft charter agreement, or by  Contractor as  Contractor deems appropriate.

1.7	Aircraft Liability.	If the Scope of Work necessitates the use of aircraft, Aircraft Liability insurance endorsed to provide coverage for non-owned as well as Guest Voluntary Settlement, shall be procured with limits of:

Bodily Injury and $5,000,000 Combined Single Property Damage Limit Each Occurrence.

Such insurance may be provided by the aircraft operator, by the aircraft charter agreement, or by  Contractor as  Contractor deems appropriate.

1.8	 Contractor’s Policies. All policies of insurance required to be maintained by  Contractor under Section 9.1 shall:

(i)	provide a severability of interests or cross liability clause; and

(ii)	include a waiver of subrogation by the insurers in favor of Owner and Lender and each of their respective assignees, affiliates, agents, officers, directors, employees, insurers or policy issuers and a waiver of any right of the insurers to any set-off or counterclaim, whether by endorsement or otherwise, in respect of any type of liability of any of the persons insured under any such policies.

EXHIBIT H-2 OWNER INSURANCE

2.1	Builder’s All Risk.	Owner shall, or shall cause to be purchased and maintained, a Builder’s “All Risk” insurance policy for the Facility covering all work at the Site in connection with the Work and all  Equipment at the Site intended for incorporation in the Facility (including, but only during construction of, temporary buildings, Site huts and offices used for the purpose of the construction of the Facility but not intended for incorporation therein and excluding construction equipment) against the risk of physical loss or damage from whatever cause (including resultant loss or damage arising from faulty materials, workmanship or design), other than risks specifically excluded by the terms of the policy.  Such insurance shall be on a “replacement cost” basis insuring the total cost of the Facility and will also provide:

(i)	coverage for removal of debris;

(ii)	transit coverage, not including ocean marine coverage;

(iii)	off-Site storage coverage;

(iv)	cold and hot (operational) testing coverage; and

(v)	twenty-four (24) months “maintenance period coverage endorsement.”

The deductibles for such insurance if economically available shall not exceed the following:

$100,000 for each and every loss during the defects liability period;

$100,000 for each and every loss in respect of design testing and commissioning; and

$25,000 each and every other loss.

2.2	Marine Cargo Insurance.	Owner shall or shall cause to be purchased and maintained, Marine Cargo Insurance on a “warehouse to warehouse” basis insuring the Equipment against loss or damage arising from customary “all risk” marine perils (including war, strikes, riots and civil commotion, if available) while in transit.  Such policy limit shall be equal to one hundred ten percent (110%) of the cost (including cost of freight and insurance) of the largest single shipment.  The deductibles under such insurance shall be $25,000 for each and every loss.

2.3	Comprehensive General Liability.	Owner shall, or shall cause to be purchased and maintained, Comprehensive General Liability Insurance on a broad form with a $5,000,000 combined single limit for bodily injury and/or property damage for each occurrence, including Contractual Liability Insurance, Personal Injury, Products and Completed Operations Insurance for one (1) year after completion of the Work, and coverage for Collapse, Explosion and Underground Hazards or insurance providing substantially similar coverage where all Work is performed.  Such insurance shall be primary for:

(i)	activities at the Site including coverage for Owner,  Contractor and  Subcontractors; and

(ii)	performance of Work activities off-Site including coverage for Owner,  Contractor and its first tier Subcontractor but not extending to any second or lower tier Subcontractor.

The deductible for such insurance if economically available shall not exceed $10,000 for each and every loss in respect of property damage only.

2.4	Permanent Property Insurance.  Upon Substantial Completion of the Facility and until such time as  Contractor has completed its warranty obligations under this Agreement, Owner shall procure and maintain “all risk” property insurance (including boiler and machinery insurance) subject to normal policy exclusions for the Facility at full replacement value with a deductible of no more than $2,000,000 (or less if commercially available on reasonable terms) for property, and $250,000 for boiler and machinery.

3.	Excess Liability.  Excess liability on a “following form” basis covering claims in excess of and following the terms of the underlying insurance set forth in Section 2.3 of this Exhibit H-2 with a $20,000,000 minimum limit.

3.1	Owner’s Policies.  Subject to Section 3.2 of this Exhibit H-2:

3.1.1	The insurance policies required to be maintained by Owner under Sections 2.1 to 2.3 of this Exhibit H-2 shall:

(i)	provide for a waiver of subrogation in favor of  Contractor, its agents, officers and employees which do not extend beyond the time necessary for  Contractor to fulfill its warranty obligations under Article 12; and

(ii)	include  Contractor and its Subcontractors as additional insureds for their respective interests.

3.1.2	The insurance policy required to be maintained by Owner under Section 2.4 of this Exhibit H-2 shall:

(i)	provide for a waiver of subrogation in favour of  Contractor, its agents, officers and employees only for the time periods that  Contractor is on Site performing its obligations under Article 12; and

(ii)	include  Contractor as an additional insured for its respective interest only for the time necessary for  Contractor to fulfil its warranty obligations under Article 12.

3.1.3	The Delay in Start-Up and Business Interruption insurance (if any) obtained by Owner shall provide for a waiver of subrogation in favor of  Contractor, its agents, officers and employees in respect of any delay in start-up or business interruption attributable to  Contractor, its agents, officers and employees.

3.2	Limitation.

3.2.1	In the event that  Contractor breaches its obligations under the first two sentences of Section 9.5.4 and such breach results in an insurer avoiding in relation to  Contractor any policy of insurance referred to in Section 9.2, any Delay in Start-Up and/or any Business Interruption insurance obtained by Owner,  Contractor shall not be regarded as an additional insured under such policy and any waiver of subrogation in favor of  Contractor included in that policy pursuant to Section 3.1 of this Exhibit H-2 shall not apply.

3.2.2	In the event that any Subcontractor fails to comply with the procedures for claims notification and administration under any policy of insurance referred to in Section 9.2, any Delay in Start-Up and/or any Business Interruption insurance obtained by Owner or does anything which might render any such policy of insurance voidable or entitle insurers to avoid liability thereunder and as a result thereof an insurer avoids in relation to that Subcontractor any such policy of insurance, that Subcontractor shall not be regarded as an additional insured under such policy and any waiver of subrogation in favor of that Subcontractor included in that policy pursuant to Section 3.1 of this Exhibit H-2 shall not apply.

3.3	Primary Insurance.  All policies of insurance referred to in this Exhibit H-2 shall be endorsed to specify that for activities at the Site, they are primary to and not excess to or on a contributing basis with any insurance or self-insurance maintained by Owner, Lender, Utility,  Contractor (and its affiliate) or any Subcontractors in respect of losses arising out of or in connection with the Works at the Site.  Subject to Section 2.3 of this Exhibit H-2,  Contractor’s insurance under Exhibit H-1 shall be primary for losses away from the Site.

4.	Cooperation.  Owner shall provide copies of the draft Builder’s “All Risk”, Marine Cargo and general liability insurance policies to  Contractor for review and comment.  Final decisions on each of the coverage terms shall rest with Owner.

5.	Placement of Insurance  [Add language relating to when the Owner CGL, BAR and Marine Cargo insurance must be in place.

EXHIBIT I SITE LOCATION MAP

EXHIBIT J-1 SAMPLE SUBSTANTIAL COMPLETION CERTIFICATE

CERTIFICATE OF SUBSTANTIAL COMPLETION

This officer’s certificate is delivered pursuant to that certain Contract dated as of ____________, between _______________ (“Owner”) and __________________ (“ Contractor”) (the “ Contract”) and all capitalized terms used in this certificate have the meaning given to such term in the  Contract.

By this certificate I, [Name of officer], the duly appointed and acting [title] of  Contractor hereby certify that:

(a)	the Facility is substantially complete in accordance with the Scope of Work, the Specifications and all applicable Governmental Authorizations and permits and can be safely operated for its purpose;

(b)	all Work required to be furnished by  Contractor for the Facility is substantially complete and all Equipment has been delivered to the Site and properly incorporated into the Facility, except for Punchlist Items;

(c)	the Performance Tests required for Substantial Completion as specified in Exhibit E-3 have been successfully completed and a certificate of the results has been received by Owner;

(d)	any Delay Liquidated Damages due have been paid;

(e)	a Punchlist has been received and accepted by Owner;

(f)	 Contractor has sufficiently completed the Work to allow Owner to enter into commercial operation under the relevant Project Agreements;

(h)	Mechanical Completion has been achieved

(i)	the Facility has met the Performance Guarantees which are listed in Part I of Exhibit E-1 as a criteria for Substantial Completion or Contractor has either paid any Performance Liquidated Damages due or has posted bond securing such amount; and

(j)	The Facility has met the Minimum Performance Guarantees which are listed in Part I of Exhibit E-1 as a criteria for Substantial Completion

IN WITNESS WHEREOF, the undersigned has signed as of the [__] day of [______], [__].

[ Contractor ]

By:_________________________

Name:______________________

Title:________________________

Acknowledged and agreed as of the date set forth above.

[Owner]

By:____________________

Name:__________________

Title:____________________

EXHIBIT J-2 SAMPLE FINAL COMPLETION CERTIFICATE

CERTIFICATE OF FINAL COMPLETION

This officer’s certificate is delivered pursuant to that certain Contract dated as of ____________, between _________ (“Owner”) and ____________ (“ Contractor”) (the “ Contract”) and all capitalized terms used in this certificate have the meaning given to such term in the  Contract.

By this certificate I, [Name of officer], the duly appointed and acting [title] of  Contractor hereby certify that:

a.	Substantial Completion has occurred and all Punchlist Items have been completed;

b.	the Availability Test has been successfully completed and a certificate of the results has been received by Owner;

c.	Contractor’s obligations under Section 3.7 and Article 10 have been completed;

d.	Contractor has provided the waiver and release required pursuant to Section 7.5; and

e.	Contractor has met all its obligations under this Agreement other than the warranty obligations under Article 12 and any obligations that survive the termination of this Agreement.

f.	the Facility has met the Performance Guarantees which are listed in Part I of Exhibit E-1 as a criteria for Final Completion or Contractor has either paid any Performance Liquidated Damages due or has posted bond securing such amount.

g.	The Facility has met the Minimum Performance Guarantees which are listed in Part I of Exhibit E-1 as a criteria for Final Completion.

IN WITNESS WHEREOF, the undersigned has signed as of the [___] day of [_______], [__].

Contractor

By:_______________________

Name:___________________________

Title:____________________________

Acknowledged and agreed as of the date set forth above

Owner

By:_______________________

Name:_____________________

Title:_______________________

EXHIBIT K GOVERNMENTAL AUTHORIZATIONS

[Note This Exhibit will contain a listing of permits to be obtained by Contractor and Owner, either in separate listing or in a responsibility table as show below]

| Governmental Authorization | Party Responsible for Preparation | Party Responsible for Submission and Obtaining |
| --- | --- | --- |
| Site Development Ruling (obtained) | Owner | Owner |
| Building Design Document | Contractor | Owner |
| Environmental Impact Assessment (obtained) | Owner | Owner |
| Permits for use | Contractor | Contractor |
| Power Generation License | Owner | Owner |
| Deforestation and Class Change Permit for Classified Forest Land | Owner | Owner |
| Deforestation Permit for Classified Construction Land | Civils Contractor | Civils Contractor |
| Transmission Line Site Development Ruling | Owner | Owner |
| Transmission Line Construction Permit | Contractor | Owner |
| Equipment Certification | Contractor | Contractor |
| Other Approvals that may be required for execution of construction works |  |  |

EXHIBIT L MAJOR SUBCONTRACTS

[Note: The Scopes of Work to be considered as Major Subcontract are comparable to those listed below.  For each contract category, multiple approved subcontractors may be listed]

|  | CONTRACT | APPROVED SUBCONTRACTOR |
| --- | --- | --- |
| 1. | Combustion Turbine Vendor |  |
| 2. | HRSG Vendor |  |
| 3. | Substation Vendor |  |
| 4. | Plant Electrical Installation |  |
| 5. | HRSG Erection |  |
| 6. | Cooling Tower Vendor |  |
| 7. | Steam Turbine Vendor |  |
| 8. | Main Step Transformers |  |
| 9 | DCS system |  |
| 10. | Condensers |  |

EXHIBIT M OWNER SCOPE OF SUPPLY INCLUDING CONSUMABLES, UTILITIES AND INTERCONNECTIONS

[NOTE: This Exhibit is intended to list Owner’s scope of supply.  Following listing is provided for illustration purposes]

1.	Owner shall provide access for construction purposes to the utilities and services listed below and shall pay for the utilities and services consumed for such purposes.  The  Contractor will be responsible for the cost of distributing utilities and services on, and in the vicinity of, the Site.

1.1	Raw Water

Date

Capacity		XX cubic meters/hour		NTP Effective Date +XX days

Pressure		X bara

Supply Point		At tie-in point on [____] raw water main as illustrated in Figure 1.

1.2	Electrical Power

Capacity		XXX kW			NTP Effective Date

Voltage			6kV, 3 phase, 50 hz.

Supply Point		Low side of transformer located in existing [____] substation.

1.3	Potable Water

Capacity		XX cubic meters/day		NTP Effective Date

Pressure		X bara

Supply Point	At tie-in point on [____] potable water main as illustrated on Figure 1.

1.4	Communications

Capacity		XX telephone lines at NTP Effective Date

Supply Point		Termination point on site

boundary as indicated on

Figure 1.

1.5	Waste Disposal

1.5.1	Contaminated Water

Capacity		XX cubic meters/day		NTP Effective Date

Discharge Point	At [____] waste water main.

Pressure Required	X bara

(Alternate:	 Contractor may collect and transport wastewater to treatment

facility.)

1.5.2	Biological Waste

Contractor to collect and transport to treatment facility.

1.5.3	Uncontaminated runoff

May be discharged to natural drainage, however,  Contractor must make provisions to control solids content.

2.	In addition to the above construction services, Owner shall provide to Contractor the following services, consumables and utilities for purposes of start-up, commissioning and testing.

2.1	Start-up and commissioning power from the grid, supplied through facilities that are provided by  Contractor as part of the Work. Such power will be made available by Owner thirty (30) days prior to start of the first gas turbine, provided that  Contractor has provided Owner with a ninety day advance notice of the start-up date.

2.2	Transmission line connection to the grid at least five (X) months prior to the Guaranteed Completion Date.

2.3	Owner will arrange for others to accept power generated during start-up and commissioning activities, provided  Contractor has given Owner required notice of the schedule and quantities of power to be generated. Any payments by others for power delivered will be to the benefit of Owner.

2.4	All fuel necessary for operation of gas turbine, auxiliary boilers, HRSG duct burners or emergency generation equipment for the purposes of start-up, commissioning or testing of the equipment or the Facility.

2.5	The  Contractor will provide first fill of all chemicals and lubricants necessary to operate the plant. The Owner will make available adequate stocks of chemicals and lubricants to replenish those consumed during start-up, commissioning and testing of the Facility at least thirty (30) days prior to start of those activities, provided that  Contractor has given Owner an estimate of the quantities of chemicals and lubricants required at least sixty (60) days prior to beginning of start-up, commissioning and testing activities.

2.6	Project insurance in accordance with Exhibit H-2.

EXHIBIT N SPECIAL TOOLS AND OPERATING SPARE PARTS

Contractor shall support and assist in the procurement of spare parts and any special tools required for the operation and maintenance of the Facility.  Contractor shall assist and support Owner with the negotiation of long term agreements for the procurement of maintenance, spare parts and special tools concurrently with placing the related  Equipment orders by  Contractor.  Upon delivery of any spare parts and special tools to the Site,  Contractor shall make storage on the Site available to Owner.

EXHIBIT O OPERATION AND MAINTENANCE TRAINING

1.1	 Contractor shall conduct the following training, at  Contractor’s own expense:

(a)	fundamental plant specific training prior to start-up and commissioning intended to familiarize qualified, experienced operators with the new Facility;

(b)	detailed hands-on training on-Site during start-up and commissioning as described in paragraph 1.6 below; and

(c)	vendor orientation training on the combustion turbines, the steam turbines, and the heat recovery steam generators and other key Facility systems for Owner’s operators prior to start-up and commissioning

as follows:

I	Two (2) on-Site training courses on plant design and overall operation, maintenance and safety concepts, duration of each course to be three (3) consecutive working days, to be performed prior to commissioning, testing and reliability run, for a total maximum of thirty-four (34) participants.

II	Two (2) training courses on MS6001 gas turbine operation and routine maintenance, duration of each course five (5) consecutive working days for a total maximum of thirty-four (34) participants.  Location on-Site.

III	One (1) training course on the gas turbine and steam turbine control (Speedtronic Mark V), duration of the course four (4) consecutive working days for a maximum of ten (10) participants.	Location:

IV	Two (2) training courses on GE steam turbine operation and routine maintenance, duration of each course five (5) consecutive working days for a maximum total of thirty-four (34) participants.  Location on-Site.

V	One (1) operator’s training course on the DCS system, duration of the course three (3) consecutive working days for a maximum of ten (10) participants.  Location on-Site.

VI	One (1) maintenance training course on the DCS system, duration of the course five (5) consecutive working days for a maximum of five (5) participants.  Location:

VII	 Contractor shall provide hands-on, on-the-job (“OTJ”) training for the plant staff during actual Equipment start-up and commissioning.  OTJ training shall be an additional job requirement of  Contractor’s personnel who commissioning. The overall purpose of OTJ training provided by the proposal will be to ensure that the plant staff is thoroughly familiar with the steps of the start-up, normal operation, routine shutdown and emergency shutdown of all Equipment.  Contractor will use a “check off” system to document that individual members of the plant staff have successfully completed OTJ training on each piece of Equipment in their area of responsibility.  Duration: During the period of start-up and commissioning.  Number of participants: Thirty-four (34).  Location: On-Site.

1.2	Operator Qualifications

For avoidance of doubt, Owner shall be responsible for:

(x)	ensuring that operators have sufficient qualifications and training such that they can safely operate similar equipment prior to attending  Contractor’s training; and

(y)	conducting any general equipment training and providing translators.

1.3	The following pertains to the training program to be provided by  Contractor:

-	all written training materials will be provided in [Host Country] except for drawings that have been prepared in English along with various vendor documentation.

-	all travel costs and temporary expenses (lodging, meals, etc.) for instructors and training personnel shall be  Contractor’s expense.

-	all hand-out training aids, manuals and materials will become the property of Owner after completion of the training program.

-	 Contractor shall prepare training records on each individual documenting the successful completion of each course of instruction.

-	 Contractor shall prepare and implement testing and performance measurement systems designed to ensure that the plant staff is proficient in the operation and maintenance of the Equipment before plant start-up.

-	Instruction shall include knowledge of the normal operating parameters for each piece of Equipment as well as knowledge of how to avoid conditions that might cause equipment damage or unsafe conditions.

-	 Contractor shall prepare schedule by week that includes the estimated duration for each of the following training program activities: development/initial preparation of the training program; review period by Manager; final preparation of lesson plans, training materials and manuals; and conduct of the training program at the Site.   Contractor shall provide the following information on each course of instruction:

-	Course Title/Subject

-	Attendees: operators, mechanics, I&E technicians, etc.

-	Course outline (short description)

-	Course duration (hours or days).

1.4	Optional Training.	In addition to the training courses set out in paragraph 1.1 above,  Contractor shall provide a list of Optional Training available either at the Site or at  Contractor’s facilities, with a “per course, per student” price or each optional course of instruction.  As an example, Optional Training might include specialized training for instrument engineers at  Contractor’s factory.

1.5	Training Manuals.	The content and extent of the training manuals shall be sufficient to permit the conduct of the training to be performed on-Site to enable Owner’s personnel to operate the Facility and undertake all necessary maintenance of the Facility.  Part of this training will be performed as OTJ training.

Thirty-four (34) sets of training manuals are to be provided one (1) month prior to the start of training.

1.6	Language.

a.	All on-Site training shall be conducted in the [____] language by  Contractor without the use of translators, except in the case of controls training, which will be conducted in English.

b.	All training conducted by Contractor or its vendors at [____] or other factory locations shall be conducted in English, and Contractor or its vendor will provide a qualified technical translator to translate the information into [Host Country].

EXHIBIT Q IMPORTATION OF EQUIPMENT

Owner shall be available for the fulfilment of reasonable signature requirements at the Port of Import for the Equipment in accordance with [Host Country]’s customs clearance procedures.   Contractor shall provide such procedural requirements to Owner no later than fifteen (15) days prior to the scheduled departure of the first shipment of Equipment and reasonable advance notification of  Contractor’s requirement for Owner’s assistance for each shipment.

Owner shall expeditiously prepare and execute or cause to be prepared and executed, any papers, that cannot be prepared or executed by  Contractor and are necessary to import any Equipment.

EXHIBIT R CONTENTS OF JOB BOOKS

Job Books shall include the following:

1.	Engineering Design:

Process Flow diagrams

P & IDs

Plot Plan

Equipment Location Plan

Underground Piping Plans

Electrical One-line Diagrams

Cable and Raceway Schedule*

Connection Report/Loop Diagrams*

Relief Valve List

Drawing Index

Reference Index

Survey Bench Marks

Line List

Equipment Data Sheets

* This information will not be provided in Job Book format; it will be provided in form and format available as a result of the design and construction process.

2.	Purchasing and Vendor Supplied Information:

One copy of all purchase orders of major Equipment (non-priced) with addenda.  Vendor information for Equipment purchased including:

Perform curves

P & IDs

Piping and electrical detail drawings where applicable

Recommendations for spare parts

Vendor operating and maintenance information/manuals

Material and fabrication certification as applicable

Installation instructions

Guarantee information

Equipment List

Line List

Project Equipment and Purchase Specifications

3.	One copy of record drawings (as-built or field-annotated, “red-lined,” issued for construction drawings) containing the following information:

Underground utilities, piping and foundations

P & IDs

PFDs

Plot Plan

Elementary Electrical Drawings

4.	Where any of the above information was produced on computer aided design and is available to  Contractor,  Contractor shall provide to Owner a disk copy of such information.  Electronic copies shall be compatible with AutoCAD Release 13, Microsoft Word Version 6.0a, and Microsoft Excel Version 5.0a or latest version.

EXHIBIT R-1 DOCUMENTS FOR REVIEW

The following documents shall be submitted to Owner for review and comment in accordance with Section 3.3.1 and Section 3.3.2.

EXHIBIT S LIST OF KEY PERSONNEL

Project Manager

Contractor shall appoint a Person as  Contractor’s project manager for the Work.  Such Person shall have full authority to act on behalf of  Contractor for all purposes in connection with this Agreement and  Contractor shall notify Owner of the normal workplace(s) of the Person who holds such post.  The project manager shall not be engaged in any project other than the Work and shall give substantially the whole of his or her time to the superintendence of the Work.

Site Manager

Contractor shall appoint a Person as the site manager.  Such Person shall be employed at the Site from the commencement of Work on the Site until Substantial Completion to supervise all work done on the Site and to receive all instructions related to Site activities given by or on behalf of Owner.  The site manager so appointed shall be present at the Site throughout normal working hours except when on leave, sick or absent for reasons connected with the proper performance of the Work.

Project Engineering Manager

Contractor shall appoint a Person as the project engineering manager.  Such Person shall be employed by Contractor from the commencement of Work until Substantial Completion to supervise all engineering and design activities and to receive all instructions related to such activities on behalf of Owner.  The project engineering manager shall not be engaged in any project other than the Work and shall give substantially the whole of his or her time to the engineering and design activities of the Work.