Statement of Work

EGM ExtraNet

On behalf of:

EGM Mid-Markets

This document is published by:

Enron Corp.
1400 Smith Street
Houston, TX 77002

The contents of this guide are the property of Enron Corp. The distribution of this material is intended for Enron Corp. employees. Distribution by any method to any other party is prohibited without the prior consent of Enron Corp. This guide may not be copied, photocopied, reproduced, translated, or reduced to any electronic medium without the prior written consent of Enron Corp.

Due to the dynamic nature of internal applications development that supports innovative business processes, Enron Corp. does not warrant that all information contained in this guide accurately reflects the current state of the application’s functionality and/or appearance.

© 2001 Enron Corp.
All rights reserved.

Contents

Revision History	4

Introduction	5

Document Purpose	5

Document Scope	5

Stakeholders	5

Executive Summary	6

Current Business Environment	7

Proposed Business Environment	8

Project Scope	9

In Scope	9

Not In Scope	9

Benefits	10

Risks	11

Project Schedule Risks	11

Project Functionality Risks	11

Assumptions	12

Constraints	13

Alternatives Considered	14

Alternative 1	14

Project Structure	15

Resources / Timeline	16

Resources	16

Estimated Timeline	16

Project Definition Number Request Form	17

Project Information	17

Estimated Costs	17

WBS Components Needed	17

Approval & Sign-off	18

Project Number Assignment	18

# Revision History

| Rev # | Name | Date | Description of Changes |
| --- | --- | --- | --- |
| 1 | Bogdan Cirlig | October 1, 2001 | Original documentation |
| 2 | Bogdan Cirlig | October 2, 2001 | Added Firewall risks in Risks table, moved user personalization to “Not in scope” section. Extended “Not in scope” with Wei’s suggestions. |
| 3 | Wei H Tai | October 10, 2001 | Updated scope changes, current business environment, proposed business environment and estimated budget and timelines. |

# Introduction

## Document Purpose

The purpose of this Statement of Work document is to provide enough detail about the scope and estimated costs associated with a project in order for the prospective Business Sponsor to make a go/no-go decision on whether to proceed with the project.  While preparing this document, project costs will be charged to the Statement of Work project definition numbers provided in the Project Charter.

## Document Scope

The scope of this document includes a description of the current business environment, proposed business environment and the scope of the project that will get the business from one to the other.  Associated benefits, risks, estimated costs and prospective project timeline are also included.  Sufficient information must be included to accomplish the purpose of the document.

## Stakeholders

|  | Name | Title |
| --- | --- | --- |
| Business |  |  |
| Business Sponsor | Bill Berkeland |  |
| IT |  |  |
| IT Sponsor | Iain Greg |  |

# Executive Summary

# EGM Mid-Markets would like to have an ExtraNet web based services that will be used as marketing tool. Its main purpose is to attract new external customers as well as retain current external customers.

# These services will enable external clients to get access to over 20 Enron In-house Reports from the EGM Fundamentals Crude Intranet, third party reports, Historical Pricing Charts and Pricing tools used by clients to predict the forward prices on a specific product.

The need for these ExtraNet services is crucial as current competitors such as Morgan Stanley, Goldman Sachs and BP all have similar products. In order for Enron to retain the related customer base and get new customers these services have to be available as a part of a complete solution, one stop shop, for the client.

# Current Business Environment

Currently, the EGM Mid-Markets group provides crude and products related information to its external clients by weekly newsletters and daily pricing sheets.  As its customer base grows, developing long-term sustaining client relationships is important.  A web based information portal provides a powerful marketing tool in attempting to secure and maintain relationships with the clients.  Customers need to have access to information that affects how they do business.  By developing a tool to aid in obtaining key market information, this will allow them to be more informed and as well aid Enron with improving client loyalty and sophistication.  This site will provide important market-affecting information currently un-aggregated or unknown to clients.

With the development of the extranet, clients of Enron Mid-Markets will be able to obtain up-to-date information pertaining to crude and products as well as receiving information on many other products and services offered by Enron.  Developing an extranet portal will provide Enron the opportunity to develop an “information sharing” atmosphere with clients while simultaneously educating them as well.  Through the development of creating more market savvy clients, we expect to improve the sophistication and volume of our transactions with these clients.  Also, the website portal can be used as an avenue to demonstrate the level of commitment of superior customer service—thus cultivating loyalty to Enron’s services.  If the customer comes to rely upon us, they are more likely to initiate new contracts with Enron, and less likely to abort old ones.

# Proposed Business Environment

In the proposed business process, the creation of the ExtraNet services will provide access to various in-house as well as third party reports, historical pricing charts and pricing tools (such as forecasting) in one centralized location for clients of Enron.  The structure of the website will provide users the option of viewing analyst reports, weekly update reports, newsletters, a business overview of a particular area (i.e. weather data, pricing data) and other information as well.

The main driver for the development of the website portal is to foster communication between Enron and clients.  In so doing, this will improve client loyalty to Enron while simultaneously creating more sophisticated clients.

# Project Scope

## In Scope

This section should include a description of the chosen alternative that will take the business from the Current Business Environment to the Proposed Business Environment.  Other alternatives that may have been considered will be listed in the Alternatives section below.  It should include what is included within the scope of the project (i.e. New Hardware if required, user manuals, user training if included, etc.).

The EGM ExtraNet will house information on:

- In-house Reports (not available until after 8:50AM)

  - Daily

    - Global Weather Report

    - Inter Market Spreads

    - OPEC Basket Price

    - Refining Margins

    - World Refinery Outages

  - Weekly

    - Critical Mass

    - The Week Ahead (a different version than on Intranet)

    - Investment Banking Summary

    - DOE Numbers

    - DOE Report

    - Refinery Utilization Report

  - Monthly

    - Forward Commodities Report

    - Jet Consumption Monthly

    - Euroilstock Inventory Report

  - Other reports

    - Future Switching Report

    - API Report

- Third Party reports

- Historical Pricing Charts

  - Will contain limited listing of indexes

  - Will contain the following price series

    - Outright price series

    - Spread price series

In order for EGM ExtraNet to fulfill the needs of the users, it must:

- Be secure and password protected and provide an Admin tool for managing the user accounts and user rights

- Provide users with a self-registration tool and ExtraNet email messaging (i.e. new user account confirmation, etc)

- Provide the ability for users to view various in-house and third party reports, historical pricing charts and forward pricing information.

- Provide the ability for content to be maintainable and changeable without the need for excessive site development or maintenance resource

- Provide multiple admin defined security levels for users (tier I/ II)

- Provide a high level of scalability to handle future needs

- Provide general site statistical information (Monthly Web Trends Report)

Phase 2 of EGM ExtraNet Project should include:

- Pricing Tools: based on forward price curves the users will be able to predict the forward prices of the product X

- Provide Personalization Services (such as user defaults)

## Not In Scope

- Option to users to have preferred charts emailed on a daily basis or when the data updates. This offers the users the convenience to have nice HTML charts first thing in the morning. It also offers the advantage of having the data through email in case the Internet website is not accessible but the email is still working.

- Subscription to publications

- Navigation admin tool

- Content admin tool

- Reporting of specific user information (user tracking, etc)

- No charge (fee) for membership

# Benefits

With the proposed creation of the EGM ExtraNet, there are several benefits for clients of Enron and analysts who maintain the accounts here at Enron.   Some of the benefits include:

- Increase communication between Enron and its client base

- Centralize information into one convenient site for client base (One stop shop)

- Increase customers reliance and dependability on website due to pertinent information affecting their industry and company

- Utilization of ExtraNet services as a learning center to increase customer sophistication, business knowledge and efficiency.

- Promote Enron products & services

- Maintain and emphasize superiority over Enron competitors

- Improve customer loyalty

# Risks

## Risk

| Risk | Risk Magnitude | Risk Description | Impacts of Risk | Mitigation/Contingency |
| --- | --- | --- | --- | --- |
| Scope Creep | Low | The project has the ability to grow in scope because of the limited amount of requirements discussed initially. | Cost of project increases | Manage requirements effectively |
|  |  |  | Deadline extended |  |
| Information Corruption | Medium | Information posted onto website is incorrect or invalid. | Clients rely upon false information, believing it to be backed by Enron | An Administrator should regularly verify new information for veracity. |
|  |  |  | Damaged customer relations | Provide legal disclaimers to inform the client |
| Website is not maintained or updated frequently | Medium | Information housed on the website is not updated frequently | The goals will be defeated, as clients will have no incentive to use the site | Project manager should stress the importance of updating website frequently to website administrators. |
| Budget Exceeded or Cut | Low | If funding is exceeded or lost, it may become difficult to complete the project. | Clients of Enron may be forced to turn to Enron competitors to get these services. | Project manager will need to work to control costs. If budget cuts are requested, business users must protect the project. |
|  |  |  | Lack of knowledge sharing business users |  |
| Website is unstable | Medium | The extranet services is not accessible by clients. | Clients would get the information from third parties or competitors. | Conduct stringent testing on extranet site. Develop a contingency plan or alternative method for users to communicate with Enron when website is not available such as reports by email. |
| Usability of website | Medium | Information housed onto website does not present any value to customers. | Customers will not utilize website | Evaluate all information prior to posting onto website. All information should go through an approval process. |
| Cost of publication subscription | Medium | Ongoing cost of maintaining publication subscription to the desired publications housed portal | Increased maintenance costs | If users do not want to maintain subscription, then the publications should not be available in the portal |
| Firewall security | Low | WebOps might not agree to open a port through firewall for COM calls originating from the webserver. | Use SOAP which is at least 300 times slower. At a load of 100 concurrent users the delay using COM is 100ms and using SOAP is 10 seconds. | WebOps should seriously think about it since COM is a very mature platform and a standard for today web applications. Their decision will affect any ExtraNet application. |
| MCS | Medium | MCS is under development | Any delay of the MCS project may affect this project. | The reports update will be done manually by WebOps with the request by EGM IT. |

# Assumptions

This section should contain a listing of the major assumptions made in selecting the proposed solution.  This should include things like hardware availability, personnel skill-sets, training requirements, personnel availability, schedule flexibility, etc.  Anything that may affect the project that has been ‘assumed’ to happen should be listed here.

- EGM Website will have secured access to the information using registered user accounts. In other words,  the services are not publicly accessible. The only interfaces made available for everyone in the Internet would be a general site descriptions, site services and user self-registration.

- The EGM ExtraNet project will be implemented in phases

  - Phase 1 of the project will focus on implementing the user interface and providing the website skeleton functionality as well as:

    - User admin tools (security groups, information access rights, user management)

    - Publication links management (to in-house reports and third party reports, i.e. path to the IIS virtual share for each publication, associations between publication name and the file name on disk, etc)

    - Historical Pricing Charts

  - Phase 2 of the project will focus on Pricing tools that will provide forecast abilities for customers (Enron prices)

- Regarding the security, the login phase could use SSL certificates available on ExtraNet webservers. There is a firewall issue regarding passing COM calls through the firewall to another COM. An alternative is to use SOAP but is extremely slow.

- As there is no COM+ object to extract the data from MKM this has to be developed. It is imperative to have a multithreaded access to MKM for scalability issues and faster response time.

- Regarding the server-side hardware issues, the EGM ExtraNet is a client application of MKM. MKM information processing will be accomplished by EGM ExtraNet. The MKM offers the data in a non-aggregated format. The aggregation is to be done by the EGM ExtraNet. The amount of computing power is yet TDB.

- Regarding the client-side hardware issues, they have to be able to run Java Applets (default option with any browser). The complexity of the Java Charts can be carried out by most of nowadays desktops without any issues. The minimal workstation configuration should be: PC IBM compatible, Pentium II Processor at 166 Mhz, 64 MB RAM, no restrictions regarding the operating system, Microsoft Internet Explorer 3.01 or higher, Netscape Navigator 3.0 or higher or Opera Browser version 3.0 or higher. Since the JetChart is a Java Applet it is compatible with any Java Virtual Machine implemented by various OS vendors including Microsoft, Sun, IBM and RedHat Linux.

- MCS will provide the actual publications to a dFS share which will be mapped to IIS webserver as a virtual path.

# Constraints

- Data extracted from MKM lacks a middle tier COM+ object that would offer the ability to scale under heavy load. This object has to be developed.

- Resources:  There is a lack of human resources for the project.

- The publications must be made available on the ExtraNet. This issue must be solved with WebOps. Once the publications are available on the ExtraNet a dedicated security must me implemented to make sure that only authorized users can retrieve them. Setting the access rights to “Read” to IUSR_COMPUTERNAME will not provide it.

- The hardware infrastructure must be evaluated prior to beginning development work such as the planned capacity (i.e. concurrent users/requests, average request length, quality of user Internet connections, etc).

- Java Applet for chart building has to be approved and the license bought.

- As MCS is being developed any delay of the MCS project may affect this project.

- The new team member, Bogdan Cirlig, is a new employee and has to get familiar with the EGM Mid-Markets deliverables as well as with MKM system.

The majority of information listed on EGM ExtraNet will be dependent on the MCS and MKM.  Should MCS break, the information on the EGM ExtraNet would be affected (not updated with the latest reports). Should MKM break, the historical and pricing tools will be unavailable.

# Alternatives Considered

| Alternative | Pros | Cons | Reason for Rejection |
| --- | --- | --- | --- |
| Existing process can continue | Inexpensive from IT perspective | The current customers would look into third party services to get the same information. | Enron would be unable to provide a complete solution to retain existing customers and acquire new clients. Current competitors do offer these services to their customers |

# Project Structure

Short description of how the project will be structured. This may include the methodology used, reporting structure, project framework, etc.

# Resources / Timeline

This section would include the initial and projected personnel (by role if specific resources are not yet identified).  Additionally, an estimated timeline for the project would be included (by phase and iteration).  A high-level cost estimate would be included with as much detail as known at the time.

## Resources

| Role | Resource | Time Commitment |
| --- | --- | --- |
| Program Manager | Randal Frisbie | Part-time |
| Project Manager | Randal Frisbie | Part-time |
| IT Developer – Lead | Bogdan Cirlig | Full-time |
| IT Developer | TBD | Full-time |
| IT Infrastructure | Brent Tiner | Part-time |
| QA | TBD | Part-time |
| DBA | Bryan Lari | Part-time |

## Estimated Timeline

| Project Phase/Deliverable |  | Duration | Iteration End Date |
| --- | --- | --- | --- |
| Phase I | Develop data schemes | 40 hours | November 2 |
| Phase I | Develop the user security and admin tools | 80 hours | November 16 |
| Phase I | Develop the In-house/Third party reports support | 40 hours | November 2 |
| Phase I / II | Develop the MKM COM+ | 120 hours | November 23 / December 14 |
| Phase I | Develop the Historical Pricing charts | 40 hours | November 9 |
| Phase I | Integration/Testing | 20 hours | November 30 |
| Phase II | Pricing Tool (front end) | 40 hours | December 14 |
| Phase II | Develop the user personalization | 40 hours | December 14 |
| Phase II | Integration/Testing | 20 hours | December 21 |
|  | Total Hours | 440 hours | Production Dates: Phase I = Dec 3, 2001 Phase II = Dec 31, 2001 |

***Notes:

The starting time of the project is October 22, 2001.  Any delay of the starting time may effect the final delivery dates.

The above final time estimate assumes 75% of the each person’s work time is met per day (two full-time employees) + 2 weeks (contingency).

Project Definition Number Request Form

## Project Information

| Project Name | EGM ExtraNet | IT Project Manager | Randal Frisbie |
| --- | --- | --- | --- |
| Project Start Date | 31 July 2001 | Est. Complete Date | 31-DEC-01 |
| Business Issue | Provide an external web site where external customers can obtain historical pricing information and publication information. |  |  |
| Business Benefit | Marketing tool to retain existing external customers. Provide in-house publications and pricing models to over 200+ external customers. |  |  |
| Responsible Cost Ctr. | 103156 |  |  |
| IT Team Members | EGM Fundamentals: Randal Frisbie – Senior Specialist Bogdan Cirlig – Senior Specialist |  |  |

## Estimated Costs

| Est. Hardware Cost (.90) | $0.00 |
| --- | --- |
| Est. Software Cost (.91) | $250.00 (Jetchart license) |
| Est. Enron Labor (.92) | $24,750.00 |
| Est. Contract Expenses (.93) |  |
| Est. Other Cost (.94) |  |
| Est. Total Cost | $25,000.00 |

## WBS Components Needed

– Please check (X) those that apply.

| Project Def. |  | Project Type |  | Home Department |  | Cost Type |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| C.xxxxxx |  | .01 (Capital) |  | .11 (103156/J. Johnson) | x | .90 (Hardware) |  |
| E.xxxxxx | x | .02 (Expense) | x | .12 (103154/S. Stock) |  | .91 (Software) |  |
| R.xxxxxx |  | .06 (Maintenance) |  | .13 (103157/R. Rao) |  | .92 (Enron Labor) | x |
|  |  |  |  | .14 (103153/J. Wong) |  | .93 (Contract Expenses) | x |
|  |  |  |  | .15 (103152/R. Burchfield) | x | .94 (Other Expenses) |  |
|  |  |  |  | .16 (103158/T. Yanowski) |  |  |  |
|  |  |  |  | .27 (103803&103366/H. Elrod) |  |  |  |

The following expense Project Definition Number was used to complete this Statement of Work document.  Close it upon assigning a new capital Project Definition Number: ______________________________

# Approval & Sign-off

By signing this document, the Business Unit Sponsor agrees with the costs to be incurred during the life of the project that is outlined in this document.   The Business Unit Sponsor should provide project set up information, which is available from their accounting team.  Project work will not begin until project set up information and approval is provided.

| Sponsor and Allocation Information |  |
| --- | --- |
| Business Unit |  |
| BU Company # |  |
| BU Cost Center* |  |
| BU Commercial Team (if applicable) |  |

*If multiple cost centers benefit from this project, provide an allocation methodology and approvals from all sponsors.  Otherwise it is assumed that 100% of the costs will be directed to the cost center provided.

#### Business Sponsor(s)

_______________________ 		Date_______________

Bill Berkeland – Director – EGM Mid-Markets

#### IT Sponsor(s)

_______________________ 		Date ______________

Iain Greig – Director IT – Commercial Support

_______________________ 		Date ______________

Randal Frisbie – Project Manager IT – EGM Fundamentals

# Project Number Assignment

To be completed by ENW Accounting.

| Project Definition # |  |
| --- | --- |
| Date Assigned |  |
| ENW Accountant |  |