| 8/30/00 | Met with EOG to discuss gas well interconnect opportunity on West Texas lateral. |
| --- | --- |
| 9/12/00 | Interconnect & Operating agreement executed and EOG committed to being responsible for construction of facilities, no $ sent. |
| 10/3/00 | TW work order executed; environmental clearance and landowner’s notification (30 days) sent. |
| 10/25/00 | EOG laying pipe to TW and expecting completion 11/5/00. |
| 11/9/00 | TW notifies EOG electronic flow measurement (EFM) still not in place. Also need water and sulfur monitors. |
| 11/13/00 | EOG opts for TW to install equipment. Customer requested ability to flow gas by 11/14. |
| 11/14/00 | Because electrical power is not immediately available, Enron will use EOG’s tower for solar energy (temporary). Will still need work with utility co (appx. 8 poles). |
| 11/15/00 | EOG wires TW $30,000 towards construction cost. |
| 11/15/00 (5:30 pm) | EOG begins flowing gas to TW at 12,500 MMBtu/d rate. |
| 12/4/00 | TW Facility Planning revises connection estimate to $423,000 (including $100,000 for income tax gross up) due to EOG scope changes. |
| 2/14/01 | Work order re-executed for $320,000 ($423,000 less tax gross up), due to scope changes. |
| 4/18/01 | Invoice sent to EOG for $290,000 ($320,000 less $30,000 prepayment). |
| 5/22/01 | EOG notifies TW that bill will not be paid. |
| 5/24/01 | Confirmed with Market Services for month-to-date during May 615,000 dth (appx. 27,000/day average). |