|  | ### ITEM | KEY DATE(S) | ## COMMENTS |
| --- | --- | --- | --- |
|  | REQUEST FOR NETWORK ACCESS & NEEDS SURVEY | DEC 1, 2000 | COMPLETED AND SENT AGREEMENT W/ ATTACH B,C,D, & E but attachment B is being revised and is not received by Enron. Will be notified when avail. |
|  | QSE APPLICATION for EPMI REP APPLICATION for EPMI | DEC 31, 2000 preferred per MRS meeting but officially is March 1, 2001 | COMPLETED and sent via Fed Ex with $500.00 fee. Steve Olinde has confirmation. QSE Agreement expected in 10 days from application file date. (only EPMI apps. Sent) |
|  | LSE APPLICATION FOR EPMI | DEC 31, 2000 preferred per meeting but officially is March 1, 2001 | No Action taken. EPMI may submit application and go through the process but without true load assigned to it can only achieve “observer status” for mock, parallel and pilot. LSE’s must also be approved by the PUCT before they may be fully qualified by ERCOT but applications will be accepted now in lieu of PUCT approval later. |

|  | QUALIFICATION PROCESS | # FROM DATE QSE Agreements are signed and accepted till Mock Market, April 1, 2001 | Includes: training, testing of communications (unit telemetry if any), systems testing |
| --- | --- | --- | --- |
|  | TRAINING PROCESS | # JAN 22, 2001 – Practice Teach # Weeklong training sessions Feb 12-16, Feb 19-23, Feb 26-Mar2, Mar 5-9 Registration for training is planned to begin 11-DEC. | Only 1 person from each organization. (critique of process) Limited space, must complete prerequisites and you may schedule partial sessions but it is not recommended. |
|  | MOCK MARKET | APRIL 1 - MAY 28, 2001 | April is scripted testing , May is parallel using real data but only participants that have actual load and generation may have “hands on” training. All others with have observer status for parallel. |
|  | PILOT | JUN- DEC 2001 | ACTUAL OPERATION FOR 5% OF MARKET |
|  | LIVE FULL MARKET | JAN 2002 |  |