Report #:	WE001206-111

NERC Region:		ECAR

Unit:		Cook 1

Mwe:		1,000

Type:		Pressurized Water Reactor (PWR)

Operator:	Indiana Michigan Power Corp.

Owners:		Indiana Michigan Power Corp.			100%

COD:		8/75

EOL:		10/2014

Current Operating Status:

As of 12/6/00, Cook 1 is shut down in an extended maintenance outage.

Recent Events:

No new event has been reported to the NRC since the 11/29/00 report.

Upcoming Events:

On 12/7/00, the NRC will meet with Cook 1 management to discuss the results of their Operational Readiness Assessment Team Inspection and Unit 1’s restart schedule.

Cook 1 is expected to complete its regulatory outage by 12/16/00.

Our Opinion:

### Cook 1 has still not entered Mode 4 hot shutdown.  Some trouble could have resulted from the Operational Readiness Assessment Team Inspection which the NRC has performed over the last week.  However, it could also be simple system startup/heatup problems having to do with equipment that has not been operating for a couple of years.  The meeting on 12/7/00 should nail down a more definitive answer to restart plans.  Currently we are projecting a 12/16/00 restart.

Report #:	WE001206-112

NERC Region:		ECAR

Unit:		Perry

Mwe:		1,205

Type:		Boiling Water Reactor (BWR)

Operator:	FirstEnergy

Owners:		FirstEnergy			100.00%

COD:		11/87

EOL:		3/2026

Current Operating Status:

As of 12/6/00, Perry is operating at 97% power.

Recent Events:

No new event has been reported to the NRC in several weeks.

Upcoming Events:

The next refueling outage is expected to begin on 2/17/01.

Our Opinion:

Perry has reported to the NRC that they have begun a coastdown to their refueling outage.  If correct, that would be a long slow coastdown of over two months.  It is possible that the status report was in error.  We are investigating Perry’s current status.

Report #:	WE001206-121

NERC Region:		MAIN

Unit:		LaSalle 2

Mwe:		1078

Type:		Boiling Water Reactor (BWR)

Operator:	Exelon

Owners:		Commonwealth Edison			100%

COD:		1/84

EOL:		5/2022

Current Operating Status:

As of 12/6/00, LaSalle 2 is operating at 90% power.

Recent Events:

On 12/1/00, while ascending in power following their refueling outage, LaSalle 2 scrammed due to high reactor vessel water level resulting from feedwater manipulations to place a Turbine Driven Reactor Feedwater Pump online.

Upcoming Events:

Full power is expected to be reached by 12/7/00.

Our Opinion:

The unit has delayed final ascension to full power in order to repair certain steam valves.  The repair should be completed today and full power should be reached by tomorrow.  We expect a good capacity factor over the next cycle in the mid to upper 90s.  It may be a bit lower in the next few months perhaps due to resolving problems that result from rushing through a refueling outage.

Report #:	WE001206-122

NERC Region:		MAIN

Unit:		Point Beach 2

Mwe:		485

Type:		Pressurized Water Reactor (PWR)

Operator:	Nuclear Management Company

Owners:		Wisconsin Electric Power Company		100%

COD:		10/72

EOL:		3/2013

Current Operating Status:

As of 12/6/00, Point Beach 2 is shut down in a refueling outage.

Recent Events:

No new event has been reported to the NRC since the 11/29/00 report.

Upcoming Events:

The refueling outage is expected to end by 12/9/00.

Our Opinion:

Point Beach 2 dropped back to cold shutdown to perform some minor maintenance.  We continue to expect restart to occur by sometime this weekend, 12/9/00-12/10/00.  The unit has operated well over the past couple of years, and we expect a capacity factor of about 96-97% over the coming cycle.

Report #:	WE001206-131

NERC Region:		MAPP

Unit:		Prairie Island 1

Mwe:		513

Type:		Pressurized Water Reactor (PWR)

Operator:	Nuclear Management Company

Owners:		Northern States Power Company		100%

COD:		12/73

EOL:		8/2013

Current Operating Status:

As of 12/6/00, Prairie Island 1 is shut down in a forced outage.

Recent Events:

On 12/3/00, the 121 Spent Fuel Special & In-Service Purge System tripped due to high radiation on lR-22, the Shield Building Stack gas radiation monitor.  This ventilation system operated for approximately 1-2 minutes prior to the high radiation trip signal.

Upcoming Events:

The next refueling outage is expected to begin on 1/20/01.

Our Opinion:

### Prairie Island 1 is shut down due to maintenance on a reactor coolant pump.  We continue to expect the maintenance to be complete by tomorrow, 12/7/00.  The maintenance outage should not affect the start of the refueling which is scheduled for 1/20/01.  The unit has performed very well over the past couple of years.

Report #:	WE001206-231

NERC Region:		SERC

Unit:		Oconee 1

Mwe:		846

Type:		Pressurized Water Reactor (PWR)

Operator:	Duke Power Company

Owners:		Duke Power Company		100%

COD:		7/73

EOL:		2/2013

Current Operating Status:

As of 12/6/00, Oconee 1 is shut down in a refueling outage.

Recent Events:

On 11/25/00, during a routine visual inspection, engineering identified a small amount (about 1 cup) of boron accumulation at the interface between the outside of the reactor vessel head and an unused reactor head thermocouple nozzle.  The source of the boron could not be concluded.  Unit 1 has eight unused thermocouple nozzles that were used during original startup.  On 12/4/00, a preliminary review of the eddy current test results from the unused thermocouple nozzle indicated that the source of the observed boron was most likely from a degraded pressure boundary.  In addition, a video inspection of the reactor head revealed trace amounts of boron around three additional thermocouple nozzles and one control rod drive nozzle. Leakage of this magnitude would not typically be detectable during operation.  A failure investigation team has been formed to evaluate this condition.

Upcoming Events:

The refueling outage is expected to complete by 1/7/01.

Our Opinion:

Oconee 1 moved in to the heart of their outage much more quickly this time than during their last refueling outage.  Its Spring 1999 refueling lasted 54 days which was a big improvement over prior outages, but the current outage has good possibilities to improve even more.

Report #:	WE001206-232

NERC Region:		SERC

Unit:		Summer

Mwe:		885

Type:		Pressurized Water Reactor (PWR)

Operator:	South Carolina Electric and Gas (SCE&G)

Owners:		SCE&G			  66.67%

Santee Cooper		  33.33%

100.00%

COD:		1/84

EOL:		8/2022

Current Operating Status:

As of 12/6/00, Summer is shut down in a refueling outage.

Recent Events:

No new event has been reported to the NRC since the 11/29/00 report.

Upcoming Events:

On 12/7/00, meeting to discuss licensee’s position on the significance of having a steam turbine driven emergency feed water pump inoperable for approx 48 days during power operation.

The refueling outage is expected to end by 1/1/01.

Our Opinion:

Site personnel continue to expect completion of the pipe replacement and outage by January 1, 2001.  Welding should begin shortly.  All pipe/weld activities are expected to end by Christmas, which leaves a week for ascending through mode changes to restart.  If the welding goes well, the schedule may be improved upon.

- Report #:	WE001206-241

NERC Region:		SPP

Unit:		ANO 2

Mwe:		858

Type:		Pressurized Water Reactor (PWR)

Operator:	Entergy Operations, Inc.

Owners:		Entergy Arkansas, Inc.	100%

COD:		3/80

EOL:		9/2018

- Current Operating Status:

- As of 12/6/00, Arkansas Nuclear One 2 is shutdown in a refueling/steam generator replacement outage.

- Recent Events:

- No new event has been reported to the NRC since the 11/29/00 report.

- Upcoming Events:

- The refueling outage is expected to end on 12/7/00.

- Our Opinion:

The unit is currently in hot standby and should move into startup today.  We expect restart (synchronization to the grid) by 12/7/00.  ANO 2 is an average performing plant.  We expect a capacity factor in the low 90s over the coming cycle.

Report #:	WE001206-311

NERC Region:		MAAC

Unit:		Hope Creek

Mwe:		1,031

Type:		Boiling Water Reactor (BWR)

Operator:	Public Service Electric & Gas Company (PSE&G)

Owners:		PSE&G					 100%

COD:		12/86

EOL:		4/2026

Current Operating Status:

As of 12/6/00, Hope Creek is operating at 100% power.

Recent Events:

No new event has been reported to the NRC since the 11/22/00 report.

Upcoming Events:

The next refueling outage is expected to begin on 9/3/01.

Our Opinion:

The unit is back to full power after performing grid maintenance in a derated condition.  The unit is a consistent performer with capacity factor at about 95%.  We expect continued performance at that level through the rest of this cycle.

Report #:	WE001206-312

NERC Region:		MAAC

Unit:		Salem 2

Mwe:		1106

Type:		Pressurized Water Reactor (PWR)

Operator:	Public Service Gas & Electric Company (PSE&G)

Owners:		PSE&G					  42.59%

PECO Energy Company			  42.59%

Atlantic City Electric Company		    7.41%

Delmarva Power & Light Company	    7.41%

100.00%

COD:		3/73

EOL:		12/2012

Current Operating Status:

As of 12/6/00, Salem 2 is operating at 100% power.

Recent Events:

No new event has been reported to the NRC since the 11/15/00 report.

Upcoming Events:

The next refueling outage is expected to start on 3/30/02.

Our Opinion:

Salem 2 is back to 100% power after derating to 97% for a couple days this past week.  This unit has made significant improvement in operation over the past couple of years.  We expect a capacity factor in the mid to upper 90s for this cycle.

Report #:	WE001206-321

NERC Region:		NPCC

Unit:		Indian Point 2

Mwe:		975

Type:		Pressurized Water Reactor (PWR)

Operator:	Consolidated Edison of New York

Owners:		Consolidated Edison of New York		100%

COD:		8/74

EOL:		9/2013

Current Operating Status:

As of 12/6/00, Indian Point 2 is shut down in a regulatory/steam generator replacement outage that began on 2/15/00.

Recent Events:

No new events have been reported to the NRC since the 11/29/00 report.

Upcoming Events:

The steam generator replacement outage is expected to complete by 12/11/00.

Our Opinion:

Indian Point 2 has not progressed past Mode 5 cold shutdown since last week.  As we had reported earlier, several engineering concerns still remain and progress through mode ascension will be slow.  The restart targeted date of 12/11/00 may be in jeopardy if Mode 4 is not reached within the next couple of days.

Report #:	WE001206-322

NERC Region:		NPCC

Unit:		Seabrook

Mwe:		1,158

Type:		Pressurized Water Reactor (PWR)

Operator:	North Atlantic Energy Service Corporation

Owners:		North Atlantic Energy Corp.				 35.98201%

United Illuminating Co.					 17.50000%

Great Bay Power Corp.					 15.03229%

# Massachusetts Municipal Wholesale Electric Co.	 	 11.59340%

National Grid						   9.95766%

Connecticut Light & Power Co.				    4.05985%

NSTAR							    3.52317%

New Hampshire Electric Cooperative, Inc.		    	    2.17391%

Taunton Municipal Light Plant				    0.10034%

Hudson Light & Power Dept.				    0.07737%

100.00000%

COD:		7/90

EOL:		10/2026

Current Operating Status:

As of 12/6/00, Seabrook is shut down in a refueling outage.

Recent Events:

No new event has been reported to the NRC since the 11/29/00 report

Upcoming Events:

The refueling outage is expected to end on 12/21/00.

Our Opinion:

# Seabrook is moving toward completion of their outage.  If Mode 4 is reached by this weekend, they will have an excellent chance at improving the restart date by about a week, from 12/21/00 to 12/14/00.