Enron Energy Operations ASE Studio Workshop

Planning Document

February 12 – 13, 2001

Sponsor Team:

Mary Solmonson

Sally Beck

Lisa Petruszka

???Other Enron???

Objectives (to be further refined during Sponsor Meeting):

- Develop an overall mission for the services Enron’s Energy Operations group will take to the public market.

- Develop and agree on a business plan that links to the mission, identifies the market opportunity, and defines the product and service offerings to be provided by Energy Operations.

- Create a list of prospective market segments/customers who would purchase these services.

- Discuss pricing strategies and methodologies and develop action plans to evaluate alternatives.

- Develop an operating model that will enable Enron to implement its business plan successfully.  This model will include major core processes and roles and responsibilities.

- Develop a 6-month action plan to successfully implement the business plan.

# Upcoming Activities

- Initial Sponsor Meeting, Friday, January 26th in Houston

- Confirm logistics and extend formal invitation

- Begin data gathering

- Develop pre-read materials

# Observations from Off-Site on Friday, January 12

Possible information to gather before the ASE Studio:

- Stratification of counterparties similar to the Market Intelligence packet presented at the Jan 12th offsite but with the following data:

- Size or volume of transactions

- Complexity of transactions

- Total counterparty transaction volume – not just trades with Enron

- Additional information on counterparties or potential customers:

- Transaction complexity/level of sophistication

- Type of trading and transaction processing systems used (i.e., off the shelf, custom developed in house, etc)

- Mid and back office cost structure of “prospects” or potential customers

- Who is in the most “pain” – small companies with large growth

- Prospect list

- Possible competitors for the proposed market and their target service offerings and timing (i.e., Aquila valuation and structuring model)

- Information on any deals where Enron is already providing the proposed services (i.e., Calgary?)

- Case study on Enron On-line including attributes that made the initiative successful

- Information on CommodityLogic, Contract Exchange (?) and EnergyDesk.com

- Output from Jan 12th session

## Questions to consider for ASE Studio:

- What will be the marketing focus?  Cost reduction?  Capital redeployment?  Efficiency or accuracy improvements?

- What services do we not have today that would be value added to Enron or third parties?

- Would we approach companies to perform an initial cost assessment?  Would we charge for this service or use it as a marketing tool?

- Would we limit our “customer” base to existing Enron counterparties or any trading organization?

- What will it take to get Energy Ops comfortable working in the new environment (i.e., an environment of "creating the short and figuring out how to cover it”)?

- Would we let customers use Enron proprietary systems?  If not, how would we integrate their legacy systems?

- How can offering services to third parties help Enron – other than through revenue generation?

- Are there companies or BU’s within the Enron umbrella that could use the services of Energy Ops?

- What other Enron BU’s or people might have info on our potential customers?  How can we identify them, gather the information and involve them in the process?

- What risks are we creating for Enron?  How should we manage them?

- How does Energy Ops overcome opposition from customers to “big Enron” providing services or having access to sensitive or strategically significant data?

- What is the profile of the “perfect customer”?

- What is the first win?  What can we book in 2Q01?

- What services would we not be able to offer because we aren’t good at providing them (lease records, DOI, etc.)?

- What is the possible implication to Enron’s competitive advantage of pursuing this strategy?  Does offering services to third parties compromise the competitive advantage?

- What is the new business model?  Full outsourcing of STP?  Modular service offering?  ASP?  Consulting services?  Custom system development?  Other?

- How could the possible services of Energy Ops be bundled with services of other Enron BU’s (like EES) to create more value for the customers and Enron?

- What cultural shifts would have to happen for Energy Ops to be successful?

- Would you be willing to permanently give up your best employee to make this initiative succeed?

- What markets would we serve?  Energy trading or financial institutions?

- Would you consider joint venture or equity arrangements with your customers?

- If Duke outsourced STP to Energy Ops next week, how would you get the resources to provide the work?

- How will you charge for your services?  Will it vary by service or customer?

- What marketing do we have to undertake internally to raise awareness and build commitment to the new Energy Ops strategy?

- What other Enron organizations are out marketing similar products or services to customers?  How should we coordinate with them?

- How should we change the industry – the processes, mindsets and practices?