Enron Japan weekly update

# Week: June 5 – June 9, 2000

| John Ambler- “Public Relations” | - Managing/containing nine outstanding media inquiries. Moved forward PR manager candidate past interviews to HR review. |
| --- | --- |
| Next Week: | - Directly handle and/or schedule outstanding media requests. Complete job specs for PR manager and progress to offer. Coordinate with IT and O’Day on internet site. Develop press release and plan for Asian weather derivatives launch, including publicity for Japan aspect. |
| Loretta Brelsford – | - Still on target for July 3 move-in date Fox contract – signature process underway…waiting for new Project Schedule from Fox. Continued negotiation of AV equipment. Confirmed trader phones will be there…will install as soon as desk in |
| Next Week: | - Prepare “who is in Tokyo and when” list (non-EJ staff). Place order for AV/video teleconferencing. Finalize Takenaka contract (meeting w/B&M, Fox, Takenaka being arranged) |
| Outstanding Issues | - Phone numbers. Copy machine/fax/shredder. Business Card scanner (getting input from PTS) |
| Archie Eubanks – # “Accounting” | - Initiated introductory meetings between Bekeng and Houston accounting, tax, treasury and information technology staffs. Received updated staffing assumptions from Gilchrist. Updated budget to be reviewed with Bekeng and forwarded to Hirl by end of week. Payments made this week (primarily related to legal fees and office expenses): |

| Vendor | Description |  |  | JPY | USD |
| --- | --- | --- | --- | --- | --- |
| McLagan Partners Asia, Inc | 1999 Tokyo Surveys |  |  | 447,800.00 |  |
| Baker & McKenzie | Services - April 2000 |  |  | 13,307,973.00 |  |
| PTS | Communication Services |  |  | 291,249.00 |  |
| Regus Japan K. K. | Office & Telecom Expenses |  |  | 1,520,354.00 |  |
| Tsunashima Co. Ltd. | Jim Pyke - Rent & Deposit |  |  | 813,400.00 |  |
| Sagawa Kyubin | Document Mailing Fee |  |  | 67,694.00 |  |
|  | Total Yen |  |  | JPY 16,448,470.00 |  |
| Vinson & Elkins | Services thru April 2000 |  |  |  | 26,681.99 |
|  | Total USD |  |  |  | $ 26,681.99 |
| Next Week: |  |  | - Complete process of setting up legal entity books on Houston SAP System. Monthly/Quarterly Reporting requirements |  |  |
| Susan Musch – “Tax” |  |  | - Met with Jan-Erland Bekeng to discuss tax issues relating to the Japanese trading office. Power Contract Documentation – Continuing to work on Japanese consumption tax issues with Michael Grimes and AA-Tokyo. |  |  |
| Next Week: |  |  | - Continue working on funding of the Japanese trading entities. Pursue steps to set up TK arrangements for Japanese entities |  |  |
| Outstanding Issues |  | - Implementation of the TK structure. Work on setting up service agreement for services being performed by Enron Japan KK for Enron Marketing KK. |  |  |  |
| Nick O’Day- ## “Regulatory/Government Affairs” |  | - Schroeder visit. International Trade Commission ITC meeting. Meeting with Suetsugu - Federation of Electric Power Utilities re inter utility market. East Asia Public Affairs Meeting |  |  |  |
| Upcoming Week: |  | - Meeting with Kansai electric re WSA/ PSA. EJ website development |  |  |  |
| Other: |  | - Meeting with Mika Watanabe – PR manager. Meeting MG Japan. Meeting with EnCom/ Epower. Third round interviews with GA candidates Meeting Osaka Gas. Clarify position re participation in the inter-utility market |  |  |  |