# Enron Project – Status as of 8/2/00

Engine:			LM6000PC E-Sprint w/o VIGV’s

Climate:		Winterization to –10F, Noise to 85 dBA

Enclosures:		Water Injection Skid, Liquid Fuel Skid, and Gauge Panel

Items Not Enclosed:	Auxiliary Skid, Hydraulic Starter, Sprint Skid, and CO2 – (Winterized)

Gas/Water Units:	Duplex LP Water Injection Pumps w/Enclosures and heaters

Dual Fuel Units:

- Standard LP/HP Water Injection Pump Skids w/Enclosures and heaters

- Single Liquid Fuel Pump Skid w/Enclosure and Heat Tracing

| UNIT | DWG SERIES | UNIT SERIAL # | PROD SALES # | FUEL | GEN | PIPNG | LINE SIDE | LUBE OIL COOLING | EXHAUST STACK | CONT DELIV DATE | ASSIGNED ##### PROJECT | PROJ DELIV DATE | COMMENTS | # OF C/O’s | UNIT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 559XXX | 308898 | 601134 | Gas | GE | RH | RH | Fin/Fan | 45 ft | ### 7/30/00 | ### ESA | ### 6/20/00 | ### Static Test |  | 1 |
| 2 | 559XXX | 308951 | 601134 | Gas | GE | LH | LH | Fin/Fan |  | 7/30/00 | Open | 7/26/00 | Static Test |  | 2 |
| 3 | 559XXX | 308972 | 601134 | Gas | GE | RH | RH | Fin/Fan |  | 7/30/00 | Open | 8/15/00 | Static Test |  | 3 |
| 4 | 559XXX | 308999 | 601134 | Gas | GE | LH | LH | Fin/Fan | 45ft | 8/30/00 | ESA | 7/5/00 |  |  | 4 |
| 5 | 559XXX | 309020 | 601134 | Gas | GE | RH | RH | Fin/Fan | 45 ft | 8/30/00 | ESA | 7/10/00 |  |  | 5 |
| 6 | 559XXX | 309073 | 601134 | Gas | GE | LH | LH | Fin/Fan | 45 ft | 8/30/00 | ESA | 7/21/00 | Static Test |  | 6 |
| 7 | 568XXX | 309101 | 601134B | Dual | Brush | RH | RH | Fin/Fan | 45 ft HVY | 9/30/00 | Florida | 6/22/00 | Static Test | ? | 7 |
| 8 | 568XXX | 309123 | 601134B | Dual | Brush | LH | ## LH | Fin/Fan | 45 ft HVY | 9/30/00 | Florida | 6/30/00 | Static Test | ? | 8 |
| 9 | ## 581XXX | 309266 | #### 601134C | Gas | Brush | RH | RH | ## Shell/Tube | NA | 10/30/00 | Austin | 8/19/00 | Static Test |  | 9 |
| 10 | 581XXX | 309307 | 601134C | Gas | Brush | LH | LH | Shell/Tube | NA | 10/30/00 | Austin | 9/1/00 | Static Test |  | 10 |
| 11 | 581XXX | 309376 | 601134C | Gas | Brush | RH | RH | Shell/Tube | NA | 10/30/00 | Austin | 9/6/00 | Static Test |  | 11 |
| 12 | 581XXX | 309398 | 601134C | Gas | Brush | LH | LH | Shell/Tube | NA | 11/30/00 | Austin | 9/14/00 | Static Test |  | 12 |
| 13 | 562XXX | 309420 | 601134A | Gas | Brush | RH | RH | Fin/Fan | ? | 11/30/00 | PSCO | 9/21/00 |  |  | 13 |
| 14 | 562XXX | “ | 601134A | Gas | Brush | LH | LH | Fin/Fan | ? | 12/30/00 | PSCO | 9/28/00 |  |  | 14 |
| 15 | 562XXX | “ | 601134A | Gas | Brush | ## LH | ## LH | Fin/Fan | ? | 12/30/00 | PSCO | 10/25/00 | Static Test |  | 15 |
| 16 | 562XXX | “ | 601134A | Gas | Brush | RH | RH | Fin/Fan | ? | 1/30/01 | PSCO | 11/1/00 |  |  | 16 |
| 17 | ## 562XXX | “ | #### 601134A | Dual | Brush | LH | LH | Fin/Fan | 45 ft HVY | 1/30/01 | Florida | 11/13/00 |  | 1 | 17 |
| 18 | 562XXX | “ | 601134A | Dual | Brush | RH | RH | Fin/Fan | 45 ft HVY | 1/30/01 | Florida | 11/20/00 | Static Test | 1 | 18 |
| 19 | 562XXX | “ | 601134A | Dual | Brush | LH | LH | Fin/Fan | 45 ft HVY | 2/28/01 | Florida | 11/27/00 | Static Test | 1 | 19 |
| 20 | 562XXX | “ | 601134A | Dual | Brush | RH | RH | Fin/Fan | 45 ft HVY | 2/28/01 | Florida | 12/11/00 | Static Test | 1 | 20 |
| 21 | 581XXX | “ | 601134C | Gas | Brush | LH | LH | Shell/Tube | NA | 3/30/01 | Las Vegas | 1/5/01 | Static Test |  | 21 |
| 22 | 581XXX | “ | 601134C | Gas | Brush | RH | RH | Shell/Tube | NA | 3/30/01 | Las Vegas | 1/12/01 |  |  | 22 |
| 23 | 581XXX | “ | 601134C | Gas | Brush | LH | LH | Shell/Tube | NA | 4/30/01 | Las Vegas | 1/20/01 |  |  | 23 |
| 24 | 581XXX | “ | 601134C | Gas | Brush | RH | RH | Shell/Tube | NA | 4/30/01 | Las Vegas | 3/13/01 | Static Test |  | 24 |