July 10, 2000

Enron North America

One Tabor Center

1200 17th Street, Suite 2750

Denver, CO 80202

Attn.: Mike Legler

Re:	Additional amendments to Agreement dated January 12 1999, as amended ("Medicine Bow Lateral Transportation Precedent Agreement" or "MBLTPA")

Ladies and Gentlemen:

Wyoming Interstate Company, Ltd. (“WIC”) Enron North America (“Enron”) entered into the referenced MBLTPA, that concerns the construction of new gas transmission facilities identified therein as the "Medicine Bow "Medicine Bow Lateral"* and transportation services thereon for Enron.

When WIC and Enron executed the MBLTPA, the parties anticipated that the transportation of the last 60 MDth/d of the TMDQIE* ("380-440 Volume") would be accomplished by WIC adding additional compression to the Medicine Bow Lateral*. To address the dramatic increase in gas volumes needing transportation out of the Powder River Basin, the parties are contemporaneously executing a Medicine Bow Loop Transportation Precedent Agreement, dated July __, 2000 ("Loop Agreement"). Under the Loop Agreement and subject to certain conditions contained therein, WIC has agreed to build new pipeline facilities that will "loop" the Medicine Bow Lateral* (the "Loop") rather than WIC installing additional compression on the Medicine Bow Lateral* (other than the additional compression scheduled to go into service in August, 2000).

Accordingly, for and in consideration of the mutual promises of the parties, Enron and WIC agree as follows:

1.	Provided that the Loop is constructed, notwithstanding any other provision of the MBLTPA, WIC shall not install compression on the Medicine Bow Lateral* to transport the 380-440 Volume. Instead, such volumes will physically flow through the Loop, although contractually the capacity will remain under the MBLTPA .

2.	Effective upon the first day of the month following the date the Loop is ready for service:

a.	Exhibit C of the MBLTPA is deleted and replaced with the new Exhibit C attached hereto and incorporated herein.

b.	Section 3(c)(iv) and Section 3(c)(v), as well as the definition of "Expansion," are deleted from the MBLTPA in their entirety.

c.	The phrase in Paragraph 3(c)(i) of the MBLTPA "Unless reduced pursuant to the provisions of Paragraphs 3(c)(ii) or (iv) of this Agreement (or the comparable provisions of the FTSAs),…" is deleted and replaced with the phrase ""Unless reduced pursuant to the provisions of Paragraph 3(c)(ii) of this Agreement (or the comparable provisions of the FTSAs),…"

d.	The FTSA* described in the MBLTPA shall be amended as necessary to conform to the provisions of this letter agreement.

e.	The definition of "Medicine Bow Lateral” in the MBLTPA is deleted and replaced with the following:

"Medicine Bow Lateral” means Transporter's gas transmission facilities extending from the meter stations in Section 33, Township 33N, Range 73W, Converse County, Wyoming, along a diagonal path to an interconnection with WIC’s mainline in Section 28, Township 12N, Range 67W, Weld County, Colorado, as the same may be modified by the addition of compression to create a total capacity of up to 380 MDth/day.

- This Amendment shall be effective upon the date hereof.  In the event, however, that WIC does not construct the Loop then this Amendment shall be of no force or effect, except that:

a. 	The parties agree that no claims shall arise from any delay necessitated by WIC seeking regulatory approvals for the compression required to transport the 380-440 Volume on the Medicine Bow Lateral because the parties recognize that WIC will be pursuing approvals for the Loop rather than approvals for such compression.

b.	Whether or not WIC constructs the Loop, Enron shall not be obligated to pay reservation charges or other charges for any volume of Enron's MDQ under the MBLTPA and FTSA* earlier than the point in time that WIC has ready for service facilities adequate to provide firm transportation for such volume.

4.	The parties' obligations under this letter agreement shall be subject to the approval, if required, of the terms of this letter agreement by WIC's lenders.

If the foregoing is acceptable to Enron, please have this letter agreement executed and return a copy to WIC.

WYOMING INTERSTATE COMPANY, LTD.

By: CIG Gas Supply Company,

General Partner

By: _____________________

Donald J. Zinko

Senior Vice President

Accepted and agreed to:

ENRON NORTH AMERICA

By:                              ______

Name:  __________________

Title:  ___________________

Exhibit C – Rate Schedule

| TMDQIE (MDth/d) | 100% Load Factor Rate ($/Dth) |
| --- | --- |
| Above 350 | 0.1260; however the rate shall be 0.1200 commencing on the first day of the month following the date the Loop goes is ready for service |
| 300-349 | 0.1330 |
| 250-299 | 0.1590 |

Those terms identified in this letter agreement with an asterisk (*) have the meaning defined in the MBLTPA.

Fuel and L&U (applicable to service on the Medicine Bow Lateral), GRI (if applicable), ACA and all other surcharges applicable to WIC’s Rate Schedule FT under WIC’s Tariff shall be payable in addition to the amount shown, except as provided in Paragraph 3 (c)(iii) of this Agreement.

Charged and payable in reservation and commodity components.