- EXHIBIT F

CHANGE ORDER PRICING

[SAMPLE]

- Formula for Calculation of Contract Price Change

Contract Change Orders for all Changes will be priced in accordance with the following formulas:

I.	Engineering/Project Management Costs:

Formula:

Estimated or actual man hours X direct salary costs X 2.25

Categories (includes but not limited to):

(i) 	Contractor in house engineering to design and review proposed changes;

(ii)	Contractor main office and field project management personnel involvement in preparing, and negotiating necessary changes with subcontractors and vendors; and

(iii)	Contractor engineering and project management personnel involvement in preparation of the change order estimates that are accepted by Owner.

II.	Contractor’s subcontractor/vendor costs:

Formula: Quoted estimated or actual costs by vendors and contractors X 1.10.

Categories (includes but not limited to):

(i)	Site construction subcontractors; and

(ii)	Equipment

III.	Contractor’s subcontracted engineering:

Formula: Actual invoices X 1.10

Categories (includes but not limited to):

(i)	Estimate preparation; and

(ii)	preparation of Change Order alternatives and design of accepted Change Order(s)

IV.	Out of pocket costs:

Formula: Actual costs X 1.00

Categories (includes but not limited to):

(i) 	travel;

(ii) 	subsistence;

(iii) 	unusual postage; and

(iv) 	photocopying and printing

V.	Craft Labor costs:

Formula:  Estimated or actual man hours X applicable labor rate (see attached Labor Rates)

Categories (includes but not limited to):

(i)	Erection;

(ii)	Material Handling;

(iii)	Labor; and

(iv)	Labor supervision

VI.	Permanent materials:

Formula:  Estimated costs or actual invoices X 1.05

VII.	Equipment:

Formula:  Calculated or actual costs of Equipment X 1.10

Categories (includes but not limited to):

(i)	Contractor owned equipment;

(ii)	Contractor leased equipment; and

(iii)	Outside rented equipment

VIII.	Fee

Formula: (I + II + III + IV + V + VI + VII) X 0.10

IX.	Total Change Order Costs

Formula: Sum I through VIII

(Note: Direct salary wage cost is employee’s gross salary wage subject to income tax).

| PROJECT | Pastoria |  |  |  | CITY |  |  | STATE | CA |  | PROP NO. | R000332 |  |  | DATE | 14-Sep-00 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BURDENS |  |  |  |  |  |  |  |  |  |  |  |  |  | ESCALATION |  |  |  |  |  |  |  |  |  |  |  |
|  | PREMIUM |  | OH/PAY TX |  |  | WORK COMP |  |  | GROUP INS |  |  | YEAR | RATE | H.O. | FLD |  |  |  |  |  |
| HOME OFC | 0% |  | 97.0% |  | 0.35% |  | 0.0% |  | 2000 | 0.0% | 35.0% | 0.0% |  |  |  |  |  |
| SALARIED | 0% |  | 52.0% |  | 0.5% |  | 0.0% |  | 2001 | 4.0% | 50.0% | 70.0% |  |  |  |  |  |
| HOURLY | 12% |  | 11.00% |  | 15.0% |  | 5.0% |  | 2002 | 8.0% | 15.0% | 30.0% |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | AVG | 3.2% | 5.2% |  |  |  |  |  |
|  |  |  |  |  |  |  |  | CREW RATE | ESCAL | PREM PAY | TLINE BASE RATE | OVHD/PAY TAX | WORK CMP | Group Ins & Fringes | TOTAL |  |  |
| ENGINEERING | HO |  |  |  | 40.00 |  |  | 45.00 | 1.44 | 0.00 | 46.44 | 45.05 | 0.16 | 0.00 | $91.65 |  |  |
| HOME OFFICE | HO |  |  |  | 40.00 |  |  | 45.00 | 1.44 | 0.00 | 46.44 | 45.05 | 0.16 | 0.00 | $91.65 |  |  |
| CONSTRUCT MGR | Sal |  |  | 90,000 | 48.27 |  |  | 53.27 | 2.77 | 0.00 | 56.04 | 29.14 | 0.28 | 0.00 | $85.46 |  |  |
| RESIDENT ENGR | Sal |  |  | 68,000 | 37.69 |  |  | 42.69 | 2.22 | 0.00 | 44.91 | 23.35 | 0.22 | 0.00 | $68.48 |  |  |
| CONSTRUCT ENGR | Sal |  |  | 50,000 | 29.04 |  |  | 34.04 | 1.77 | 0.00 | 35.81 | 18.62 | 0.18 | 0.00 | $54.61 |  |  |
| GENERAL SUPT | Sal |  |  | 72,000 | 39.62 |  |  | 44.62 | 2.32 | 0.00 | 46.94 | 24.41 | 0.23 | 0.00 | $71.58 |  |  |
| DISCIPLINE SUPTS | Sal |  |  | 63,000 | 35.29 |  |  | 40.29 | 2.10 | 0.00 | 42.39 | 22.04 | 0.21 | 0.00 | $64.64 |  |  |
| SR PROJ CTRL ENGR | Sal |  |  | 70,000 | 38.65 |  |  | 43.65 | 2.27 | 0.00 | 45.92 | 23.88 | 0.23 | 0.00 | $70.03 |  |  |
| PRJ CTRL ENGR | Sal |  |  | 50,000 | 29.04 |  |  | 34.04 | 1.77 | 0.00 | 35.81 | 18.62 | 0.18 | 0.00 | $54.61 |  |  |
| FIELD ACCOUNTANT | Sal |  |  | 47,000 | 27.60 |  |  | 32.60 | 1.70 | 0.00 | 34.30 | 17.84 | 0.17 | 0.00 | $52.31 |  |  |
| HUMAN RESOURCES | Sal |  |  | 65,000 | 36.25 |  |  | 41.25 | 2.15 | 0.00 | 43.40 | 22.57 | 0.22 | 0.00 | $66.19 |  |  |
| PURCH AGENT | Sal |  |  | 52,000 | 30.00 |  |  | 35.00 | 1.82 | 0.00 | 36.82 | 19.15 | 0.18 | 0.00 | $56.15 |  |  |
| SR QA/QC SUPV | Sal |  |  |  | 32.04 |  |  | 37.04 | 1.93 | 0.00 | 38.97 | 20.26 | 0.19 | 0.00 | $59.42 |  |  |
| QA/QC SUPV | Sal |  |  |  | 28.52 |  |  | 33.52 | 1.74 | 0.00 | 35.26 | 18.34 | 0.18 | 0.00 | $53.78 |  |  |
| SAFETY SUPT | Sal |  |  |  | 28.51 |  |  | 33.51 | 1.74 | 0.00 | 35.25 | 18.33 | 0.18 | 0.00 | $53.76 |  |  |
| MEDIC | Sal |  |  |  | 20.00 |  |  | 25.00 | 1.30 | 0.00 | 26.30 | 13.68 | 0.13 | 0.00 | $40.11 |  |  |
| FIELD ENGR | Hr |  |  |  | 27.00 |  |  | 33.00 | 1.72 | 4.17 | 38.89 | 4.28 | 5.83 | 10.00 | $59.00 |  |  |
| PARTY CHIEF | Hr |  |  |  | 27.00 |  |  | 33.00 | 1.72 | 4.17 | 38.89 | 4.28 | 5.83 | 10.00 | $59.00 |  |  |
| CHAINMAN | Hr |  |  |  | 25.00 |  |  | 30.00 | 1.56 | 3.79 | 35.35 | 3.89 | 5.30 | 10.00 | $54.54 |  |  |
| CLERKS | Hr |  |  |  | 18.00 |  |  | 23.00 | 1.20 | 2.90 | 27.10 | 2.98 | 4.07 | 1.36 | $35.51 |  |  |
| RECEPTIONIST | Hr |  |  |  | 18.00 |  |  | 23.00 | 1.20 | 2.90 | 27.10 | 2.98 | 4.07 | 1.36 | $35.51 |  |  |
| TIMEKEEPER | Hr |  |  |  | 25.00 |  |  | 30.00 | 1.56 | 3.79 | 35.35 | 3.89 | 5.30 | 10.00 | $54.54 |  |  |
| TOOLROOM | Hr |  |  |  | 25.00 |  |  | 30.00 | 1.56 | 3.79 | 35.35 | 3.89 | 5.30 | 10.00 | $54.54 |  |  |
| QA/QC TECH | Hr |  |  |  | 21.00 |  |  | 26.00 | 1.35 | 3.28 | 30.63 | 3.37 | 4.59 | 1.53 | $40.12 |  |  |
| SAFETY TECH | Hr |  |  |  | 21.00 |  |  | 26.00 | 1.35 | 3.28 | 30.63 | 3.37 | 4.59 | 1.53 | $40.12 |  |  |

|  |  | 0% | 0% | 75% |  | $1.50 | $2.50 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | h3 | h2 | h1 | jm | fm | gf |  |  |  |  |  |  |  |  |  |  |
| BOILERMAKERS | Crew Mix | 0.0 | 0.0 | 0.5 | 4.6 | 1.0 | 1.0 |  |  |  |  |  | 14.69% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 22.25 | 29.66 | 31.16 | 32.16 | 29.69 | 1.54 | 3.75 | 34.98 | 3.85 | 5.14 | 8.41 | $52.38 |  |  |
| CEMENT FINISHERS | Crew Mix | 0.0 | 0.0 | 0.3 | 2.6 | 1.0 | 0.0 |  |  |  |  |  | 13.62% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 25.36 | 33.81 | 35.31 | 36.31 | 33.57 | 1.75 | 4.24 | 39.56 | 4.35 | 5.39 | 5.57 | $54.87 |  |  |
| CARPENTERS | Crew Mix | 0.0 | 0.0 | 0.8 | 7.2 | 1.0 | 0.5 |  |  |  |  |  | 13.62% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 21.37 | 28.49 | 29.99 | 30.99 | 28.18 | 1.47 | 3.56 | 33.21 | 3.65 | 4.52 | 6.80 | $48.18 |  |  |
| ELECTRICIAN | Crew Mix | 0.0 | 0.0 | 0.0 | 9.0 | 1.0 | 0.5 |  |  |  |  |  | 5.47% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 27.28 | 36.37 | 37.87 | 38.87 | 36.63 | 1.90 | 4.62 | 43.15 | 4.75 | 2.36 | 7.34 | $57.60 |  |  |
| INSTR FITTER | Crew Mix | 0.0 | 0.0 | 0.8 | 6.9 | 1.0 | 0.3 |  |  |  |  |  | 11.32% |  |  |  |  |
| use Pipefitter | Base Rate | 0.00 | 0.00 | 25.52 | 34.03 | 35.53 | 36.53 | 33.55 | 1.74 | 4.23 | 39.52 | 4.35 | 4.47 | 10.86 | $59.20 |  |  |
| IRONWORKER | Crew Mix | 0.0 | 0.0 | 0.9 | 7.9 | 1.0 | 0.5 |  |  |  |  |  | 50.92% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 22.13 | 29.50 | 31.00 | 32.00 | 29.14 | 1.52 | 3.68 | 34.34 | 3.78 | 17.49 | 8.74 | $64.35 |  |  |
| LABORER | Crew Mix | 0.0 | 0.0 | 1.0 | 9.0 | 1.0 | 0.0 |  |  |  |  |  | 13.62% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 17.69 | 23.58 | 25.08 | 26.08 | 23.18 | 1.21 | 2.93 | 27.32 | 3.01 | 3.72 | 6.29 | $40.34 |  |  |
| MECHANIC | Crew Mix | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 0.0 |  |  |  |  |  | 11.32% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 20.00 | 26.66 | 28.16 | 29.16 | 26.66 | 1.39 | 3.37 | 31.42 | 3.46 | 3.56 | 4.53 | $42.97 |  |  |
| MILLWRIGHT | Crew Mix | 0.0 | 0.0 | 1.0 | 8.6 | 1.0 | 0.5 |  |  |  |  |  | 11.32% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 25.01 | 33.35 | 34.85 | 35.85 | 32.88 | 1.71 | 4.15 | 38.74 | 4.26 | 4.39 | 7.70 | $55.09 |  |  |
| OPERATOR, HEAVY | Crew Mix | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 0.0 |  |  |  |  |  | 11.32% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 21.76 | 29.01 | 30.51 | 31.51 | 29.01 | 1.51 | 3.66 | 34.18 | 3.76 | 3.87 | 4.17 | $45.98 |  |  |
| OPERATOR, LIGHT | Crew Mix | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 0.0 |  |  |  |  |  | 11.32% |  |  |  |  |

|  | Base Rate | 0.00 | 0.00 | 19.13 | 25.50 | 27.00 | 28.00 | 25.50 | 1.33 | 3.22 | 30.05 | 3.31 | 3.40 | 4.69 | $41.45 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PIPEFITTER | Crew Mix | 0.0 | 0.0 | 0.7 | 6.3 | 1.0 | 0.3 |  |  |  |  |  | 6.92% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 27.79 | 37.05 | 38.55 | 39.55 | 36.54 | 1.90 | 4.61 | 43.05 | 4.74 | 2.98 | 10.86 | $61.63 |  |  |
| PAINTER | Crew Mix | 0.0 | 0.0 | 0.4 | 3.8 | 1.0 | 0.0 |  |  |  |  |  | 16.37% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 17.34 | 23.12 | 24.62 | 25.62 | 22.94 | 1.19 | 2.90 | 27.03 | 2.97 | 4.42 | 2.46 | $36.88 |  |  |
| REBAR | Crew Mix | 0.0 | 0.0 | 1.1 | 10.0 | 1.0 | 0.1 |  |  |  |  |  | 13.62% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 22.13 | 29.50 | 31.00 | 32.00 | 28.97 | 1.51 | 3.66 | 34.14 | 3.76 | 4.65 | 8.74 | $51.29 |  |  |
| RIGGER | Crew Mix | 0.0 | 0.0 | 0.8 | 7.6 | 1.0 | 0.5 |  |  |  |  |  | 14.69% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 22.13 | 29.50 | 31.00 | 32.00 | 29.15 | 1.52 | 3.68 | 34.35 | 3.78 | 5.05 | 8.74 | $51.92 |  |  |
| TRUCK DRIVER | Crew Mix | 0.0 | 0.0 | 0.2 | 1.4 | 1.0 | 1.0 |  |  |  |  |  | 11.32% |  |  |  |  |
|  | Base Rate | 0.00 | 0.00 | 15.18 | 20.24 | 21.74 | 22.74 | 21.13 | 1.10 | 2.67 | 24.90 | 2.74 | 2.82 | 3.77 | $34.23 |  |  |
| WELDER ALLOY | Crew Mix | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 0.0 |  |  |  |  |  | 6.92% |  |  |  |  |
| use Pipfitter | Base Rate | 0.00 | 0.00 | 27.56 | 36.75 | 38.25 | 39.25 | 36.75 | 1.91 | 4.64 | 43.30 | 4.76 | 3.00 | 10.86 | $61.92 |  |  |
| WELDER STRUCT | Crew Mix | 0.0 | 0.0 | 0.0 | 1.0 | 0.0 | 0.0 |  |  |  |  |  | 50.92% |  |  |  |  |
| use Ironworker | Base Rate | 0.00 | 0.00 | 25.54 | 34.05 | 35.55 | 36.55 | 34.05 | 1.77 | 4.30 | 40.12 | 4.41 | 20.43 | 8.74 | $73.70 |  |  |