| Earnings |  |  |  |
| --- | --- | --- | --- |
| Achieve audit clearance for the booking of the gain on a Base Gas sales transaction. | Earnings of at least the NBV of the deal to be booked in 2000. | Complete 2nd Qtr 2000 recognizing full gain. | 2nd Qtr. 2000 |
| Implement early adoption of FAS 133 for Citrus Trading (Saunders) | Independent auditor acceptance of $46 million pretax Citrus income recognition due to change in accounting for Citrus Trading operations to comply with management’s interpretation of FAS133 requirements. | Auditor sign-off complete and will occur in the 3rd Quarter 2000 | 2nd Qtr. 2000 |
| Sunniland (Ballentine): - Complete definitive Agreement, - Close Transaction to avoid $6MM write-off | - Date of Signed Agreement - Receipt of assets to save the recognition of a $6MM loss through bankruptcy. | - Complete 2nd Qtr 2000 - Complete 2nd Qtr 2000 | - 1st Qtr. 2000 - 2nd Qtr. 2000 |
| Develop a structure to allow the recognition of a sale of a NNG asset for a $10 MM gain (Hayslett) | Complete definiton of the structure necessary to allow the gain to be recognized. | Complete in first quarter. | 1st Qtr. 2000 |
| Develop the capability to write-off the remaining Brooker assets with no adverse impact (Geaccone) | Write-off assets while maintaining targets | Complete. | 1st Qtr. 2000 |
| Reduce the Net MMF charges from corporate so that the amount is essentially flat to 1999 charges. (Hayslett+) | Achieve a $2.5 MM reduction. | On target through 7 months for $2.5 MM | Full year 2000 |
| Assist in the completion of recognition of a gain from the sale of excess undervalued inventory. (Hayslett ) | Achieve book recognition of $15MM of earnings. | On target, | 3rd Qtr 2000 |
| Develop a plan to reduce Corporate Charges by $2.5MM/yr (Hayslett) | Presentation of plan to management | Completed | 1st Qtr 2000 |
| Execute Plan to reduce corpoarate Charges by $2.5MM/yr (Hayslett) | Achieve $2.5MM reduction. | On target thru 7 months for $2.8 MM | Full Year 2000 |

| Other |  |  |  |
| --- | --- | --- | --- |
| Put long term borrowing facilities in place supporting Phase IV and Phase V expansions, Expansion and refinancing at Border and replacement in Tranwestern (Hayslett + ) | Completed bank/lender documentation at acceptable amounts and costs | Plan is in place and we are on target for November 1, close. Management decision to delay financing to create an opportunity for AFUDC of $18MM has moved the transaction to a 4th Qtr 2000 transaction. | 4th Qtr. 2000 |
| Complete transition to new accounting system in 2000 (Saunders) | Use of system for all financial activity | Complete July 2000 | 3rd Qtr. 2000 |
| Reduce Construction Overheads to be Charged in 2000 on NNG (Hayslett) | Cleaning out of Account in 1999 of about $9.5 MM | Complete February 2000 | 1st Qtr. 2000 |
| Complete a Restacking Plan for GPG in the Enron Building (Hayslett) | Plan submitted for review and approval. | Plan reviewed and decision to wait unitl 2001 made. Currently beginning planning for 2001 restacking. | 2ndQtr. 2000 |
| Complete a review of the insurance program and make a recommendation to management. | Recommendation submitted for review and approval. | Insurance Program reviewed and recommendation is in process. | 3rd Qtr. 2000 |
| Develop a Solution to the problem of the lack of management reporting in SAP. | Reports in place. | Nearly complete. Short term solution is working and am leading an Enron wide project to solve the same problem with expected completion in september of Phase 1. | 3rd Qtr 2000 |
| Assist Azurix with development of a restucturing program for Wessex | Participation in process. | Participated in the development of term sheets for the operational restucturing of the water company. | 3rd Qtr 2000 |