| # LNG Weekly Report Week Ending 08/17/01 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # | Responsible/Date |  | Project |  | Description |  | Activity |
| A |  |  | Eastern Hemisphere Origination |  |  |  |  |
| ##### A.1 |  |  | ##### Merchant Trading |  |  |  |  |
| ##### A.1.a | Harris / August 17 |  | ADGAS |  | - Uncommitted capacity of 300,000 to 500,000 mta plus any unused DPC volumes (up to another 500,000 mta). Also ex-ship capacity subject to TEPCO annual program. - Master Ex-ship agreement in place. |  | - All terms and wording, except treatment of “failure to deliver”, finalized. - Arcos Term Sheet submitted 2/15. Have advised Adgas that a revised term sheet will be submitted in the very near future to address revised project timing and pricing. - General review meeting held with Adgas staff on Aug 6th. |
| ##### A.1.b | Harris / August 17 |  | Oman LNG |  | - OLNG has requested proposals for uncommitted capacity and from a proposed third train. - Master FOB agreement in place. |  | - Arcos Term Sheet submitted 2/15. Discussions on hold pending resolution of TPA issues in Spain. - Submitted proposal for FOB purchases on the Hoegh Galleon and Excalibur. Will meet with OLNG and consultant on Aug 22nd. - K Acacia spot cargo loaded on July 27 for delivery to Lake Charles. - Unable to market Hanjin Muscat spot cargo into Europe. |
| ##### A.1.c | Harris / August 17 |  | ### RasGas |  | - Uncommitted capacity of over 2 million tons from Ras Laffan and QatarGas plants. |  | - Arcos Term Sheet submitted in late January. Follow up meetings will be scheduled when RasGas staff return from summer leave. |
| ##### A.1.d | Harris / August 17 |  | Japanese Trading Companies |  | - Expand close relationships with Mitsubishi and Nissho Iwai into formal agreements for merchant transactions. - Further develop new relationships with Itochu and Mitsui. |  | - Nissho Iwai: Next round of discussions with NIC’s LNG group to be held in Tokyo later this month (comments on the draft master ex-ship contract with Enron as Seller, West Coast terminal development and possible other areas of cooperation). - Mitsubishi: Discussing possible areas of cooperation in merchant LNG trading activities. CA under internal review. Ex-ship version of master spot contract tabled. - Itochu: Itochu is still reviewing Enron-tabled master contracts and would like to meet in late August to discuss. - Mitsui: Discussions on Enron-tabled master ex-ship contract (Enron as Buyer) under way. Next meeting to be held in late August. |
| ##### A.1.e | Rao /August 17 |  | North West Shelf/Australia |  | - Purchase of spot cargoes. |  | - Meeting held with NWS in mid June to discuss Master Spot Agreement - Plan to meet again in September for further discussions |
| ##### A.1.f | Rao / August 17 |  | ### Pertamina Master Agreement |  | - Bontang has uncommitted capacity of over 2 million tons. - Potential supplier of spot cargoes in ’02 and supply for West coast US project. |  | - PT Arun likely to start by 13th Aug. - Change in Pertamina org: Mr Javed Sumbung taking over the LNG dept, starting September - Will be issuing a revised draft to Pertamina and Bontang PSC’s by August end. - Next meeting to discuss Master Agreement on a more formal basis with Pertamina & the PSCs will occur in Sept. |
| ##### A.1.g | Rao /August 17 |  | MLNG/Malaysia |  | - Spot Cargoes Purchase in 02 - West Coast USA LNG Purchase |  | - Mark-up Mater SPA draft to be sent to MLNG the week of Aug 21 |
| ##### A.1.h | Rao / August 17 |  | KOGAS |  | - KOGAS merchant opportunities - Sale of spot cargoes in winter 2001 period |  | - Met with Kogas in mid June, no major issues regarding the forwarded Master Spot Agreement. Kogas will be forwarding formal comments shortly. - Kogas has confirmed their interest in finalizing a spot agreement but will not know their winter requirements until August/September. |
| ##### A.1.i | Gerych / August 17 |  | #### Osaka Gas Merchant Opportunities |  | - Diversion/repurchase of three OG excess cargoes from OLNG in winter 2001/2 period - Operational agreement to share LNG shipping and storage - Swap for Middle East/Japan LNG |  | - Prospects for a three-cargo diversion later this year seem remote. Developing strategy for continuing relationship. - Confidentiality agreement is under internal review |
| ##### A.2 |  |  | ##### DPC LNG Supply |  |  |  |  |
| ##### A.2.a | Harris / August 17 |  |  |  | - MSEB has rescinded the PPA and stopped dispatching power on May 29th. DPC issued the Preliminary Termination Notice on May 19th triggering a six month cure period. - GOI is discussing possible “buy-out” of Enron, Bectel, and GE interests in Dabhol. |  | - Arbitration proceedings with GoM and GoI are in progress. Petition has been filed with Indian Supreme Court seeking a ruling on the jurisdiction of MERC. - Supreme Court sent case back to Mumbai High Court for a ruling on MERC jurisdiction. |
| ##### A.2.b | Harris / August 17 |  | ### Oman DPC SPA |  | - LNG supply for 1.6 mmta |  | - DPC met with OLNG in Dubai on July 19th and advised OLNG there would be at least a one year delay in the start up of Dabhol. Contractual remedies were not discussed. Working with DPC to prepare a written proposal to DPC on potential mitigation scenarios. - OLNG has sent letter requesting that DPC provide a formal position with respect to offtake. Situation needs prompt action to prevent damaging Global LNG relationship with OLNG. Meeting scheduled for August 20th in London. |
| ##### A.2.c | Harris / August 17 |  | ADGAS DPC SPA |  | - LNG supply for 0.48 mmta |  | - Met with Adgas on Aug 5th to provide update. DPC need to send letter pursuant to SPA providing early warning of situation. |
| ##### A.3 |  |  | ##### Merchant Trading |  |  |  |  |
| ##### A.3.a | Harris / August 17 |  |  |  | - Enron Japan/ EPower - Work with E Power and Enron Japan on merchant terminal opportunities. Provide LNG origination for any requirements. |  | - Evaluating opportunity to work with NIC to jointly develop LNG opportunities in Japan. - Conducted video conference with EJ and NIC on Aug 2nd to discuss possibility of joint cooperation on the UF/E LNG project in Egypt. CA executed, waiting on data package. |
| ##### A.3.b | Gerych /August 17 |  | Mikawa Bay LNG: 1. Terminal/IPP Opportunity in Japan 2. BHP Billiton LNG Supply |  | - Secure access to LNG receiving terminal in Mikawa Bay in Central Japan and to other terminals under development by E Power - Develop LNG supply opportunity from BHP Billiton’s Scarborough and Macedon fields |  | - Provided all required LNG elements for the feasibility study (to be issued soon) - Draft term sheet under review by BHP Billiton (possible supply of up to 3 MMTA to Enron Global LNG with worldwide destination rights; start date of 2007 to coincide with COD of energy projects in Japan or elsewhere) - BHP Billiton asked for a meeting at a later date (mid-September). |
| ##### A.3.c | Rao/Gerych / August 17 | ### Nissho Iwai Partnership |  | - Supporting Enron Japan’s efforts to facilitate a strategic partnership with Nissho Iwai of Japan. Specifically, utilizing NI relationship to penetrate Japanese LNG market and leverage off their asset positions for Global LNG objectives. |  | - Presentation given to Nissho Iwai on July 13th. Several potential opportunities identified including LNG wholesale merchant activities, Jcc hedging for Japanese customers, sub-chartering of capacity on vessels controlled by NI. - Nissho is yet to revert to Enron on some specific questions raised at the presentation. Matsubara-san following up. - Next meet set for mid August. |  |
| ##### A.4 | Rao/August 17 | #### South Korea LNG Terminal |  | - Potential LNG terminal opportunity between SK-Enron and POSCO is southern part of peninsula |  | - Submitted an Enron LNG Qualification paper - to Darrell Kinder - Meeting with POSCO confirmed for August 24 |  |
| ##### B |  |  | ### Atlantic Basin |  |  |  |  |
| ##### B.1 | Arnell / July 27 |  | #### Grand Bahama LNG Terminal |  | - LNG terminal located in Freeport, Grand Bahama and 96-mile natural gas pipeline from Grand Bahama to an FGT interconnect in Broward County, FL (Port Everglades/Fort Lauderdale area). - Initial throughput of terminal (target) = 500 MMSCFD - Pipeline size = NPS 24 - Total Project Cost = $500 MM (terminal plus pipeline, includes soft costs) ## Project milestones Early completion Late completion - Submitted FERC permit application - 19JUL01 - Receive FERC preliminary determination - 1NOV 01 - Receive FERC approval - 1MAY 02 - 1SEP 02 - Issue EPC bid package for terminal - 1APR 01 - 1APR 02 - Receive EPC bids - 1AUG 01 - 1AUG 02 - Award terminal EPC contract - 1SEP 01 - 1SEP 02 - Begin delivering gas to Florida - 1JUL 04 - 1JUL 05 - Complete EPC - 1OCT 04 - 1OCT 05 |  | - FERC and MMS applications submitted 7/19. - EPC bids sent out; IHI dropped out of the bidding. Three remaining companies are: CBI, Skanska, and Tractebel. - HOA with Bahamian government sent out to government 7/26. - Harbour Use Agreement and Addendum to Land Option documents sent out. - Business License with Grand Bahama letter of offer received; currently under negotiation. - Targeting September to hold ‘Town Expo’ for communities surrounding terminal area. |
| ##### B.2 | Webber / August 17 |  | #### Elba Island LNG Terminal |  | - LNG receiving terminal located on Elba Island near Savannah, GA. - Planned reactivation date – October 6, 2001 - 162.8 Bcf (gas equivalent) total firm capacity held by El Paso Merchant Energy (EPME) [Enron sales entitlement = 58 Bcf] - 22 year term - Enron right but not obligation to deliver and sell LNG to EPME at market prices, less fee = share of monthly terminal cost-of-service - Enron right to take redelivery of vaporized LNG at tailgate of terminal and to sell to third parties - Maximum 1075 Btu per cf HHV on LNG receipts |  | - Met with El Paso (Jenkins) on Monday, August 13. Generally outlined Enron’s proposed plan to progress the Definitive Agreement process with El Paso (Selection of Expert, Expert Terms of Reference and Procedures, and Determination of Unresolved Matters). El Paso wants to start with the July 2000 draft Sales and Purchase Agreement as the basis rather than the Term Sheet. - Will formalize our DA process proposal in a letter to El Paso (Jenkins and Eisbrenner) on August 21. - Comments on the US Coast Guard NPRM are being submitted on August 20. Will participate in the revised consensus filing by the Marine Interface Group. The USCG will likely mandate “Made-Up” tugs on vessels passing a moored LNG tanker, based on discussions with the USCG at the Shippers Meeting in Savannah on August 10. - El Paso Merchant is moving to capture the Southern Company power generation demand at McIntosh. - Terminal cool-down cargo now scheduled for late-September. |
| ##### B.3 | Vicens/ Gerstandt/August 17 |  | Jose LNG |  | - 2.1 MTPA LNG liquefaction and export facility in eastern Venezuela - Sponsor : Enron. PDVSA-Gas Venezuela’s national oil company has option to buy into 25% of the project’s equity - Investment: $580 million EPC costs and $220 million of soft costs, including IDC - Natural Gas Supply: 350,000 MMBtus to be supplied by PDVSA - LNG Off-take: Under evaluation. Most likely Enron and PDVSA will be off-takers (under discussion with PDVSA) - Ultimate Markets: US East Coast LNG receiving terminals, Puerto Rico, other Caribbean, Iberia and Brazil |  | - Copy of the gas availability report for 2001 is in our hands. Currently in the process of analyzing results and overall report comments and assumptions, although initial review looks very favorable to export projects; - Apparently and according to PDVSA sources, the commission is reporting findings to the Vice minister all this week. It is possible that next week we can find out what came out of this meetings unofficially. It will take a few more weeks to have an official answer; Development Engineering Update : - Proposal received from Tecnoconsult for Power Survey. - Pre FEED activities identified. - All FEED contractors advised that start date uncertain. |
| ##### B.4 | Sierra /July 27 |  | Puerto Rico #### J00009101XX ##### Expenditure to date: ##### $ _____ Burn rate: $ _______ /mth |  | - EcoElectrica Management - EcoElectrica Ownership Transaction |  | - Facility Availability 100% for the week. - EcoElectrica has maintained lower excess generation pricing to $5.30/mmBtu to see if PREPA will raise the dispatch. Dispatch forecast is 76%. So far limited Excess LNG has been sold. - Did not execute agreement for Enron supply of a sport cargo for late July 2001. Cost of tug service was excessive and made the transaction uneconomic. Next LNG delivery forecast for mid August (under the Cabot contract). - Agreement regarding sale of EcoElectrica Ownership completed. Efforts now focused toward completing requirements for closing transaction (approvals, opinions, consents, PR management) - Developed plans for commercial management of EcoElectrica until completion of the transaction. - Continued to efforts to manage key commercial issues that may affect the transaction - Credit Agreement Term Out, PREPA issues, EPC close out, insurance matters, and Eco personnel. |
| ##### B.5 | Whitehead/Harris August 17 |  | ### Nigeria LNG |  | - Long Term LNG purchase - Start date April 2005 - CIF deliveries to US and Med. |  | - New MOU initialed 15th Aug - Existing MOU cancelled and replaced with 4 BCM @91.5% Nymex. Destination flex on 100% of volume to NA and Europe - Signature meeting to be held late Aug |
| ##### B.6 | Whitehead / August 17 |  | ##### Lake Charles Capacity |  | - Secure Capacity from BG for Lake Charles |  | - Met with Simon Bonini Aug 3 - BG Interested in selling Lake Charles capacity until 05 or 09 for the HG and Exc. - BG to revert with a proposal mid August |
| ##### B.7 | Arnell / July 27 |  | ### Angola LNG |  | - Long Term LNG Purchase - 2.1 MMTA with option to increase to 3.0 MMTA, 20 years, North America deliveries are NYMEX related, start date April 2005 |  | - No formal response to LOI sent to Angola on 7/06 but phone call from Mike Sinclair was positive; decision will be going to board soon. - They are offering 2.1 MMTA but want the firm option to increase that up to 3.0 MMTA. They would like to hold this option right up until the time of signing the SPA which they are targeting March '02. - They want a firm right to deliver 1.2 MMTA to Elba if the Bahamas does not go ahead. |
| ##### B.8 | Whitehead/ August 17 |  | Egypt LNG |  | - Long Term LNG Purchase |  | - Frevert visiting EGPC Chairman and Energy Minister in Cairo on Aug 27th - New term Sheet sent Aug 2nd |
| ##### B.9 | Whitehead/ August 17 |  | TotalFinaElf |  | - Short term sale of LNG on Hoegh Galleon, Middle East to Spain & France |  | - In the final stages of signing a master agreement - TFE have given us a bid for the HG into Spain. Needs reworking into an FOB term sheet for Oman |
| ##### B.10 | Whitehead/ August 17 |  | Gas de France |  | - Two Year terminal access to Montoir - Gas Swap to NBP or Zeebrugge |  | - Met with GdF on July 24th. They expressed a great deal of interest. - Term Sheet due to GdF by end August |
| ##### B.11 | Gerych/August 17 |  | West Coast LNG - USA |  | - Develop LNG Terminal(s) on U.S. West Coast |  | - Defining relationship with Merlin (FSRU), addressing design issues (dynamic simulation study, LPG extraction) - Engaged PTL on Oregon/Washington siting - Developing economic models, gathering comparative data for U.S. and Mexican sites - Reviewing permitting agencies - Weekly conference calls resume next Wednesday |
| ##### B.12 | Curran/August 17 |  | West Coast LNG - Baja California |  | - Develop LNG Terminal in N. Mexico |  | - Site visit held on August 10 - Finalizing partnership agreement with Cal-Mex - Sent due diligence questionnaire to Cal-Mex |
| ##### C |  |  | LNG Shipping |  |  |  |  |
| C.1 | Whitehead/ August 17 |  | Lakshmi |  | - Ownership JV and Time Charter of one 135,000 cm LNG ship for the Dabhol Power Company Project in India. |  | - DPC have not exercised their option to extend - Key Dates: Oct 21st: End of PCA period, Nov 15th: Current Vessel delivery date - Discussions to commence with MOL with regards to next steps - Vessel 98% completed. Sea Trials set for end of August. |
| C.2 | Galt / August 17 |  | Hoegh Galleon |  | - Time Charter of one 87,66 cm LNG ship for Enron Merchant trade. |  | - Vessel discharged 3rd cargo at Lake Charles on July 31. - Vessel in transit to Oman. ETA August 25th. |
| C.3 | Galt / August 17 |  | Excalibur |  | - Time Charter of one 138,000 cm LNG ship for Enron Merchant trade. |  | - Vessel construction on schedule. - Enron consultant in the shipyard to be de-mobilized on Sept 22. - Cargo pump tests start Aug 20 at Ebara in Nevada. - Next quarterly technical meeting to be held the week of Sept. 17. |
| ### D |  |  | ### Fuel Management |  |  |  |  |
| ##### D.1 | Y’Barbo / August 17 |  | EcoEléctrica #### E00041201XX ##### Expenditure Year to date: ### $69,134 ### Burn rate: $ 13,827 /mth Fuel Management fee covers expenses |  | - Fuel Management for EcoEléctrica /Cabot LNG SPA |  | - Current schedule of LNG deliveries: - Discharged ~120,000 CBM from Matthew on August 16th - Expect 119,000 CBM approx. September 24th - Both combustion turbines in service - “Excess LNG” offered to PREPA at $5.18/MMBtu – 8/16/01 - Price of non-Winter Cargo LNG is $3.483/mmbtu for all 2001 (does not include the demand charge of $0.846/mmbtu) - Work on COU agreement still in progress - Working on feasibility of buying some non-Cabot LNG in both 2001 and 2002 - Non-binding estimate of the quantity and timing of plant LNG requirements for 2002 pending Cabot’s delivery of maintenance schedule for Trinidad and the Matthew |
| ##### D.2 | Y’Barbo / August 17 |  | DPC #### E00017801XX Expenditure year to date : $ 86,286 ### Burn rate: $ 17,257 /mth |  | - Fuel Management for DPC of LNG SPA’s |  | - Work related to OLNG and ADGAS supply contracts on hold. - No further mention by OLNG of visit to Houston in first half of July - DPC to take delivery of Lakshmi on November 15th. |
| ##### E |  |  | ### Other |  |  |  |  |
| ##### E.1 | Galt / August 17 |  | ### DPC Project Harbor/Terminal Support 061P –C000194102XX ##### Expenditure to date: $ _____ Burn rate: $ _______ /mth |  | - Provide LNG support services to the DPC LNG Terminal project including tugs, harbor and berth procedures, etc. |  | - Tug construction is on schedule. - Pilot training program tested on Aug. 2. Minor modification required to complete program. Changes to be made by end of Aug. |
| E.2 | Galt / August 17 |  | ### EcoElectrica Harbor/Terminal Support ##### 067S-E00018301XX ##### Expenditure to date: ##### $ _____ Burn rate: $ _______ /mth |  | - Provide LNG support service to the EcoElectrica LNG Terminal project including harbor and berth procedures and USGC Support |  | - No activity in consideration of pending sale of facility. |
| ### F |  |  | ### Greg Curran |  |  |  |  |
| ##### F.1 | Y’Barbo / August 17 |  | Grand Bahama LNG Terminal |  | - LPG Extraction and Marketing |  | - Estimate production of 240,000 MT C3 and 160,000 MT C4 per year assuming 500,000 MMBtu/d pipeline sendout and “average” Nigerian LNG quality - Evaluating max/min C2, C3, C4’s based on Nigerian MOU quality specs - Evaluating freight cost and plant cost |