|  | PROJECT | LEGAL | TAX | COMMERCIAL | PROJECTED DEADLINE | STATUS |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Argentina: evaluate (i) Master Services Agreement between ENA and Enron Comercializadora de Energia Argentina S.A. and (ii) proposed Trading Guidelines | B. Hendry S. Shackleton | L. Aven R. Hopkinson | Don Black | 11/99 | Sara/Brent/Lynn reviewing Trading Guidelines for B.A. and Houston offices. |
| 2. | Bolivia: financial trading questionnaire Physical trading questionnaire | B. Hendry S. Shackleton | L. Aven R. Hopkinson | Don Black | unknown | Brent assessing physical requirements. No work on financial |
| 3. | Brazil: Brokerage Accounts - Enron Power Holdings XII Ltd. (“EPH”) - Others (?) | S. Shackleton M. Heard |  | Bruce Harris | 10/15/99 | EPH account opened with Morgan Stanley & Co. Inc. on 10/28/99 |
| 4. | Brazil Trading: Cross-border and CC-5 accounts, Local Derivatives, Pure OTC Swaps | A. Bertone B. Hendry S. Shackleton | L. Aven | Bob Crane Bruce Harris Gary Hickerson Joe Kishkill | 10/99 | Met w/Tozzini on 11/30/99 in Sao Paulo. Should receive response by 12/31/99 and can assess need for further work.. |
| 5. | Brazil Transactions: - Millennium Put - Votorantium Celulose e Papel | A. Bertone R. George S. Shackleton A. Bertone B. Hendry S. Shackleton | L. Aven L. Aven | Mike Guerriero | 10/1/99 (Stage 1) |  |