|  | Arbitration Options |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Arbitrate our right to terminate - we seek only the confirmation that we have the right to terminate given Furnas’ past actions. | Suspends right to terminate during Arb Default continues until cured or contract terminated | -It is preemptive -Furthers default strategy -Avoids appearance of weakness evident in default extensions -Buys time to refine region’s Cuiaba strategy -Will Save time if we terminate because Furnas will elect this option as their initial defense - Will allow us to see Furnas’ perceived defenses | - if we lose, may have no other remedies - If we lose could not pursue strategy of putting EPE to Furnas | -Furnas may sign Consent & Additivo #4 - Furnas may proceed to arbitrate | -Per PPA clause 103: 1. Send Registered Letter 2. 30 days to respond 3. 15 days - appoint 3rd 4. 90 days to arbitrate -Final step is litigate to enforce arbitration result. | YES | YES |
|  | Arbitrate to force specific performance by Furnas to sign current Consent | In lieu of termination Default continues until Consent signed Termination would remain remedy if Furnas fails to honor positive judgement | - Avoids appearance of weakness evident in default extensions -Buys time to refine region’s Cuiaba strategy - Would force Furnas to address our issue without inserting theirs into discussion - Would clarify key legal concept for all options | -may cause consent to become uncoupled from Eletrobras Guar issue (Additivo 4) | -Furnas may sign Consent & Additivo #4 - Furnas may proceed to arbitrate -Furnas alleges our repeated revisions caused delay - Furnas asserts other factors inhibited financing | -Per PPA clause 103: 1. Send Registered Letter 2. 30 days to respond 3. 15 days – appoint 3rd 4. 90 days to arbitrate - Final step is litigate to enforce arbitration result. | No | (?) |
| 2 | Arbitrate to force specific performance by Furnas to sign the original consent from Assumption Agreement | In lieu of termination Default continues until Consent signed Termination would remain remedy if Furnas fails to honor positive judgement | - Would force Furnas to address our issue without inserting theirs into discussion - Would clarify key legal concept for all options - Eliminates argument that repeated revisions caused delay | -may cause consent to become uncoupled from Eletrobras Guar issue (Additivo 4) - Lenders lose desirable provisions negotiated in interim | -Furnas may sign -Furnas may proceed to arbitrate Furnas asserts other factors inhibited financing | -Per PPA clause 103: 1. Send Registered Letter 2. 30 days to respond 3. 15 days – appoint 3rd 4. 90 days to arbitrate - Final step is litigate to enforce arbitration result. | No | YES |
| 3 | Arbitrate our right to damages | Seeks economic compensation in lieu of termination Default continues in interim Termination could occur without resolution. | - Clarifies that there is a cost associated with delay in providing Consent - Avoids appearance of weakness evident in default extensions - Determines Compensation for increased legal and capital costs | -does not address lender issues - Eliminates strategy of putting EPE to Furnas | -Furnas may sign -Furnas may proceed with arbitration - Furnas asserts other factors inhibited financing | -Per PPA clause 103: 1. Send Registered Letter 2. 30 days to respond 3. 15 days - appoint 3rd 4. 90 days to arbitrate - Final step is litigate to enforce arbitration result. | NO | NO |
|  | Litigation Option |  |  |  |  |  |  |  |
| 4 | Litigate to force specific performance by Furnas to sign the original consent from Assumption Agreement | In lieu of termination Default continues until Consent signed Termination would remain remedy if Furnas fails to honor positive judgement | - Would force Furnas to address our issue without inserting theirs into discussion - Would clarify key legal concept for all options (affirmative obligation to provide Consent) - Could be speediest approach if injunctive | - may cause consent to become uncoupled from Eletrobras Guar issue - Lenders lose desirable provisions negotiated in interim | --Furnas may sign Consent & Additivo #4 -Furnas could demand arbitration first | -Under PPA Arbitration Provision, litigation may not be immediate option. -If Furnas agrees: 1. Submit injunctive relief 2. 2 weeks to see if works 3. Otherwise, timing unknown. | YES | YES |
|  | Economic Equilibrium |  |  |  |  |  |  |  |
| 5 | Submit economic equilibrium claim* to compensate for extended use of Sponsor equity capital without interrupting termination procedure. | Seeks economic compensation in lieu of termination Default continues in interim and Termination could occur without resolution. | -Clarifies that there is a cost associated with delay in providing Consent - Avoids appearance of weakness evident in default extensions | -Time consuming if only option pursued -Furnas will act only thru arbitration or litigation | -Furnas ignores us -Furnas reviews claim and says “NO” -Furnas alleges our repeated revisions caused delay - Furnas asserts other factors inhibited financing - Arbiter may rule that this is a claim for damages and throw out (although Tozzini believes low probability) | -Under PPA EE provision: 1. Submit request w/ damage calculation 2. Timing unknown | NO | Maybe |
|  | Other Options |  |  |  |  |  |  |  |
| 6 | Discontinue default notice and continue negotiations with Furnas |  | - Contributes to amicable long term relationship - May achieve other contractual benefits such as converting to a financial contract | -EPE Foregoes right to terminate - May introduce spot market liability as additional impediment to financing | - Furnas may negotiate in earnest - Furnas may drag out or wait on responses from ANEEL | PPA provisions relating to EE do not specify times for response or resolution. | ? | YES |
| 7 | Extend default period/delay termination notice (monthly, up to 6 months) |  | -Buys time to refine strategy -Does not impact our ability to terminate if < 6 mos. | -appearance of weakness -may lose our credibility | -Furnas may continue to ignore us | Extend monthly, up to 6 months. | ? | ? |