# GALLUP, NEW MEXICO

ELECTRIC MOTOR DRIVER AND SUBSTATION POWER FACILITIES

ENGINEERING, PROCUREMENT, AND

# CONSTRUCTION AGREEMENT

| 1. PARTIES Owner: Contractor: | ENRON COMPRESSION SERVICES COMPANY, a Delaware Corporation (which expression shall include successors and permitted assigns); and ENRON ENGINEERING & CONSTRUCTION COMPANY, a Delaware Corporation (which expression shall include successors and permitted assigns) |
| --- | --- |
| 2. OWNER'S REPRESENTATIVE: | Owner shall, by notice in writing to the Contractor, appoint a person to act in the capacity of the Owner's Representative with full authority to act on behalf of the Owner under this Agreement. |
| 3. CONTRACTOR'S REPRESENTATIVE: | The Contractor shall, by notice in writing to the Owner, appoint a person to act in the capacity of the Contractor's Representative with full authority to act on behalf of the Contractor under the Agreement. |
| 4. SCOPE OF WORK: | The facilities to be constructed on behalf of Owner consist of the electric tap and transmission line from Continental Divide Electric Cooperative, Inc. to the high side of the electrical substation, the electrical substation, variable speed drive and, the electric motor and the, drive shaft and gearbox (the "Owner's Facilities") at the point of connection to Tranwestern Pipeline Company's ("TW") Compressor at TW's Gallup Electric Compressor Station located on Contractor's TW's San Juan Lateral in McKinley County, New Mexico(Owner's Facilities). Constructor shall cause Owner's Facilities to be procured, constructed, installed, tested, and made available for service (the "Work"). Contractor shall mobilize for the Work, demobilize after the Work is complete and shall provide such supervisory, administrative, technical and other services as shall be required for the installation of Owner's Facilities. Such Work shall include, but is not specifically limited to, design of facilities, procurement of all materials, securing of all permits required of Contractor for its performance of the Work, installation of temporary fences, clearing the right-of-way, grading, loading and transporting of materials, installation, construction supervision, final grading and site clean-up and return of all unused material. Constructor shall perform its services the Work and fulfill its responsibilities hereunder, and shall require all consultants, contractors, subcontractors and materialmen furnishing labor, material or service for the design, construction, installation, and testing of Owner's Facilities to carry out their responsibilities in a good, workmanlike manner, in accordance with Contractor's practices and standards, the approved practices and standards of the industry, and the Scope of Work in compliance with all applicable federal and state laws and applicable regulations of governmental bodies having jurisdiction. Owner shall have the right to review and approve the Contractor's plan for the design, construction, installation, and purchase of Owner's Facilities prior to construction, purchase, and/or installation. |
| 5. PRICE: | Contractor estimates that the total costs for the Scope of Work as defined in Section 4 of this Engineering, Construction, and Procurement Agreement at $_______________. Contractor acknowledges that the above estimated costs is a +/-5% estimated based upon Contractors good faith and expertise. 6. PAYMENT: The Price shall be due and payable by Owner to Contractor within 30 days following Owner's final acceptance of the Work. Owner shall reimburse the Contractor for all costs incurred by Contractor in the performance of the Work and shall pay the Contractor a fixed fee of $100,000 (the "Contractor's Fee") for the Contractor's management and performance of the Work. |
| 6. PAYMENT: | Contractor shall invoice the Owner for costs incurred in the performance of the Work as such costs are incurred by Contractor in accordance with the Contractor's commitment schedule. Such invoice shall be payable by Owner within 30 days of Owner's receipt thereof. The Contractor's Fee shall be due a payable by Owner within 30 days following first beneficial use of the Owner's Facilities and completion of 48 hours of reliable operation of the Owner's Facilities (the "Reliability Test") Late payments shall accrue interest at the rate of one (1) percent per month or portion thereof. |
| 7. SCHEDULE: | Contractor, with Owner's full cooperation, shall perform the Work at such a rate of progress as necessary to complete the Work for first beneficial use by Owner on or before May 1, 2000 (the "Work Completion Date"). |
| 8. WARRANTY: | Contractor warrants that its design, materials and workmanship shall be free of defects for the hereby assigns to Owner, all warranties applicable to the Work and the Owner's Facilities including, without limitation, equipment manufacturer warranties and subcontractor warranties for design, construction, installation, and workmanship. Contractor shall manage, on behalf of Owner, and assist Owner with any warranty claims for a period of one (1) year from final completion and acceptance of the Work, subject to normal wear and tear, and proper operations. Contractor shall cause any equipment manufacturer warranties to be assigned to Owner. the date of completion of the Reliability Test. |
| 9. OWNER'S RESPONSIBILITIES: | The Owner shall be responsible without charge for furnishing to the Contractor upon request all such information, data, drawings, and documents as are in the possession or control of the Owner, and which the Contractor may reasonably require, in order to enable it to perform the Work. Owner shall be responsible for assisting Contractor in securing all permits required of Owner for the Work by regulatory authorities with jurisdiction over the Work. Contractor represents that it shall comply with all terms of the permits and shall assure compliance with such permits by its subcontractors. |
| 10. TERMINATION: | Unless otherwise provided in this Agreement, in the event that one of the following occurs, the non-defaulting party may terminate this Agreement by giving written notice of termination to the other party which shall specify in reasonable detail the circumstances giving rise to the termination notice, along with the effective date of the termination: (a) the bankruptcy, insolvency or dissolution of a party; (b) a material failure by a party to perform any of its material obligations under this Agreement (including payment obligations), unless such party has cured its breach within thirty (30) days of its receipt of written notice from the other party demanding such cure. |
| 11. INDEMNITY: | Subject to the provisions of Limits of Liability, each party agrees to defend, protect, release, indemnify, and hold the other party, its officers, directors, agents, and employees, and its affiliates, their respective officers, directors, agents, and employees, harmless from and against any and all losses, damages to persons or property, injuries, or deaths of persons, liability, claims, liens, demands, and causes of action of every kind and character, including environmental liability, and including the amounts of judgments, penalties, interest, court costs, and legal fees incurred by that party, its affiliates or their respective officers, agents, and employees in defense of the same arising in favor of any person, corporation, or other entity, including the parties hereto and their employees, contractors its servants or agents which arise out of a breach by the indemnifying party of any obligation under this Agreement, and third party, excluding any damages, losses, or claims arising out of the negligence of or willful misconduct of the indemnified party. |
| 12. LIMITS OF LIABILITY: | Neither Owner nor Contractor shall be liable to the other by way of indemnity or by reason of any breach of this Agreement or of statutory duty or by reason of tort (including but not limited to negligence) for any loss of profit, loss of use, loss of production, loss of contracts, or for any similar financial or economic loss or for any indirect or consequential damage suffered by the other, provided that the foregoing shall not affect any liability that the Contractor may otherwise have in respect of remedying physical damage or defects in any works carried out pursuant to the Work or the cost of doing so. |
| 13. FORCE MAJEURE: | In this Agreement, "Force Majeure" means any event or circumstance (or combination of events and/or circumstances) beyond the control of the affected party including: (a) explosions, fires, nuclear radiation contamination, hurricanes, earthquakes, floods, natural disasters, epidemics, other acts of God, and any other similar circumstances; (b) war and other hostilities (whether declared or not), revolution, public disorders, insurrection, rebellion, sabotage, acts of public officials, or terrorist action; (c) any action or relative material inaction taken by any national or local government or judicial authority after the date of this Agreement including without limitation any order, legislation, enactment judgment, ruling or decision; and (d) national or regional strikes which are not specific to the Site. No party shall be considered to be in default or in breach of its obligations under this Agreement to the extent that performance of such obligations is prevented by any circumstances of Force Majeure which arise after the date of this Agreement. |
| 14. INSURANCE: | Contractor shall maintain in effect and shall require that all contractors and subcontractors performing services in connection with the Work carry and maintain the minimum insurance coverage set forth in Exhibit "1", which shall be subject to Owner's approval as to form, amount and issuing company. Contractor shall cause all contractors and subcontractors performing services in connection with the Work to comply with all "Additional Requirements" provisions of Exhibit "1" and said provisions are hereby incorporated in this Paragraph 14 as if fully set forth herein. Contractor shall submit to Owner at the time Contractor executes this Agreement, require such contractors and subcontractors to produce a Certificate of Insurance, in form satisfactory to Owner, evidencing that satisfactory coverage of the type and limits set forth hereinabove are in effect. |
| 15. TITLE AND RISK OF LOSS: | (a) Contractor shall be responsible for and be obligated to replace, repair, or reconstruct the Work and any material, equipment, or supplies furnished for the Work which is lost, damaged or destroyed prior to transfer of care, custody and control thereof to Company Owner which transfer of care, custody, and control shall be deemed to occur at the point in time when natural gas is first introduced into the Facility upon completion of the Reliability Test; provided, however, that Contractor shall not be liable for any damage to the Work caused by Company Owner or persons under the direction or control of Company Owner. (b) Title to the Work or any part thereof shall pass to Company Owner when payment for the Work or any part thereof is made. The provisions of Section 15(a) shall govern the risk of loss under this Agreement, notwithstanding the provisions of this Section 15(b) respecting the passage of title. |
| 16. INDEPENDENT CONTRACTOR: | The Work herein provided for shall be performed by Contractor as an independent contractor, and Contractor has full power and authority to select the means, methods and manner of performing the Work, and Contractor is responsible to Owner only for the results herein contracted. Contractor shall not represent itself to third persons to be other than an independent contractor to Owner. |
| 17. GOVERNING LAW: | This Agreement is made under and shall be governed by the laws of the State of Texas, without regard to the conflict of law principles thereof. |
| 18. ASSIGNMENT: | This Agreement shall be binding upon and inure to the benefit of the respective successors and assigns of the Owner and Contractor. This Agreement may be assigned whole or in part by Owner without prior written approval of Contractor, but may not be assigned by the Contractor without Owner's prior written approval, which shall not be unreasonably withheld. |
| 19. ARBITRATION: | In the event of any dispute or disagreement arising out of or relating to the implementation or performance of this Agreement, which dispute the parties hereto have been unable to settle or agree upon within a period of thirty (30) days after the dispute or disagreement arises, each party shall nominate a senior officer of its management to meet at an agreed time and place not later than forty five (45) days after the dispute or disagreement has arisen to attempt to resolve such dispute or disagreement. Should a resolution of such dispute or disagreement not be obtained within fifteen (15) days after the meeting of senior officers for such purpose, either party may then by notice to the other submit the dispute to arbitration in accordance with the provisions of this Section 19. Any claim, dispute or controversy arising out of or relating to this Agreement, shall be submitted to binding arbitration by the Arbitration Committee of the American Arbitration Association, in accordance with the construction industry rules then in effect. The arbitration hearing shall be held in Houston, Harris County, Texas, on at least twenty (20) business days prior written notice to the parties. There shall be three arbitrators, with each party selecting one; the third arbitrator, who shall be the chairman of the panel, shall be selected by the two party-appointed arbitrators. The claimant shall name its arbitrator in the demand for arbitration and the responding party shall name its arbitrator within thirty (30) days after receipt of the demand for arbitration. The third arbitrator shall be named within thirty (30) days after the appointment of the second arbitrator. The Arbitration Committee of the American Arbitration Association shall be empowered to appoint any arbitrator not named in accordance with the procedure set forth herein. Each arbitrator will be qualified by at least ten (10) years experience in the electric construction and engineering industry. The decision of the arbitrators shall be final and binding upon the parties without the right of appeal to the courts. In deciding the substance of any such claim, dispute or disagreement, the arbitrators shall apply the substantive Laws of the State of Texas; provided, however, except as is otherwise provided in this Agreement, that the arbitrators shall have no authority to award consequential damages or punitive damages under any circumstances (whether it be exemplary damages, treble damages, or any other penalty or punitive type of damages) regardless of whether such damages may be available under Texas Law, the parties hereby waiving their right, if any, to recover consequential damages or punitive damages suffered by the other in connection with any such claims, disputes or disagreements. The award rendered by the arbitrators shall be final and judgment thereon may be entered by any court having jurisdiction thereof. The costs and expenses of the arbitration (including reasonable attorneys’ fees) will be borne by the losing party, unless the arbitrators determine that it would be manifestly unfair to honor this agreement of the parties and determine a different allocation of costs. Pending final resolution of any dispute, whether or not submitted to arbitration hereunder, Owner and Contractor shall continue to fulfill their respective obligations hereunder. |
| 20. EFFECTIVE DATE: | This Agreement shall become effective on the date of last execution. |
| 19 21. ENTIRE AGREEMENT: | This Agreement constitutes the entire agreement of the Parties and supersedes all prior agreements, written or oral, between the Parties or their affiliates with respect to the Work. This Agreement shall not be modified or supplemented except by written instrument duly executed by both Parties. |

IN WITNESS WHEREOF, the undersigned duly authorized Parties hereto have executed this Agreement on behalf of their respective corporation/organization.

ENRON COMPRESSION SERVICES		ENRON ENGINEERING &

COMPANY						CONSTRUCTION COMPANY

Signature:						Signature:

Name:							Name:

Title:							Title:

Date:							Date:

EXHIBIT 1

MINIMUM INSURANCE REQUIREMENTS

#### Worker Compensation and Employers Liability Insurance

Contractor agrees to comply with Workers Compensation laws of the state where the Work is performed, and to maintain a Workers Compensation and Employers Liability policy.    This policy shall be endorsed to provide: all states coverages, voluntary compensation coverages and occupational disease.    If the Work is to be performed on or near navigable waters, the policy shall include coverage for United States Longshoremen's and Harbor Worker's, Death on the High Seas, Jones Act, and all shall contain endorsement for Borrowed Servants.

Workers Compensation		Statutory

Employer's Liability		$1,000,000 Each Accident (Minimum)

$1,000,000 Disease Each Employee

General Liability Insurance

General Liability insurance, endorsed to provide coverage for explosion, collapse and underground damage hazards to property of others; Contractual Liability (particularly the applicable provisions of the "General Indemnity" section of this Agreement); Contractors Protective Liability (if subcontracting is authorized) and Products and Completed Operations (for a minimum of two year after acceptance of the Work).    Watercraft exclusions deleted (if Work necessitates the use of watercraft of any kind).

Bodily Injury				$1,000,000 Each Occurrence (Minimum)

Property Damage			$1,000,000 Each Occurrence (Minimum)

or

Bodily Injury and

Property Damage			$1,000,000 Combined Single Limit Each Occurrence (Minimum)

Automobile Liability Insurance

Automobile Liability insurance which shall include coverage for all owned, non-owned and hired vehicles.

Bodily Injury				$1,000,000 Each Person (Minimum)

$1,000,000 Each Occurrence (Minimum)

Property Damage			$1,000,000 Each Occurrence (Minimum)

or

Bodily Injury and

Property Damage			$1,000,000 Combined Single Limit Each Occurrence (Minimum)

Excess Umbrella Liability Coverage

Bodily Injury and

Property Damage			$10,000,000 Combined Single Limit Each Occurrence (Minimum)

Additional Requirements

Contractor shall require any subcontractor at any tier, vendor, supplier, material dealer and others connected with the Work to provide and maintain insurance at all times during the period that their agreement related to Work under this Agreement is in force and effect at the subcontractor's, vendor's, supplier's, material dealer's, or others' own cost, with insurance limits and in form and issuing companies acceptable to Owner.

Policies providing such coverages shall contain provisions that no cancellation or material changes in the policies shall become effective except on thirty (30) days advance written notice thereof to Owner.    Irrespective of the requirements as to insurance to be carried as provided for herein, the insolvency, bankruptcy or failure of any insurance company carrying insurance of Contractor, the failure of any insurance company to pay claims accruing, or the inadequacy of the limits of the insurance, shall not affect, negate or waive any to the provisions of this Agreement including, without exception, the indemnity obligations of Contractor.

Contractor agrees to require any policies of insurance, except Workers Compensation coverages, which are in any way related to the Work and that are secured and maintained by any contractor or subcontractors, to include Owner, its parent and affiliated companies, and their directors, officers, employees and agents, as Additional Insured.    Furthermore, Underwriters shall waive all rights of recovery against Owner, its parent and affiliated companies which Contractor may have or acquire because of deductible clauses in or inadequacy of limits of, any policies of insurance maintained by Contractor.

Contractor agrees to require all such policies of insurance which are in any way related to the Work and that are secured and maintained by Contractor or its subcontractors, to include clauses providing that each underwriter shall waive its rights of recovery, under subrogation or otherwise, against Owner, its parent and affiliated companies and their directors, officers, employees and agents.

All policies of insurance required herein shall be endorsed to provide that the insurance shall be primary and not excess to or contributing with any insurance or self-insurance maintained by the Owner.

This redlined draft, generated by CompareRite (TM) - The Instant Redliner, shows the differences between -

original document      : O:\LEGAL\GNEMEC\COMPRESSION SERVICES\GALLUP\GALLUP CONSTRUCTION.DOC

and revised document: O:\LEGAL\GNEMEC\COMPRESSION SERVICES\GALLUP\GALLUP CONSTRUCTION1.DOC

CompareRite found      34 change(s) in the text

Deletions appear as Overstrike text

Additions appear as Bold text