Exhibit A

Term Sheet

GE will provide a nominal 165 MW GE-7FA DLN Gas Turbine package for use in combined cycle operation on natural gas in accordance with the Agreement.

- Scope of Supply (Furnish Only – Installation by Others)

# Base Case Gas Turbine Package

Outdoor Unit – Coastal, High Humidity

DLN 2.6

- Natural Gas – 9 ppmvd NOx (dry)

Evaporative Cooler w/ standard GE options for high humidity environments:

- Epoxy Paint/CZ11 primer for inlet system

- Stainless Steel Silencer Perf Plate

No Stack

No fin fan cooler (Closed loop CT)

LCI Static Start System

Water Wash Skid

Extended Combustion Kit

Power System Stabilizer

Second Battery Charger

No historian

65k Amp Bus Bracing

7Fh2 Generator (0.85 lagging/0.95 leading)

1 local and 1 remote HMI

85dB(A) @ 3 ft Near Field

Level 1 Silencing

- Performance Guarantees With DLN Combustor

Basis Conditions

Site Elevation – 10 feet

Ambient Dry Bulb 52 degrees F at 78% RH

Evaporative Cooler – On

Natural Gas LHV –

Performance

Gas Turbine Net Output (kW)*

Heat Rate (Btu / kWh – LHV)

HHV/LHV Ratio

CTG Generator Model 		7FH2

* Net of CTG auxiliary loads

- Emission Guarantees for DLN Combustor

NOx

CO

PM10

VOC

Preliminary estimates of startup emissions for a single gas turbine during the first hour of operation for a cold startup using the GE standard S/U sequence

NOx

CO

VOC

- Delivery

CTG #1	Earlier – September 02 Ex works – rail delivery Port of Longview October 2002.

(Note – Gas Turbine must be on site October 2002 to meet July 1, 03 COD)

- Liquidated Damages

OUTPUT			$ 800 per kW

Heat Rate			$ 8500 per Btu/kWh

Gas Turbine Delivery	$15,000 per day Days 1-30

$ 25,000 per day Days 31 and more

Documentation		$ 500 per day per document: Days 1 –30

$ 1,000 per day per document: Days 30 and over

Take-Over	LDs		$ XXX per day

- Price

Base CTG plus adders as identified above, Ex Works on needed delivery date:

- Fuel Analysis