AGREEMENT IN PRINCIPLE

FOR

TURBINE PURCHASE AGREEMENT

BETWEEN

GE PACKAGED POWER, INC.

AND

E-NEXT GENERATION LLC

Acting through its Agent

ENRON NORTH AMERICA CORP.

FOR

FOUR – LM 6000 SPRINT GAS TURBINE GENERATOR SETS

APRIL 3, 2001

TABLE OF CONTENTS

ARTICLE	PAGE

1.	General Terms of Sale.	3

2.	Price and Payment Schedule.	4

3.	Delivery and Readiness to Ship (RTS).	4

4.	termination.	5

5.	Waiver of Consequential Damages.	5

6.	Governing Law.	6

7.	Entire Agreement.	6

Appendixes

Appendix A:	Agreement By and Between E-Next Generation LLC, acting through its agent, Enron North America Corp. and GE Packaged Power, Inc. dated effective February 28, 2001

Appendix B: Payment and Termination Schedule

Appendix C: Shipment Schedule

AGREEMENT IN PRINCIPLE

FOR

TURBINE PURCHASE AGREEMENT

This AGREEMENT IN PRINCIPLE FOR TURBINE PURCHASE AGREEMENT (the “Agreement”) is entered into as of the ___ day of April, 2001, by and between GE PACKAGED POWER, INC. (referred to as “GE AeroEnergy Products” or “GE” or” Seller”), and E-Next Generation LLC ("Buyer"), acting through its agent, Enron North America Corp., a corporation incorporated under the laws of the state of Delaware, with offices located at 1400 Smith Street, P.O. Box 1188, Houston, TX 77251-1188 ("Agent")  (Seller and Buyer are referred to herein individually as a “Party” and collectively as the "Parties").

RECITALS

WHEREAS Seller and its affiliates are, among other things, in the business of manufacturing and selling gas turbine generators; and

WHEREAS Buyer requires (Four) LM 6000 Sprint gas turbine generator sets for installation in the project located in Las Vegas, Nevada (the “Project”); and

WHEREAS Buyer has assigned and delegated certain of its rights, responsibilities and obligations under this Agreement to Agent and Agent has accepted same assignment and delegations

as set forth in this Agreement; and

WHEREAS Seller has available to ship (Four) LM 6000 Sprint gas turbine generator sets, associated auxiliary equipment, all as more fully described in Appendix A (“Units 25-28” or the “Equipment”), and is prepared to provide Services (as defined below) by the dates specified in Appendix C; and

WHEREAS Buyer desires to purchase and Seller desires to sell the Equipment for installation in the Project, subject to the terms of this Agreement.

NOW, THEREFORE, in consideration of the promises and mutual covenants set forth herein the Parties agree as follows:

# General Terms of Sale.

(a) 	Buyer agrees to buy and Seller agrees to sell the Equipment, provided that a definitive Contract of Sale for the Equipment shall have been executed by both Parties no later than April 30, 2001 unless extended by mutual agreement.

(b)	Buyer agrees to buy and Seller agrees to provide (or procure from its affiliates who provide) technical advisory and training services in connection with the installation of the Equipment (the “Services”).

(c)	The Parties agree to negotiate reasonably and in good faith, beginning promptly after the execution of this Agreement and continuing until the termination of this Agreement, to finalize and execute the terms and conditions of the Contract of Sale within the time frame set forth in paragraph (a) above. The Contract of Sale shall be substantially based upon this Agreement, including Appendix B and Appendix C, and the Agreement By and Between E-Next Generation LLC, acting through its agent, Enron North America Corp, and GE Packaged Power, Inc. dated effective February 28, 2001, attached hereto as Appendix A, including the override letter agreements and related provisions contemplated herein.

(d)	The Parties (with Agent acting on behalf of the Buyer) agree to exclusively negotiate reasonably and in good faith for a period of up to six months, beginning promptly after the execution of this Agreement to finalize and execute a Long Term Service Agreement (LTSA) for the Equipment.

(e)	E-Next Generation LLC has appointed Enron North America Corp. as its Agent and delegated to Enron North America Corp. all of the rights and obligations of E-Next Generation LLC as Buyer under this Agreement, other than the obligation to pay the purchase price set forth herein and any indemnification obligations set forth herein.

# Price and Payment Schedule.

- As consideration for the Equipment and Services, Buyer agrees to pay to Seller Fifteen Million Seven Hundred Sixty Nine Thousand Seven Hundred Twenty Five U.S. dollars ($15,769,725.00) per turbine generator set (including one additional HMI  and power system stablizer per generator set) as may be subsequently established through scope modifications or in the Contract of Sale (the “Contract Price”).

- No later than close of business in Houston on March 2, 2001, Buyer shall pay to Seller by wire transfer a non-refundable sum equal to Five Hundred Thousand U.S. dollars ($500,000.00) (the “Order Commitment Option Payment”). An additional non-refundable sum equal to Two Million Six Hundred Forty Five Thousand Six Hundred U.S. Dollars ($ 2,653,945.00) will be paid  on April 4, 2001 (collectively, the Order Commitment Option Payment plus this subsequent payment are referred to as the “Order-Commitment Payment”).  The remainder of the Contract Price shall be paid as set forth in Appendix B.

# Delivery and Readiness to Ship (RTS).

- Seller guarantees the RTS Dates set forth in Appendix C, provided:

- This Agreement will be executed by March 1, 2001, and the Order Commitment Option Payment is paid to Seller by March 2, 2001;

- that the balance of the Order Commitment Payment is received by Seller by close of business on April 4, 2001;

- that final scope definition will be agreed to no later than April 30, 2001.

- that the Contract of Sale with respect to such Equipment is signed by both Parties no later than April 30, 2001.

The time within which conditions 2(a), (3) and (4) above must be accomplished may be extended by written agreement of the Parties.

- With respect to the turbine generator sets, the “RTS Date” set forth in Appendix C means the date upon which the major components of each of Units 25-28 are available for shipment from the Seller’s manufacturing facility.

- It is expressly understood that the Seller will have the right to utilize all resources within its global manufacturing and vendor network to supply the requirements of this Agreement and the resulting Contract of Sale.

(d)	After the conditions set forth in section 3(a) above have been fulfilled, the Buyer shall have no right to suspend or delay manufacture or delivery of the Equipment under this Agreement or the subsequent Contract of Sale.

# Termination.

(a)	This Agreement shall come into force and effect on the day upon which Seller receives the Order Commitment Option Payment from Buyer (the “Effective Date”).

(b)	This Agreement shall terminate:

(1)  upon execution by the Parties of the Contract of Sale; or

(2) Upon receipt by Seller of Buyer’s written notice to terminate this Agreement ; or

- upon written agreement of the Parties to terminate this Agreement; or

whichever shall first occur.

In the event of termination pursuant to clause 4(b) (other than subclause 4(b)(1)), Buyer shall pay Seller the amount determined by reference to the Payment and Termination Schedule set forth in Appendix B.  Payments, including the Order Commitment payment, made against the purchase price shall be credited against the termination payment, provided that Seller shall in any event be entitled to retain the Order Commitment Payment.  The foregoing shall constitute Buyer’s and Seller’s sole obligation upon termination after the Effective Date.  Upon fulfillment of these obligations, neither Party shall have any liability to the other Party with respect to this Agreement or the Project whether in contract, warranty, tort (including negligence) or otherwise.

# Waiver of Consequential Damages.

Neither Party shall be liable to the other Party under this Agreement for any consequential, incidental, indirect, punitive, special or exemplary damages whatsoever, including but not limited to loss of profit or revenues, loss of use of Units 25-28 or of any associated equipment, cost of capital, cost of substitute equipment, facilities, services or replacement power, downtime costs or claims of Buyer’s customers.

# Governing Law.

This Agreement, its interpretation and any disputes relating to, arising out of or connected with this Agreement, shall be governed by the laws of the State of Texas, without regard to its conflicts of law provisions.

# Entire Agreement.

This Agreement together with the Appendices hereto contains the entire agreement of the Parties with respect to the subject matter hereof.  All prior, correspondence, negotiations and agreements, oral or written, among the Parties with respect to the subject matter hereof are superseded by this Agreement.

IN WITNESS WHEREOF, the Parties have caused this Agreement to be executed by their respective authorized representatives as of the date first set forth above.

| GENERAL ELECTRIC COMPANY By: _________________________ Name: _______________________ Title: ________________________ | ## ENRON NORTH AMERICA CORP. ## As Agent for ## E-NEXT GENERATION LLC By: ___________________________ Name: _________________________ Title: __________________________ |
| --- | --- |

APPENDIX B

PAYMENT AND TERMINATION SCHEDULE

This proposal is based upon receipt of the  following progressive payments:

| Payment Date | Payment Amount |
| --- | --- |
| Order Commitment Payment by 4 Apr., 2001: | 5% |
| Contract Payment #2 by 4 Apr., 2001 | 10% |
| Contract Payment #3 by 21 Apr., 2001 | 10% |
| Contract Payment #4 by 21 May, 2001 | 10% |
| Contract Payment #5 by 21 June, 2001 | 10% |
| Contract Payment #6 by 21 July, 2001 | 10% |
| Contract Payment #7 by 21 Aug., 2001 | 10% |
| Contract Payment #8 by 21 Sept., 2001 | 10% |
| Contract Payment #9 by 21 Oct., 2001 | 10% |
| Contract Payment #10 by 21 Nov., 2001 | 10% |
| Contract Payment #11 by 21 Jan., 2002 | 5% |

TERMINATION  SCHEDULE

| Receipt of Termination Notice by GE Aero Energy Products | Termination Payment, Percent (or Amount) of Contract Price |
| --- | --- |
| On or before 21 March, 2001 | $ 500,000 |
| 21 March, 2001 - 20 Apr., 2001 | 10% |
| 21 Apr., 2001 - 20 May, 2001 | 20% |
| 21 May, 2001 - 20 June, 2001 | 30% |
| 21 June, 2001 - 20 July, 2001 | 40% |
| 21 July, 2001 - 20 Aug., 2001 | 50% |
| 21 Aug., 2001 - 20 Sept., 2001 | 60% |
| 21 Sept., 2001 - 20 Oct., 2001 | 70% |
| 21 Oct., 2001 - 20 Dec., 2001 | 80% |
| 21 Dec., 2001 - 20 Jan., 2002 | 90% |
| After 20 Jan., 2002 | 100% |

APPENDIX C

###### SHIPMENT SCHEDULE AND TRANSPORTATION PRICE

###### Based upon execution of an Agreement in Principle by March [2], 20001 and receipt of a reservation fee by March 2, 2001, the following shipment dates are offered subject to prior sale:

            Unit # 25,		Ready to Ship 15 October 2001
            Unit #26	Ready to Ship22 October 2001

###### Unit # 27		Ready to Ship 4 November 2001

###### Unit # 28		Ready to Ship 31 December 2001		
 
If a wire transfer of $500,000 is received by GE on March 2, 2001, and the remainder of the 5% reservation fee is received by GE before the end of business on April 4, 2001 the shipment dates promised above are assured.  To facilitate manufacturing, GE at its option, may build and title transfer Units up to 90 days earlier than the schedule above without acceleration of payment by Enron.

###### GE Aero Energy Products can provide insured transportation to the jobsite.  
             The price will be the actual cost incurred plus 7% if  a purchase commitment for
             transportation is received by GE from Enron at least 90 days before the 
             scheduled  commencement of transportation. The price will be the actual cost 
             incurred plus 15% if a purchase commitment for transportation is received by
             GE from Enron less than 90 days before the scheduled commencement of 
             transportation.