ENRON

PROJECT

GE Sales Orders

601134, 601134A, 601134B, 601134C

24 Units

LM6000 60Hz Sprint

Gas Generator Sets

PROGRESS REPORT

For

November 2000

Mike Storm

Project Manager

Date:  November 17, 2000

Table of Contents

1.0  Management Summary

1.1	Overall Project Situation

1.2	Major Activity

1.3	Significant Problems

2.0 Progress Review

2.1	Milesotne Report

2.2	Updated manufacturing  Schedule

2.3	Problems Affecting Progress

2.4	Decisions and Actions

2.5	Actions and Orientations required from Purchaser

3.0 Commercial Situation

3.1	Payment Status

3.2	Change  Order Status

3.3	Notice of Claims

3.4	Quality Assurance / Quality Control

3.5	Projected Tests and Reports

4.0 Transportation

4.1	Austin Project

4.2	Fountain Valley Project

4.3	Electrobolt Project

4.4	Lodi Porject………………………………………………………………………………………………………...

5.0 Drawing List

5.1	601134 Units 1,2,3,4,5,6,21 & 22

5.2	601134A Units 13,14,15 &16

5.3	601134B Units 7,8,17 & 18

5.4	601134C Units 9,10.,11,12,19,20 , 23 & 24

6.0 Attachments

1	Unit Configuration Chart

2

3

4

Management Summary

1.1	Overall Project Summary

As of November 17, 18 units have progressed through the factory and test line.  Currently, units 1 through 17 have been moved to our storage locations.  Unit 18 is in final preparation for movement into storage, with some major components already relocated.  Enron has accepted title transfer on units one through 14.  GE will issue notification of ready to ship for units fifteen and sixteen.

Remaining units are on schedule as detailed in the weekly manufacturing schedule (reference section  2.1).  A change as been negotiated between Enron and GE to move out the delivery of units 19, 20, 23 and 24.  New delivery scheduled can be found under section 2.

GE has been informed, Power Engineers will no longer be involved with the Las Vegas Project.  GE has been informed Delta Hudson will now perform the engineering functions for the Las Vegas Project as it pertains to the equipment being assigned from this contract.

Colorado Springs, Fountain Valley project has been increased to 6 units overall.  GE has been informed project will receive units 13 to 16, 7 and 8.  Nepco has requested a quote for transportation, which GE has provided for all six units.  No confirmation has been made as to whether or not GE will provide transportation.  A six unit average guarantee has been provided for this site.  Enron has provided an email to GE confirming need to purchase six power system stabilizers and two additional 45 foot standard exhaust stacks.

Nepco has as signed an engineering team to the Lodi (Central Valley Power Energy Facility) California.  Nepco team members have been assigned project net access.  Nepco has displayed interest in having GE provide control houses with MCC and switch-gear arrangement.

An error has been identified on the configuration chart issued with each monthly report.  Unit 9 generator serial number has been reported as 3207, the correct serial number is 3213.  The configuration spread sheet has been corrected.

1.2	Major Activity

- Changed delivery schedule of units 19, 20, 23 and 24

| Unit # | Contract Delivery Date | New Delivery Date | New Target Date |
| --- | --- | --- | --- |
| 19 | 28-Feb-01 | 30-July-01 | 21-July-01 |
| 20 | 28-Feb-01 | 30-July-01 | 24-July-01 |
| 23 | 30-Apr-01 | 30-July-01 | 31-July-01 |
| 24 | 30-Apr-01 | 15-Aug-01 | 01-Aug-01 |

- Completed Factory String Test of Unit 18 on 11/01/00

- Significant Problems

- All Altair Filter houses have been rejected due to manifold welds not meeting specifications.  GE is working with it supplier to provide a plan for corrective measures.  GE is in progress of providing Enron with a corrective plan.  Initial plan will be provided to Enron on November 17.

- The amount of customer required unit shipments during the months, November through March will impact GE ability to ship units at late request.  Enron should consider and provide best known required shipment dates in order to arrange shipment slots early.

- PROGRESS REVIEW

2.1	Milestone Report

- UNITS MOVED TO STORAGE

| Serial | Customer and | Unit | Piping | Turbine | Generator | Date | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Order # | Unit Number | Test | Conf. | Serial # | Serial # | Stored |  |
| 308898 | Enron # 1 | Static | RH | 191-198 | GE 336X638 | 6/19/00 | Air filter NCR |
| 309123 | Enron # 8 | Static | LH | 191-213 | 290ERJT / 3205 | 6/16/00 | Air filter NCR |
| 309101 | Enron # 7 | Full | RH | 191-192 | 290ERJT / 2979 | 6/29/00 | Air filter NCR |
| 308951 | Enron # 2 | Static | LH | 191-227 | GE 336X641 | 9/27/00 | Air filter NCR |
| 308972 | Enron # 3 | Static | RH | 191-214 | GE 336X637 | 9/27/00 | Air filter NCR |
| 308999 | Enron # 4 | Static | LH | 191-226 | GE 336X640 | 9/27/00 | Air filter NCR |
| 309020 | Enron #5 | Static | RH | 191-204 | GE 336X639 | 9/27/00 | Air filter NCR |
| 309073 | Enron #6 | Full | LH | 191-212 | GE 336X636 | 9/27/00 | Air filter NCR |
| 309266 | Enron #9 | Static | RH | 191-209 | 290ERJT/3213 | 9/27/00 | Air filter NCR |
| 309547 | Enron #10 | Static | LH | 191-220 | 290ERJT/3217 | 9/27/00 | Air filter NCR |
| 309575 | Enron #11 | Static | RH | 191-219 | 290ERJT/3219 | 9/27/00 | Air filter NCR |
| 309578 | Enron #12 | Full | LH | 191-222 | 290ERJT/3206 | 9/27/00 | Air filter NCR |
| 309420 | Enron #13 | Static | RH | 191-230 | 290ERJT/3220 | 9/27/00 | Air filter NCR |
| 309505 | Enron #14 | Full | LH | 191-225 | 290ERJT/3211 | 9/27/00 | Air filter NCR |
| 309573 | Enron #15 | Static | LH | 191-229 | 290ERJT/3298 |  | Moved off site, Air filter NCR |
| 309601 | Enron #16 | Static | RH | 191-232 | 290ERJT/3299 |  | Moved off site/ Air filter NCR |
| 309604 | Enron #17 | Static | LH | 191-236 | 290ERJT/ |  | Needs Generator assigned |
| 309718 | Enron #18 | Full | RH | 191-2236 | 290ERJT/3222 |  | Moving into storage, complete by 11/27 |

- Units 1 to 14 have been formally titled transferred

- Units 15 to 18 main components have moved to storage.  GE is completing packing list.

- Revision 8.0 Unit Configuration Chart (attachment 1)

- Updated Manufacturing Schedule

| ### CUSTOMER |  |  |  |  |  |  | STATIC TEST |  |  | LOAD TEST |  |  |  | NEED |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| W/O # | NAME | Starting in A Dates | Start B | Start C | Start D | Leaving D1 | Finish Static Test (7 days) | Finish tear down & paint | Finish Dress out & ship | Finish Load Test 28 Days | Finish tear down & paint | Finish Dress Out & ship | Test y /n | Turbine & Generator need date, turbine for C & Generator for prep. | FUELSYS |
| 309578 | Enron 12 | 7/10/00 | 7/17/00 | 7/24/00 | 7/31/00 | 8/7/00 | N/A | N/A | N/A | 8/31/00 | 9/10/00 | 9/17/00 | Y | 7/24/00 | G |
| 309420 | Enron 13 | 7/17/00 | 7/24/00 | 7/31/00 | 8/7/00 | 8/14/00 | 8/18/00 | 8/25/00 | 9/1/00 | N/A | N/A | N/A | N | 7/31/00 | G |
| 309505 | Enron 14 | 7/24/00 | 7/31/00 | 8/7/00 | 8/14/00 | 8/21/00 | N/A | N/A | N/A | 9/18/00 | 9/22/00 | 9/29/00 | Y | 8/7/00 | G |
| 309573 | Enron 15 | 8/16/00 | 8/23/00 | 8/30/00 | 9/7/00 | 9/13/00 | 9/20/00 | 9/26/00 | 10/31/00 | N/A | N/A | N/A | N | 10/31/00 | G |
| 309601 | Enron 16 | 8/23/00 | 8/30/00 | 9/7/00 | 9/13/00 | 9/20/00 | 9/27/00 | 10/3/00 | 10/31/00 | N/A | N/A | N/A | N | 10/31/00 | G |
| 309604 | Enron 17 | 9/5/00 | 9/11/00 | 9/18/00 | 9/25/00 | 10/2/00 | 10/9/00 | 10/13/00 | 10/20/00 | N/A | N/A | N/A | N | 9/18/00 | D |
| 309718 | Enron 18 | 9/7/00 | 9/13/00 | 9/20/00 | 9/27/00 | 10/4/00 | N/A | N/A | N/A | 11/1/00 | 11/7/00 | 11/16/00 | Y | 9/20/00 | D |
|  | Enron 19 | 4/25/01 | 5/02/01 | 5/09/01 | 5/16/01 | 5/23/01 | 5/30/01 | 6/06/01 | 6/13/00 | N/A | N/A | N/A | N | 9/27/00 | G |
| 309988 | Enron 20 | 4/30/01 | 5/07/01 | 5/14/01 | 5/21/01 | 5/28/01 | 6/04/01 | 6/11/01 | 6/18/01 | N/A | N/A | N/A | N | 5/09/01 | G |
| 309898 | Enron 21 | 11/13/00 | 11/20/00 | 11/27/00 | 12/04/00 | 12/11/00 | 12/18/00 | 12/22/00 | 01/01/01 | N/A | N/A | N/A | N | 5/14/01 | G |
|  | Enron 22 | 11/06/00 | 11/13/00 | 11/20/00 | 11/27/00 | 12/04/00 | 12/11/00 | 12/17/0 | 12/28/00 | N/A | N/A | N/A | N | 11/22/00 | G |
|  | Enron 23 | 5/07/01 | 5/14/01 | 5/21/01 | 5/28/01 | 6/04/01 | 6/11/01 | 6/18/01 | N/A | N/A | N/A | N/A | N | 5/21/01 | G |
|  | Enron 24 | 5/09/01 | 5/16/01 | 5/23/01 | 5/30/01 | 6/06/01 | 6/13/01 | 6/20/01 | 6/27/01 | N/A | N/A | N/A | N | 5/23/01 | G |

Notes:

Bold Dates = Actual Dates, Underline dates = Complete Dates, All other dates are  planned dates

Dates for units 19, 20, 23 & 24 have been revised as a result of change order 4.

S/N for units 19, 20, 23 & 24 will not be issued until near fabrication dates

2.3	Problems Affecting Progress

Currently there are no issues affecting progress of units through manufacturing.  There are areas of concern regarding Non-Conformance/Discrepancy and storage procedures.

2.4	Decisions and Actions

- GE and Enron have negotiated an acceptance of title transfer for units 1 to 6 and 9 to 14.  As part of the agreement, GE will provide storage of these units at no charge through the month of May, 2001.

2.5	Actions and Orientations required from Purchaser

- GE requires issuance of change order for options being exercised for the Fountain Valley project.  Which includes six power system stabilizers and 2 additional 45’ standard exhaust stacks.

- GE requires issuance of change order 5, order placed by Enron for a 60 kV GSU

- Early shipment of units 1 to 8 and 13 through 16 is being considered by Enron.  GE requests that Enron provide a shipping plan to illustrate order in which units and equipment will be required for loading.

- COMMERCIAL SITUATION

3.1	Payment Status

Value of Contract

| Total Value of Contract with Change Orders (See sec. 9 for change orders) | $352,289,400.00 |
| --- | --- |

Contract Value reflects pricing through change order four.  Payment schedule below based on original contract value.  Need to talk with customer about invoicing separately for change orders (See Section 3.2)

Project Number:	601134

Project Name:	Enron North America Corp.

Contracting Party	Westdeutsche Landesbank Girozentrale, New York Branch

| No. | Payment Date | Payment % | Invoice Date | Received Date | Amount Received | Milestone |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 9/23/1999 | 5% | 9/22/1999 | 9/22/1999 | $16,740,000 | Downpayment |
| 2 | 12/1/1999 | 10% | 11/1/1999 | 12/1/1999 | $33,480,000 | Downpayment |
| 3 | 3/15/2000 | 10% | 2/14/2000 | 3/15/2000 | $33,480,000 | 5 units released for production |
| 4 | 6/15/2000 | 10% | 5/16/2000 | 6/26/2000 | $33,480,000 | Units 1,2,3 in heavy fabrication |
| 5 | 8/15/2000 | 10% | 7/17/2000 | 08/16/00 | $33,480,000 | Units 4,5,6 in heavy fabrication |
| 6 | 9/15/2000 | 10% |  | 9/20/00 | $33,480,000 | Units 7,8 in heavy fabrication |
| 7 | 10/15/2000 | 10% | 9/16/00 | 10/16/00 | $33,480,000 | Units 9,10,11 in heavy fabrication |
| 8 | 11/15/2000 | 10% | 10/16/00 | 11/15/00 | $33,480,000 | Units 12,13 in heavy fabrication; Units 1 through 8 shipped |
| 9 | 1/15/2001 | 10% |  |  |  | Units 14,15,16,17 in heavy fabrication; Units 9 through 13 shipped |
| 10 | 2/15/2001 | 0% |  |  |  | Units 21 & 22 in production. Units 16, 17 & 18 shipped |
| 10A | 5/15/2001 | 5% |  |  |  | Units 19,20,23,24 in production; Units 21 & 22 shipped |
| 11 | 7/30/2001 | 5% |  |  |  | Units 19 & 20 shipped |
| 12 | 8/15/2001 | 5% |  |  |  | Units 23 & 24 shipped |

Total Received: $251,100,000 as of November 16th

  - Change Order Status

- Change orders

| # | Purpose | Potential/Submitted Amt. | Sub Date | Approved Amt | Approved Date |
| --- | --- | --- | --- | --- | --- |
| 1 | Dual Fuel Option for Units 7/8 & 17/18 | $1,120,000.00 | 6/2/2000 | $1,120,000. | 6/2/2000 |
| 2 | Exhaust Stacks 45’ Stand. | $792,000.00 | 9/30/00 | $792,000. | 11/03/00 |
| 3 | Exhaust Stacks, Chillers, Cooling towers, Power Stab., control houses & MCC | $12,649,400 | 9/30/00 | $12,649,400 | 11/03/00 |
| 4 | Change delivery dates for units 19,20,23 & 24. Modify payments | N/A | 9/30/00 | N/A | 11/03/00 |
|  | Total Approved |  |  | $14,561,400 |  |

GE still requires a change order for the following items that we committed to purchasing on behalf of Enron.

Summary of Cost:

a.	Exhaust Stack 45’ Standard Base (2) $198,000 per Unit	$ 396,000.00

b.	Power System Stabilizer (6) $31,875 per unit	$191,250.00

c.	60 kV GSU Transformer (1) $505,000 per Unit	$,505,000.00

Total amount of outstanding change order $1,092,250.00

3.3	Notice of Claims

- They are no outstanding claims for this month

  - Quality Assurance / Quality Control

- GE will provide a final copy of storage procedures on or before October 31, 2000

- GE to provide Quality plans and vendor information for equipment being purchased as options (BOP Equipment), as purchases are confirmed and finalized.

- Enron has provided formal notification on it’s intent to perform an audit of purchasing functions and design review of the Altair supplied equipment.  Along with this request, Enron has request complete summary of all issues associated with the Altair supplied equipment and performance plan to carry out required repairs.

  - Projected Test and Reports

- Unit 18 completed  Factory String test on November 1, 2000

- TRANSPORTATION

  - Austin Energy Project

- Delivery for units nine (9) through twelve (12) to Austin, Tx. is currently scheduled for Nov 30, 2000.  Delivery of optional control houses scheduled for Jan/01.

- Nepco as requested GE to provide transportation for all equipment which it is supplying.

- GE will begin shipping non-permit loads on 11-20-00.

  - Fountain Valley Project (Colorado Springs)

- Nepco Colorado as provided tentative ship dates for units thirteen (13) through sixteen (16).  GE has provided a price quote to Nepco based on Enron contract pricing.  GE has been informed, this project may increase to six units

- Unit 13 to ship on 01/22/01

- Unit 14 to ship on 01/29/01

- Unit 15 to ship on 02/05/01

- Unit 16 to ship on 02/12/01

- Enron has informed GE it may elect to perform transportation of all six Colorado units.  Shipment may occur prior to January 2001.

  - Electrobolt Project (Brazil)

- Enron has informed GE it may elect to perform transportation for six of the Electrobolt assigned units prior to January 2001.  Enron has further informed, GE may be selected to move equipment to a free trade zone prior to January 2001.

- Feb/01 has been provided as an estimated shipping time frame to begin shipment of equipment internationally.

  - Lodi/Pleasenton (California)

- No arrangements or inquires have been placed regarding shipment

- Feb/01 has been provided as an estimated shipping time frame for GTG equipment

DRAWING LIST

  - 601134  Units 1, 2, 3, 4, 5, 6, 21 & 22

LM6000, 60Hz, Gas Fuel, GE Generator, Fin/Fan Lube Oil Cooler

| Dwg Series | DWG NO | REV | TITLE | TRANSMITTED |
| --- | --- | --- | --- | --- |
| 601134 | 287335 | - | MODIFIED SPREADER ALTAIR AIR FILTER | 09/06/2000 |
| 601134 | 302690 | - | AREA CLASSIFICATION DRAWING,MAIN UNIT RH | 09/26/2000 |
| 601134 | 535005 | - | ELECTRICAL SYMBOLS,ABBR,AND REF DATA | 08/28/2000 |
| 601134 | 535013 | C | NAMEPLATE LIST,ENGRAVING SCHE&SWITCH DEV | 08/28/2000 |
| 601134 | 535137 | C | SPECIFIC DETAILS,TURBINE CONTROL PANEL | 08/28/2000 |
| 601134 | 535931 | A | SYS SCHEMATIC,FIRE & GAS PROTECTION | 08/28/2000 |
| 601134 | 535932 | C | SYSTEM SCHEMATIC,VIBRATION | 08/28/2000 |
| 601134 | 549270 | A | F&ID,SPRINT SYSTEM,SPRINT SKID |  |
| 601134 | 559000 | - | DRAWING LIST,MASTER | 03/29/2000 |
| 601134 | 559001 | - | DRAWING LIST,CUSTOMER |  |
| 601134 | 559005 | - | ELECTRICAL SYMBOLS,ABBR,AND REF DATA | 10/27/1999 |
| 601134 | 559006 | - | INTERCONNECT PLAN,ELECTRICAL | 11/15/1999 |
| 601134 | 559006 | A | INTERCONNECT PLAN,ELECTRICAL | 02/03/2000 |
| 601134 | 559006 | B | INTERCONNECT PLAN,ELECTRICAL | 03/20/2000 |
| 601134 | 559007 | - | INTERCONNECT WIRING DIAGRAM,CUSTOMER | 04/04/2000 |
| 601134 | 559007 | A | INTERCONNECT WIRING DIAGRAM,CUSTOMER | 08/29/2000 |
| 601134 | 559007 | B | INTERCONNECT WIRING DIAGRAM,CUSTOMER |  |
| 601134 | 559008 | - | INTERCONNECT WIRING DIAG,CONTROL HOUSE | 11/06/2000 |
| 601134 | 559009 | - | INTERCONNECT CABLE SCHEDULE | 06/29/2000 |
| 601134 | 559012 | - | LAYOUT,JUNCTION BOXES |  |
| 601134 | 559013 | - | NAMEPLATE LIST,ENGRAVING SCHEDULE | 10/27/1999 |
| 601134 | 559013 | A | NAMEPLATE LIST,ENGRAVING SCHEDULE |  |
| 601134 | 559013 | B | NPL,ENGRAVING SCHEDULE & SWITCH DEV | 01/31/2000 |
| 601134 | 559013 | C | NPL,ENGRAVING SCHEDULE & SWITCH DEV | 05/10/2000 |
| 601134 | 559013 | D | NPL,ENGRAVING SCHEDULE & SWITCH DEV | 08/29/2000 |
| 601134 | 559014 | - | PLAN & ELEVATION,TURB CONT PANEL | 01/17/2000 |
| 601134 | 559017 | - | PLAN & ELEVATION,MOTOR CONTROL CENTER |  |
| 601134 | 559018 | - | PLAN & ELEVATION,24VDC BATTERY SYSTEM | 11/09/1999 |
| 601134 | 559018 | A | PLAN & ELEVATION,24VDC BATTERY SYSTEM | 01/19/2000 |
| 601134 | 559018 | B | PLAN & ELEVATION,24VDC BATTERY SYSTEM | 02/25/2000 |
| 601134 | 559018 | C | PLAN & ELEVATION,24VDC BATTERY SYSTEM | 05/10/2000 |
| 601134 | 559022 | - | PLAN & ELEVATION,LINESIDE CUBICLE | 10/27/1999 |
| 601134 | 559022 | A | PLAN & ELEVATION,LINESIDE CUBICLE |  |
| 601134 | 559022 | B | PLAN & ELEVATION,LINESIDE CUBICLE | 02/14/2000 |
| 601134 | 559022 | C | PLAN & ELEVATION,LINESIDE CUBICLE | 03/15/2000 |
| 601134 | 559023 | - | PLAN & ELEVATION,NEUTRAL CUBICLE | 10/27/1999 |
| 601134 | 559023 | A | PLAN & ELEVATION,NEUTRAL CUBICLE | 02/07/2000 |
| 601134 | 559023 | B | PLAN & ELEVATION,NEUTRAL CUBICLE | 03/01/2000 |
| 601134 | 559023 | C | PLAN & ELEVATION,NEUTRAL CUBICLE | 05/12/2000 |
| 601134 | 559031 | - | ONE LINE DIAGRAM | 10/27/1999 |
| 601134 | 559031 | A | ONE LINE DIAGRAM |  |
| 601134 | 559031 | B | ONE LINE DIAGRAM | 02/21/2000 |
| 601134 | 559031 | C | ONE LINE DIAGRAM | 08/31/2000 |
| 601134 | 559031 | D | ONE LINE DIAGRAM | 10/19/2000 |
| 601134 | 559032 | - | THREE LINE DIAGRAM,GENERATOR METERING | 10/27/1999 |
| 601134 | 559032 | A | THREE LINE DIAGRAM,GENERATOR METERING | 03/07/2000 |
| 601134 | 559032 | B | THREE LINE DIAGRAM,GENERATOR METERING | 06/19/2000 |
| 601134 | 559032 | C | THREE LINE DIAGRAM GENERATOR METERING | 10/19/2000 |
| 601134 | 559034 | - | THREE LINE DIAGRAM,BLACKSTART DIESEL |  |
| 601134 | 559035 | - | SCHEDULE,MOTOR CONTROL CENTER | 10/27/1999 |
| 601134 | 559035 | A | SCHEDULE,MOTOR CONTROL CENTER | 01/18/2000 |
| 601134 | 559035 | B | SCHEDULE,MOTOR CONTROL CENTER | 02/28/2000 |
| 601134 | 559035 | C | SCHEDULE,MOTOR CONTROL CENTER | 03/21/2000 |
| 601134 | 559037 | - | SYSTEM SCHEMATIC,GENERATOR EXCITATION | 10/27/1999 |
| 601134 | 559037 | A | SYSTEM SCHEMATIC,GENERATOR EXCITATION |  |
| 601134 | 559037 | B | SYSTEM SCHEMATIC,GENERATOR EXCITATION | 09/15/2000 |
| 601134 | 559037 | C | SYSTEM SCHEMATIC,GENERATOR EXCITATION | 10/19/2000 |
| 601134 | 559041 | - | SCHEMATIC DIAGRAM,CIRCUIT BREAKER CONT | 10/29/1999 |
| 601134 | 559041 | A | SCHEMATIC DIAGRAM,CIRCUIT BREAKER CONT | 06/19/2000 |
| 601134 | 559041 | B | SCHEMATIC DIAGRAM, CIRCUIT BRKR CONT | 10/19/2000 |
| 601134 | 559044 | - | SCHEMATIC DIAGRAM,MOTOR CONTROL CENTER | 10/29/1999 |
| 601134 | 559044 | A | SCHEMATIC DIAGRAM,MOTOR CONTROL CENTER | 02/03/2000 |
| 601134 | 559044 | B | SCHEMATIC DIAGRAM,MOTOR CONTROL CENTER | 03/07/2000 |
| 601134 | 559044 | C | SCHEMATIC DIAGRAM,MOTOR CONTROL CENTER | 04/10/2000 |
| 601134 | 559044 | D | SCHEMATIC DIAGRAM,MOTOR CONTROL CENTER | 08/29/2000 |
| 601134 | 559047 | - | SCHEMATIC DIAGRAM,DISCRETE CONTROL | 03/09/2000 |
| 601134 | 559047 | A | SCHEMATIC DIAGRAM,DISCRETE CONTROL | 08/29/2000 |
| 601134 | 559047 | B | SCHEMATIC DIAGRAM,DISCRETE CONTROL | 10/24/2000 |
| 601134 | 559048 | - | SCHEMATIC DIAGRAM,ANALOG CONTROL | 03/15/2000 |
| 601134 | 559048 | A | SCHEMATIC DIAGRAM,ANALOG CONTROL | 08/29/2000 |
| 601134 | 559049 | - | SCHEMATIC DIAGRAM,ANALOG CONTROL | 03/13/2000 |
| 601134 | 559049 | A | SCHEMATIC DIAGRAM,ANALOG CONTROL | 08/29/2000 |
| 601134 | 559051 | - | LOGIC FLOW DIAGRAM,FIRE PROT SYS(CO2) | 11/08/1999 |
| 601134 | 559051 | A | LOGIC FLOW DIAG. FIRE & GAS PROT SYS | 09/05/2000 |
| 601134 | 559057 | - | WIRING DIAGRAM,TURB CONT PNL,CONT CUB | 06/29/2000 |
| 601134 | 559057 | A | WIRING DIAGRAM,TURB CONT PNL,CONT CUB | 08/31/2000 |
| 601134 | 559058 | - | WIRING DIAGRAM,TURB CONT PNL,TERMN CUB |  |
| 601134 | 559058 | A | WIRING DIAGRAM,TURB CONT PNL,TERMN CUB | 06/29/2000 |
| 601134 | 559058 | B | WIRING DIAGRAM,TURB CONT PNL,TERMN CUB | 08/29/2000 |
| 601134 | 559058 | C | WIRING DIAGRAM,TURB CONT PNL,TERMN CUB |  |
| 601134 | 559077 | - | WIRING DIAGRAM,FIRE & GAS PROT SYSTEM | 01/17/2000 |
| 601134 | 559077 | A | WIRING DIAGRAM,FIRE & GAS PROT SYSTEM | 09/15/2000 |
| 601134 | 559080 | - | WIRING DIAGRAM,LINESIDE CUBICLE | 02/03/2000 |
| 601134 | 559080 | A | VOID-WIRING DIAGRAM,LINESIDE CUBICLE |  |
| 601134 | 559081 | - | WIRING DIAGRAM,NEUTRAL CUBICLE |  |
| 601134 | 559081 | A | WIRING DIAGRAM,NEUTRAL CUBICLE | 06/29/2000 |
| 601134 | 559081 | B | WIRING DIAGRAM,NEUTRAL CUBICLE | 08/31/2000 |
| 601134 | 559091 | - | WIRING DIAGRAM TURBINE SKID |  |
| 601134 | 559091 | A | WIRING DIAGRAM TURBINE SKID | 05/10/2000 |
| 601134 | 559092 | - | WIRING DIAGRAM,GENERATOR SKID | 02/03/2000 |
| 601134 | 559092 | A | WIRING DIAGRAM,GENERATOR SKID |  |
| 601134 | 559092 | B | WIRING DIAGRAM,GENERATOR SKID |  |
| 601134 | 559092 | C | WIRING DIAGRAM,GENERATOR SKID | 08/31/2000 |
| 601134 | 559143 | - | WORKSHEET,FUEL CONTROL | 06/29/2000 |
| 601134 | 559145 | - | FUEL CONTROL LAYOUT | 06/29/2000 |
| 601134 | 559146 | - | WORKSHEET,SEQUENCER | 06/29/2000 |
| 601134 | 559147 | - | SEQUENCER LAYOUT | 06/29/2000 |
| 601134 | 559148 | - | WORKSHEET,DISTRIBUTED I/O CONFIGURATION | 04/04/2000 |
| 601134 | 559148 | A | WORKSHEET,DISTRIBUTED I/O CONFIGURATION | 06/22/2000 |
| 601134 | 559148 | B | WORKSHEET,DISTRIBUTED I/O CONFIGURATION | 08/03/2000 |
| 601134 | 559200 | - | GA,MAIN UNIT-RH | 04/05/2000 |
| 601134 | 559200 | A | GA,MAIN UNIT-RH | 04/12/2000 |
| 601134 | 559200 | B | GA,MAIN UNIT-RH |  |
| 601134 | 559200 | C | GA,MAIN UNIT-RH | 05/09/2000 |
| 601134 | 559200 | D | GA,MAIN UNIT-RH | 06/29/2000 |
| 601134 | 559200 | E | GA,MAIN UNIT-RH | 10/19/2000 |
| 601134 | 559201 | - | GA,MAIN UNIT-LH | 04/05/2000 |
| 601134 | 559201 | A | GA, MAIN UNIT-LH | 04/12/2000 |
| 601134 | 559201 | B | GA,MAIN UNIT-LH |  |
| 601134 | 559201 | C | GA,MAIN UNIT-LH | 05/15/2000 |
| 601134 | 559201 | D | GA,MAIN UNIT-LH | 06/22/2000 |
| 601134 | 559201 | E | GA,MAIN UNIT-LH | 06/29/2000 |
| 601134 | 559201 | F | GA,MAIN UNIT-LH |  |
| 601134 | 559209 | - | GENL ARR,SPRINT SYSTEM, SPRINT SKID | 03/02/2000 |
| 601134 | 559218 | - | GENL ARR,AUXILIARY SKID | 04/03/2000 |
| 601134 | 559218 | A | GENL ARR,AUXILIARY SKID | 10/26/2000 |
| 601134 | 559222 | - | ANCHOR BOLT & SHEAR LUG DETAIL | 03/14/2000 |
| 601134 | 559224 | - | INSTL FTPT,AB & SHEAR LUG LCTN,LM6000 | 03/14/2000 |
| 601134 | 559225 | - | LIFT ARRANGEMENT | 05/24/2000 |
| 601134 | 559226 | - | SHIPPING DATA | 05/24/2000 |
| 601134 | 559226 | A | SHIPPING DATA | 09/26/2000 |
| 601134 | 559231 | - | FLOW AND EQUIPMENT SYMBOLS,MECHANICAL | 12/03/1999 |
| 601134 | 559232 | - | F&ID,HYDR START SYS(60HZ) | 12/01/1999 |
| 601134 | 559232 | A | F&ID,HYDR START SYSTEM | 02/03/2000 |
| 601134 | 559232 | B | F&ID,HYDR START SYSTEM |  |
| 601134 | 559232 | C | F&ID,HYDR START SYSTEM | 05/23/2000 |
| 601134 | 559232 | D | F&ID,HYDR START SYSTEM |  |
| 601134 | 559239 | - | F&ID,VENT & COMB AIR SYSTEM | 05/18/2000 |
| 601134 | 559239 | A | F&ID,VENT & COMB AIR SYSTEM | 07/25/2000 |
| 601134 | 559244 | - | F&ID,TURBINE LUBE OIL SYSTEM | 12/13/1999 |
| 601134 | 559244 | A | F&ID,TURBINE LUBE OIL SYSTEM | 04/10/2000 |
| 601134 | 559244 | B | F&ID,TURBINE LUBE OIL SYSTEM | 05/22/2000 |
| 601134 | 559244 | C | F&ID,TURBINE LUBE OIL SYSTEM | 10/20/2000 |
| 601134 | 559248 | - | F&ID,GENERATOR LUBE OIL SYSTEM | 02/24/2000 |
| 601134 | 559248 | A | F&ID,GENERATOR LUBE OIL SYSTEM | 04/12/2000 |
| 601134 | 559248 | B | F&ID,GENERATOR LUBE OIL SYSTEM | 05/24/2000 |
| 601134 | 559248 | C | F&ID,GENERATOR LUBE OIL SYSTEM | 06/02/2000 |
| 601134 | 559248 | D | F&ID GEN. LUBE OIL SYSTEM | 06/23/2000 |
| 601134 | 559254 | - | F&ID,FIRE PROTECTION SYSTEM | 12/09/1999 |
| 601134 | 559260 | - | F&ID, FUEL SYSTEM | 12/09/1999 |
| 601134 | 559262 | - | F&ID,WATER WASH SYSTEM | 12/13/1999 |
| 601134 | 559262 | A | F&ID,WATER WASH SYSTEM | 04/06/2000 |
| 601134 | 559262 | B | F&ID,WATER WASH SYSTEM | 11/06/2000 |
| 601134 | 559268 | - | F&ID,SPRINT SYSTEM ,MAIN UNIT | 01/31/2000 |
| 601134 | 559268 | A | F&ID,SPRINT SYSTEM ,MAIN UNIT | 03/09/2000 |
| 601134 | 559268 | B | F&ID,SPRINT SYSTEM ,MAIN UNIT | 04/27/2000 |
| 601134 | 559269 | - | F&ID,WATER INJECTION PUMP(DUAL SIMPLEX) | 03/30/2000 |
| 601134 | 559269 | A | F&ID,WATER INJECTION PUMP(DUAL SIMPLEX) | 05/09/2000 |
| 601134 | 559270 | - | F&ID,SPRINT SYSTEM,SPRINT SKID | 12/10/1999 |
| 601134 | 559270 | A | F&ID,SPRINT SYSTEM,SPRINT SKID | 03/01/2000 |
| 601134 | 559272 | - | INSTRUMENT DIAGRAM,AUXILIARY SYSTEMS | 03/09/2000 |
| 601134 | 559272 | A | INSTRUMENT DIAGRAM,AUXILIARY SYSTEMS | 07/05/2000 |
| 601134 | 559284 | - | GA,FIRE PROTECTION SKID |  |
| 601134 | 559290 | - | GENL ARR,WATER INJECTION SKID(SIMPLEX) | 04/05/2000 |
| 601134 | 559301 | - | AIR FILTER,DWG LIST |  |
| 601134 | 559302 | - | 302 THRU 399 MECHANICAL (RESERVED) |  |
| 601134 | 559600 | - | GENERAL ARRANGEMENT MAIN UNIT RH | 10/11/2000 |
| 601134 | 559601 | - | GA, MAIN UNIT-LH | 10/10/2000 |
| 601134 | 559741 | - | 741 THRU 771 WORKSHEETS (RESERVED) |  |
| 601134 | 559742 | - | GE,GENERATOR EXCITATION SYSTEM MODULE | 01/20/2000 |
| 601134 | 559742 | A | GE,GENERATOR EXCITATION SYSTEM MODULE | 11/08/2000 |
| 601134 | 559800 | - | 800 THRU 899 BOP (RESERVED) |  |
| 601134 | 559930 | - | SYSTEM SCHEMATIC,LIGHTING & DISTRIBUTION |  |
| 601134 | 559930 | A | SYSTEM SCHEMATIC,LIGHTING & DISTRIBUTION | 06/29/2000 |
| 601134 | 559930 | B | SYSTEM SCHEMATIC,LIGHTING & DISTRIBUTION | 07/10/2000 |
| 601134 | 559931 | - | SYSTEM SCHEMATIC,FIRE & GAS PROTECTION | 06/28/2000 |
| 601134 | 559932 | - | SYSTEM SCHEMATIC VIBRATION |  |
| 601134 | 559932 | A | SYSTEM SCHEMATIC VIBRATION |  |
| 601134 | 559932 | B | SYSTEM SCHEMATIC VIBRATION | 02/07/2000 |
| 601134 | 559932 | C | SYSTEM SCHEMATIC VIBRATION | 03/15/2000 |
| 601134 | 559933 | - | VOID-SYSTEM SCHEMATIC,HYD STARTER PANEL | 11/01/1999 |
| 601134 | 559934 | - | SYSTEM SCHEMATIC COMMUNICATION | 12/28/1999 |
| 601134 | 559934 | A | SYSTEM SCHEMATIC, COMMUNICATION | 02/14/2000 |
| 601134 | 559934 | B | SYSTEM SCHEMATIC, COMMUNICATION | 03/30/2000 |
| 601134 | 559960 | - | GENERATOR PROTECTIVE RELAY SETTINGS | 04/03/2000 |
| 601134 | 559960 | A | GENERATOR PROTECTIVE RELAY SETTINGS | 09/08/2000 |
| 601134 | 559961 | - | AUTOMATIC VOLTAGE REGULATOR SETTINGS | 04/04/2000 |
| 601134 | 559961 | A | AUTOMATIC VOLTAGE REGULATOR SETTINGS | 05/16/2000 |
| 601134 | 560233 | A | VEN,DARO, OFFSET 3/16" STRAP HINGE |  |
| 601134 | 562032 | - | THREE LINE DIAGRAM,GENERATOR METERING | 08/28/2000 |
| 601134 | 562226 | A | SHIPPING DATA | 09/14/2000 |
| 601134 | 562232 | D | F&ID,HYDR START SYSTEM | 08/16/2000 |
| 601134 | 562244 | B | F&ID,TURBINE LUBE OIL SYSTEM |  |
| 601134 | 562248 | A | F&ID,GENERATOR LUBE OIL SYSTEM | 04/12/2000 |
| 601134 | 562254 | A | F&ID,FIRE PROT SYSTEM | 08/17/2000 |
| 601134 | 562268 | B | F&ID,SPRINT SYSTEM,MAIN UNIT |  |
| 601134 | 565600 | - | ASSY,TURB GAUGE PNL GAS FUEL, WTR INJ |  |
| 601134 | 568031 | C | ONE LINE DIAGRAM | 07/10/2000 |
| 601134 | 568218 | - | GA,AUXILIARY SKID |  |
| 601134 | 568226 | B | SHIPPING DATA | 09/18/2000 |
| 601134 | 568232 | B | F&ID,HYDR START SYSTEM | 08/11/2000 |
| 601134 | 568254 | B | F&ID,FIRE PROT SYSTEM | 08/16/2000 |
| 601134 | 568260 | A | F&ID,DUAL FUEL SYSTEM |  |
| 601134 | 568960 | A | GENERATOR PROTECTIVE RELAY SETTINGS | 08/28/2000 |
| 601134 | 581226 | B | SHIPPING DATA | 09/18/2000 |
| 601134 | 581232 | B | F&ID,HYDR START SYSTEM | 08/16/2000 |
| 601134 | 581239 | B | F&ID,VENT & COMB AIR SYS | 09/14/2000 |
| 601134 | 581254 | A | F&ID,FIRE PROT SYSTEM | 08/16/2000 |
| 601134 | 701815 | - | WRG DIAG, TCP, CNTRL CUB, PSS | 10/18/2000 |
| 601134 | 701816 | - | WRG DIAG, TCP, TERM CUB, PSS | 10/18/2000 |

  - 601134A Units 13, 14, 15 & 16

LM6000, 60Hz, Gas Fuel, Brush Generator, Fin/Fan Lube Oil Cooler

| Dwg Series | DWG NO | REV | TITLE | TRANSMITTED |
| --- | --- | --- | --- | --- |
| 601134A | 559006 | B | INTERCONNECT PLAN,ELECTRICAL | 08/04/2000 |
| 601134A | 559013 | C | NPL,ENGRAVING SCHEDULE & SWITCH DEV | 08/04/2000 |
| 601134A | 559018 | C | PLAN & ELEVATION,24VDC BATTERY SYSTEM | 08/04/2000 |
| 601134A | 559022 | C | PLAN & ELEVATION,LINESIDE CUBICLE | 10/09/2000 |
| 601134A | 559023 | C | PLAN & ELEVATION,NEUTRAL CUBICLE | 08/04/2000 |
| 601134A | 559077 | A | WIRING DIAGRAM,FIRE & GAS PROT SYSTEM |  |
| 601134A | 559091 | A | WIRING DIAGRAM TURBINE SKID | 08/04/2000 |
| 601134A | 559930 | B | SYSTEM SCHEMATIC,LIGHTING & DISTRIBUTION | 08/04/2000 |
| 601134A | 559931 | - | SYSTEM SCHEMATIC,FIRE & GAS PROTECTION | 08/04/2000 |
| 601134A | 559932 | C | SYSTEM SCHEMATIC VIBRATION | 08/04/2000 |
| 601134A | 559934 | B | SYSTEM SCHEMATIC, COMMUNICATION | 08/04/2000 |
| 601134A | 562000 | - | DRAWING LIST,MASTER |  |
| 601134A | 562001 | - | DRAWING LIST,CUSTOMER |  |
| 601134A | 562005 | - | ELECTRICAL SYMBOLS,ABBR,AND REF DATA |  |
| 601134A | 562007 | - | INTERCONNECT WIRING DIAGRAM,CUSTOMER | 04/12/2000 |
| 601134A | 562009 | - | INTERCONNECT CABLE SCHEDULE | 04/06/2000 |
| 601134A | 562014 | - | PLAN & ELEVATION,TURB CONT PANEL | 08/04/2000 |
| 601134A | 562031 | - | ONE LINE DIAGRAM |  |
| 601134A | 562032 | - | THREE LINE DIAGRAM,GENERATOR METERING | 05/05/2000 |
| 601134A | 562035 | - | SCHEDULE,MOTOR CONTROL CENTER | 01/18/2000 |
| 601134A | 562035 | A | SCHEDULE,MOTOR CONTROL CENTER | 02/28/2000 |
| 601134A | 562035 | B | SCHEDULE,MOTOR CONTROL CENTER | 03/21/2000 |
| 601134A | 562041 | - | SCHEMATIC DIAGRAM,CIRCUIT BREAKER CONT | 05/18/2000 |
| 601134A | 562044 | - | SCHEMATIC DIAGRAM,MOTOR CONTROL CENTER | 03/09/2000 |
| 601134A | 562044 | A | SCHEMATIC DIAGRAM,MOTOR CONTROL CENTER | 04/13/2000 |
| 601134A | 562047 | - | SCHEMATIC DIAGRAM,DISCRETE CONTROL | 03/13/2000 |
| 601134A | 562048 | - | SCHEMATIC DIAGRAM,ANALOG CONTROL | 03/20/2000 |
| 601134A | 562049 | - | SCHEMATIC DIAGRAM,ANALOG CONTROL | 03/16/2000 |
| 601134A | 562051 | - | LOGIC FLOW DIAGRAM,FIRE PROT SYS(CO2) |  |
| 601134A | 562058 | - | WIRING DIAGRAM,TURB CONT PNL,TERMN CUB | 04/10/2000 |
| 601134A | 562077 | - | WIRING DIAGRAM,FIRE PROT SYS-CO2 |  |
| 601134A | 562078 | - | WIRING DIAGRAM,WATER INJECTION SKID |  |
| 601134A | 562143 | - | WORKSHEET,FUEL CONTROL SYS | 08/04/2000 |
| 601134A | 562145 | - | FUEL CONTROL LAYOUT | 05/15/2000 |
| 601134A | 562146 | - | WORKSHEET,SEQUENCER | 08/04/2000 |
| 601134A | 562147 | - | SEQUENCER LAYOUT | 08/04/2000 |
| 601134A | 562148 | - | WORKSHEET,DISTRIBUTED I/O CONFIGURATION | 06/19/2000 |
| 601134A | 562148 | A | WORKSHEET,DISTRIBUTED I/O CONFIGURATION | 06/22/2000 |
| 601134A | 562200 | - | GA,MAIN UNIT-RH | 03/30/2000 |
| 601134A | 562200 | A | GA,MAIN UNIT-RH | 04/11/2000 |
| 601134A | 562200 | B | GA,MAIN UNIT-RH | 05/02/2000 |
| 601134A | 562200 | C | GA,MAIN UNIT-RH |  |
| 601134A | 562200 | D | GA,MAIN UNIT-RH | 06/09/2000 |
| 601134A | 562200 | E | GA,MAIN UNIT-RH |  |
| 601134A | 562200 | F | GA,MAIN UNIT-RH | 10/19/2000 |
| 601134A | 562201 | - | GA,MAIN UNIT-LH | 04/07/2000 |
| 601134A | 562201 | A | GA,MAIN UNIT-LH | 04/12/2000 |
| 601134A | 562201 | B | GA,MAIN UNIT-LH | 05/01/2000 |
| 601134A | 562201 | C | GA,MAIN UNIT-LH | 05/09/2000 |
| 601134A | 562201 | D | GA,MAIN UNIT-LH | 06/29/2000 |
| 601134A | 562201 | E | GA,MAIN UNIT-LH | 10/20/2000 |
| 601134A | 562209 | - | GA,SPRINT SYSTEM,SPRINT SKID | 03/07/2000 |
| 601134A | 562218 | - | GA,AUXILIARY SKID | 04/03/2000 |
| 601134A | 562218 | A | GA,AUXILIARY SKID | 10/26/2000 |
| 601134A | 562222 | - | ANCHOR BOLT & SHEAR LUG DETAIL | 03/14/2000 |
| 601134A | 562224 | - | INSTL FTPT,AB & SHEAR LUG LCTN,LM6000 | 03/14/2000 |
| 601134A | 562224 | A | INSTL FTPT,AB & SHEAR LUG LCTN,LM6000 | 10/20/2000 |
| 601134A | 562225 | - | LIFT ARRANGEMENT | 05/18/2000 |
| 601134A | 562226 | - | SHIPPING DATA | 05/18/2000 |
| 601134A | 562226 | A | SHIPPING DATA |  |
| 601134A | 562231 | - | FLOW AND EQUIPMENT SYMBOLS,MECHANICAL | 12/10/1999 |
| 601134A | 562232 | - | F&ID,HYDR START SYS(60HZ) | 12/13/1999 |
| 601134A | 562232 | A | F&ID,HYDR START SYSTEM | 02/03/2000 |
| 601134A | 562232 | C | F&ID,HYDR START SYSTEM | 05/22/2000 |
| 601134A | 562232 | D | F&ID,HYDR START SYSTEM |  |
| 601134A | 562239 | - | F&ID,VENT & COMB AIR SYS(3 STAGE,60HZ) | 05/18/2000 |
| 601134A | 562239 | A | F&ID,VENT & COMB AIR SYS(3 STAGE,60HZ) | 07/25/2000 |
| 601134A | 562244 | - | F&ID,TURBINE LUBE OIL SYSTEM |  |
| 601134A | 562244 | A | F&ID,TURBINE LUBE OIL SYSTEM | 04/10/2000 |
| 601134A | 562244 | B | F&ID,TURBINE LUBE OIL SYSTEM | 05/22/2000 |
| 601134A | 562244 | C | F&ID,TURBINE LUBE OIL SYSTEM | 05/30/2000 |
| 601134A | 562244 | D | F&ID,TURBINE LUBE OIL SYSTEM | 10/26/2000 |
| 601134A | 562248 | - | F&ID,GENERATOR LUBE OIL SYSTEM | 12/10/1999 |
| 601134A | 562248 | B | F&ID,GENERATOR LUBE OIL SYSTEM | 05/22/2000 |
| 601134A | 562254 | - | F&ID,FIRE PROT SYSTEM (CO2) |  |
| 601134A | 562260 | - | F&ID, FUEL SYSTEM | 12/09/1999 |
| 601134A | 562262 | - | F&ID,WATER WASH SYSTEM |  |
| 601134A | 562262 | A | F&ID,WATER WASH SYSTEM | 04/10/2000 |
| 601134A | 562268 | - | F&ID,SPRINT SYSTEM,MAIN UNIT | 01/31/2000 |
| 601134A | 562268 | A | F&ID,SPRINT SYSTEM,MAIN UNIT |  |
| 601134A | 562268 | B | F&ID,SPRINT SYSTEM,MAIN UNIT | 04/26/2000 |
| 601134A | 562269 | - | F&ID,WATER INJECTION PUMP(DUAL SIMPLEX) | 03/30/2000 |
| 601134A | 562269 | A | F&ID,WATER INJECTION PUMP(DUAL SIMPLEX) | 05/04/2000 |
| 601134A | 562270 | - | F&ID,SPRINT SYSTEM,SPRINT SKID | 12/10/1999 |
| 601134A | 562270 | A | F&ID,SPRINT SYSTEM,SPRINT SKID | 03/01/2000 |
| 601134A | 562272 | - | INSTRUMENT DIAGRAM,AUXILIARY SYSTEMS | 12/10/1999 |
| 601134A | 562272 | A | INSTRUMENT DIAGRAM,AUXILIARY SYSTEMS | 04/04/2000 |
| 601134A | 562272 | B | INSTRUMENT DIAGRAM,AUXILIARY SYSTEMS | 07/17/2000 |
| 601134A | 562284 | - | GA,FIRE PROTECTION SKID |  |
| 601134A | 562290 | - | GA, WATER INJECTION SKID (SIMPLEX) | 03/30/2000 |
| 601134A | 562290 | A | GA, WATER INJECTION SKID (SIMPLEX) | 04/10/2000 |
| 601134A | 562600 | - | GA, MAIN UNIT, RH | 06/27/2000 |
| 601134A | 562600 | A | GA, MAIN UNIT, RH | 07/01/3100 |
| 601134A | 562601 | - | GA, MAIN UNIT-LH | 06/27/2000 |
| 601134A | 568031 | C | ONE LINE DIAGRAM | 08/04/2000 |
| 601134A | 568037 | A | SYSTEM SCHEMATIC,GENERATOR EXCITATION | 08/04/2000 |
| 601134A | 568057 | - | WIRING DIAGRAM,TCP, CONTROL CUBICLE | 08/04/2000 |
| 601134A | 568081 | A | WIRING DIAGRAM,NEUTRAL CUBICLE | 08/04/2000 |
| 601134A | 568091 | A | WIRING DIAG,TURBINE SKID | 08/04/2000 |
| 601134A | 568092 | A | WIRING DIAGRAM GENERATOR SKID | 08/04/2000 |
| 601134A | 568226 | B | SHIPPING DATA |  |
| 601134A | 568960 | A | GENERATOR PROTECTIVE RELAY SETTINGS | 08/04/2000 |
| 601134A | 568961 | - | AUTOMATIC VOLTAGE REGULATOR SETTINGS | 08/04/2000 |
| 601134A | 701308 | A | WIRING DIAGRAM, TURB GAUGE PANEL, UNIV. | 08/04/2000 |
| 601134A | 701341 | - | LM6000/60,FAB DTL, LUBE OIL PIPE GEN LH |  |
| 601134A | 701402 | B | WIRING DIAGRAM, GENERATOR MODULE,UNIV | 08/04/2000 |
| 601134A | 701404 | A | WIRING DIAGRAM, NEUTRAL CUBICLE,UNIV | 08/04/2000 |
| 601134A | 701406 | C | WIRING DIAGRAM, AUXILIARY SKID,UNIV | 08/04/2000 |
| 601134A | 701407 | A | WIRING DIAGRAM, SPRINT SKID,UNIV | 08/04/2000 |
| 601134A | 701408 | D | WIRING DIAGRAM,TCP, CONTROL CUBICLE,UNIV | 08/04/2000 |
| 601134A | 701409 | D | WIRING DIAGRAM, TCP, TERMN CUBICLE,UNIV | 08/04/2000 |
| 601134A | 701413 | A | WIRING DIAGRAM, AIR INLET FILTER,UNIV | 08/04/2000 |
| 601134A | 701414 | C | WIRING DIAGRAM, TURBINE MODULE,UNIV. | 08/04/2000 |
| 601134A | 701415 | - | WIRING DIAGRAM, TURBINE MODULE,GAS | 08/04/2000 |
| 601134A | 701419 | - | WIRING DIAGRAM, TURB MODULE,NOX WATER | 08/04/2000 |
| 601134A | 701423 | - | WIRING DIAGRAM,TCP,CONT CUBICLE,GAS | 08/04/2000 |
| 601134A | 701424 | - | WIRING DIAGRAM,TCP,CONT CUB,NOX WATER |  |
| 601134A | 701604 | A | WIRING DIAGRAM,TURBINE GAUGE PANEL, GAS | 08/04/2000 |
| 601134A | 701613 | A | WRG DIAG,TURB GAUGE PANEL, SPRINT | 08/04/2000 |
| 601134A | 701615 | A | WIRING DIAGRAM,TURBINE MODULE,ENH SPRINT | 08/04/2000 |
| 601134A | 701616 | - | WIRING DIAGRAM,TCP,TERM CUB, NOX WATER | 08/04/2000 |
| 601134A | 701617 | - | WIRING DIAGRAM,TCP,TERMN CUBICLE,GAS | 08/04/2000 |
| 601134A | 701629 | A | WIRING DIAGRAM,TCP,TERM CUB,ENH. SPRINT | 08/04/2000 |
| 601134A | 701633 | A | WIRING DIAG,GEN MODULE,SPACE HEATER | 08/04/2000 |
| 601134A | 701634 | B | WIRING DIAG,TURB MODULE,SPACE HEATER | 08/04/2000 |
| 601134A | 701635 | - | WIRING DIA, LINESIDE CUBICLE, UNIV | 08/04/2000 |
| 601134A | E9955BOM | 0 | VEN,BRADEN,BM-6000-X-45 EXT,BOM |  |
| 601134A | L1049-02-201 | 5 | VEN,ALTAIR, GT COMBUSTION INLET SILENCER |  |
| 601134A | L1049-02-210 | 9 | VEN,ALTAIR,DUAL ASPECT INTAKE FOR - | 10/09/2000 |

  - 601134B Units 7, 8, 17 & 18

LM6000, 60Hz, Dual Fuel, Brush Generator, Fin/Fan Oil Cooler

| Dwg Series | Field59 | DWG NO | REV | TITLE | TRANSMITTED |
| --- | --- | --- | --- | --- | --- |
| 601134B | 568 | 559022 | C | PLAN & ELEVATION,LINESIDE CUBICLE | 10/09/2000 |
| 601134B | 568 | 559023 | C | PLAN & ELEVATION,NEUTRAL CUBICLE |  |
| 601134B | 568 | 559032 | B | THREE LINE DIAGRAM,GENERATOR METERING |  |
| 601134B | 568 | 559041 | A | SCHEMATIC DIAGRAM,CIRCUIT BREAKER CONT |  |
| 601134B | 568 | 559077 | A | WIRING DIAGRAM,FIRE & GAS PROT SYSTEM |  |
| 601134B | 568 | 559930 | B | SYSTEM SCHEMATIC,LIGHTING & DISTRIBUTION |  |
| 601134B | 568 | 559932 | C | SYSTEM SCHEMATIC VIBRATION |  |
| 601134B | 568 | 559934 | B | SYSTEM SCHEMATIC, COMMUNICATION |  |
| 601134B | 568 | 568006 | - | INTERCONNECT PLAN,ELECTRICAL | 01/31/2000 |
| 601134B | 568 | 568007 | - | INTERCONNECT WIRING DIAGRAM,CUSTOMER | 03/30/2000 |
| 601134B | 568 | 568007 | A | INTERCONNECT WIRING DIAGRAM,CUSTOMER | 07/10/2000 |
| 601134B | 568 | 568009 | - | INTERCONNECT CABLE SCHEDULE | 03/29/2000 |
| 601134B | 568 | 568009 | A | INTERCONNECT CABLE SCHEDULE | 07/03/2000 |
| 601134B | 568 | 568013 | - | NAMEPLATE LIST,ENGRAVING SCHEDULE |  |
| 601134B | 568 | 568014 | - | PLAN & ELEVATION,TURB CONT PANEL |  |
| 601134B | 568 | 568031 | - | ONE LINE DIAGRAM | 01/31/2000 |
| 601134B | 568 | 568031 | A | ONE LINE DIAGRAM | 02/21/2000 |
| 601134B | 568 | 568031 | B | ONE LINE DIAGRAM | 05/05/2000 |
| 601134B | 568 | 568031 | C | ONE LINE DIAGRAM | 07/07/2000 |
| 601134B | 568 | 568035 | - | SCHEDULE,MOTOR CONTROL CENTER | 01/18/2000 |
| 601134B | 568 | 568035 | A | SCHEDULE,MOTOR CONTROL CENTER | 02/28/2000 |
| 601134B | 568 | 568035 | B | SCHEDULE,MOTOR CONTROL CENTER | 03/21/2000 |
| 601134B | 568 | 568037 | - | SYSTEM SCHEMATIC,GENERATOR EXCITATION | 01/31/2000 |
| 601134B | 568 | 568037 | A | SYSTEM SCHEMATIC,GENERATOR EXCITATION | 05/08/2000 |
| 601134B | 568 | 568044 | - | SCHEMATIC DIAGRAM,MOTOR CONTROL CENTER | 03/09/2000 |
| 601134B | 568 | 568044 | A | SCHEMATIC DIAGRAM,MOTOR CONTROL CENTER | 06/27/2000 |
| 601134B | 568 | 568047 | - | SCHEMATIC DIAG,DISCRETE CONTROL | 02/28/2000 |
| 601134B | 568 | 568047 | A | SCHEMATIC DIAG,DISCRETE CONTROL | 06/27/2000 |
| 601134B | 568 | 568048 | - | SCHEMATIC DIAGRAM,ANALOG CONTROL | 02/28/2000 |
| 601134B | 568 | 568049 | - | SCHEMATIC DIAGRAM,ANALOG CONTROL | 03/01/2000 |
| 601134B | 568 | 568049 | A | SCHEMATIC DIAGRAM,ANALOG CONTROL | 07/10/2000 |
| 601134B | 568 | 568051 | - | LOGIC FLOW DIAGRAM,FIRE & GAS PROT SYS | 07/03/2000 |
| 601134B | 568 | 568057 | - | WIRING DIAGRAM,TCP, CONTROL CUBICLE |  |
| 601134B | 568 | 568058 | - | WRG DIAG, TCP,TERMINATION CUBICLE |  |
| 601134B | 568 | 568058 | A | WRG DIAG, TCP,TERMINATION CUBICLE | 07/10/2000 |
| 601134B | 568 | 568081 | - | WIRING DIAGRAM,NEUTRAL CUBICLE |  |
| 601134B | 568 | 568081 | A | WIRING DIAGRAM,NEUTRAL CUBICLE |  |
| 601134B | 568 | 568084 | - | VOID- WIRING DIAGRAM,AUXILIARY SKID |  |
| 601134B | 568 | 568091 | - | WIRING DIAG,TURBINE SKID |  |
| 601134B | 568 | 568091 | A | WIRING DIAG,TURBINE SKID |  |
| 601134B | 568 | 568092 | - | WIRING DIAGRAM GENERATOR SKID | 03/16/2000 |
| 601134B | 568 | 568092 | A | WIRING DIAGRAM GENERATOR SKID |  |
| 601134B | 568 | 568143 | - | WORKSHEET,FUEL CONTROL |  |
| 601134B | 568 | 568145 | - | FUEL CONTROL LAYOUT |  |
| 601134B | 568 | 568146 | - | WORKSHEET SEQUENCER |  |
| 601134B | 568 | 568147 | - | SEQUENCER LAYOUT |  |
| 601134B | 568 | 568148 | - | WORKSHEET,DISTRIBUTED I/O COMMUNICATION | 04/04/2000 |
| 601134B | 568 | 568148 | A | WORKSHEET,DISTRIBUTED I/O COMMUNICATION | 06/22/2000 |
| 601134B | 568 | 568200 | - | GA,MAIN UNIT-RH | 03/13/2000 |
| 601134B | 568 | 568200 | A | GA,MAIN UNIT-RH | 04/03/2000 |
| 601134B | 568 | 568200 | B | GA,MAIN UNIT-RH | 04/12/2000 |
| 601134B | 568 | 568200 | C | GA,MAIN UNIT-RH | 04/28/2000 |
| 601134B | 568 | 568200 | D | GA,MAIN UNIT-RH | 05/10/2000 |
| 601134B | 568 | 568200 | E | GA,MAIN UNIT-RH | 06/17/2000 |
| 601134B | 568 | 568200 | F | GA,MAIN UNIT-RH | 07/17/2000 |
| 601134B | 568 | 568200 | G | GA,MAIN UNIT-RH | 10/20/2000 |
| 601134B | 568 | 568201 | - | GA,MAIN UNIT-LH | 03/14/2000 |
| 601134B | 568 | 568201 | A | GA,MAIN UNIT-LH | 04/03/2000 |
| 601134B | 568 | 568201 | B | GA,MAIN UNIT-LH |  |
| 601134B | 568 | 568201 | C | GA,MAIN UNIT-LH | 05/01/2000 |
| 601134B | 568 | 568201 | D | GA,MAIN UNIT-LH | 05/10/2000 |
| 601134B | 568 | 568201 | E | GA,MAIN UNIT-LH | 06/23/2000 |
| 601134B | 568 | 568201 | F | GA,MAIN UNIT-LH | 06/29/2000 |
| 601134B | 568 | 568209 | - | GA,SPRINT SYSTEM,SPRINT SKID | 02/28/2000 |
| 601134B | 568 | 568212 | - | GA,LIQUID FUEL PUMP SKID(BOOST) | 04/07/2000 |
| 601134B | 568 | 568218 | - | GA,AUXILIARY SKID | 04/07/2000 |
| 601134B | 568 | 568218 | A | GA,AUXILIARY SKID | 08/03/2000 |
| 601134B | 568 | 568218 | B | GA,AUXILIARY SKID | 10/24/2000 |
| 601134B | 568 | 568222 | - | ANCHOR BOLT & SHEAR LUG DETAIL | 03/13/2000 |
| 601134B | 568 | 568222 | A | ANCHOR BOLT & SHEAR LUG DETAIL | 08/08/2000 |
| 601134B | 568 | 568224 | - | INSTALLATION FOOTPRINT(MAIN UNIT) | 03/13/2000 |
| 601134B | 568 | 568224 | A | INSTALLATION FOOTPRINT(MAIN UNIT) | 08/08/2000 |
| 601134B | 568 | 568225 | - | LIFT ARRANGEMENT | 05/19/2000 |
| 601134B | 568 | 568226 | - | SHIPPING DATA | 05/18/2000 |
| 601134B | 568 | 568226 | A | SHIPPING DATA | 07/05/2000 |
| 601134B | 568 | 568226 | B | SHIPPING DATA |  |
| 601134B | 568 | 568231 | - | FLOW AND EQUIPMENT SYMBOLS,MECHANICAL | 03/13/2000 |
| 601134B | 568 | 568231 | A | FLOW AND EQUIPMENT SYMBOLS,MECHANICAL | 08/02/2000 |
| 601134B | 568 | 568232 | - | F&ID,HYDR START SYSTEM | 03/13/2000 |
| 601134B | 568 | 568232 | A | F&ID,HYDR START SYSTEM | 05/22/2000 |
| 601134B | 568 | 568232 | B | F&ID,HYDR START SYSTEM |  |
| 601134B | 568 | 568239 | - | F&ID,VENT & COMB AIR SYS | 05/18/2000 |
| 601134B | 568 | 568239 | A | F&ID,VENT & COMB AIR SYS | 06/13/2000 |
| 601134B | 568 | 568239 | B | F&ID,VENT & COMB AIR SYS | 07/21/2000 |
| 601134B | 568 | 568244 | - | F&ID,TURBINE LUBE OIL SYSTEM | 04/07/2000 |
| 601134B | 568 | 568244 | A | F&ID,TURBINE LUBE OIL SYSTEM | 05/22/2000 |
| 601134B | 568 | 568244 | B | F&ID,TURBINE LUBE OIL SYSTEM | 10/20/2000 |
| 601134B | 568 | 568248 | - | F&ID,GENERATOR LUBE OIL SYSTEM | 04/07/2000 |
| 601134B | 568 | 568248 | A | F&ID,GENERATOR LUBE OIL SYSTEM | 05/22/2000 |
| 601134B | 568 | 568248 | B | F&ID,GENERATOR LUBE OIL SYSTEM | 07/05/2000 |
| 601134B | 568 | 568248 | C | F&ID,GENERATOR LUBE OIL SYSTEM | 07/26/2000 |
| 601134B | 568 | 568254 | - | F&ID,FIRE PROT SYSTEM | 03/13/2000 |
| 601134B | 568 | 568254 | A | F&ID,FIRE PROT SYSTEM | 08/02/2000 |
| 601134B | 568 | 568254 | B | F&ID,FIRE PROT SYSTEM |  |
| 601134B | 568 | 568260 | - | F&ID,DUAL FUEL SYSTEM | 03/13/2000 |
| 601134B | 568 | 568260 | A | F&ID,DUAL FUEL SYSTEM | 06/30/2000 |
| 601134B | 568 | 568260 | B | F&ID,DUAL FUEL SYSTEM | 08/02/2000 |
| 601134B | 568 | 568261 | - | F&ID,CDP PURGE SYSTEM (DUAL FUEL) | 03/14/2000 |
| 601134B | 568 | 568261 | A | F&ID,CDP PURGE SYSTEM (DUAL FUEL) | 08/02/2000 |
| 601134B | 568 | 568262 | - | F&ID,WATER WASH SYSTEM | 03/13/2000 |
| 601134B | 568 | 568262 | A | F&ID,WATER WASH SYSTEM | 04/03/2000 |
| 601134B | 568 | 568262 | B | F&ID,WATER WASH SYSTEM | 08/02/2000 |
| 601134B | 568 | 568265 | - | F&ID, LIQUID FUEL PUMP (BOOST) | 04/19/2000 |
| 601134B | 568 | 568268 | - | F&ID,SPRINT SYSTEM,MAIN UNIT | 03/01/2000 |
| 601134B | 568 | 568268 | A | F&ID,SPRINT SYSTEM,MAIN UNIT | 04/27/2000 |
| 601134B | 568 | 568269 | - | F&ID,WATER INJECTION PUMP(DUAL SIMPLEX) | 04/05/2000 |
| 601134B | 568 | 568269 | A | F&ID,WATER INJECTION PUMP(DUAL SIMPLEX) | 06/05/2000 |
| 601134B | 568 | 568270 | - | F&ID,SPRINT SYSTEM,SPRINT SKID | 03/13/2000 |
| 601134B | 568 | 568270 | A | F&ID,SPRINT SYSTEM,SPRINT SKID | 08/02/2000 |
| 601134B | 568 | 568272 | - | INSTRUMENT DIAGRAM,AUXILIARY SYSTEMS | 03/13/2000 |
| 601134B | 568 | 568272 | A | INSTRUMENT DIAGRAM,AUXILIARY SYSTEMS | 07/05/2000 |
| 601134B | 568 | 568272 | B | INSTRUMENT DIAGRAM,AUXILIARY SYSTEMS | 08/08/2000 |
| 601134B | 568 | 568284 | - | GA,FIRE PROTECTION SKID |  |
| 601134B | 568 | 568290 | - | GA,WATER INJECTION SKID(DUAL SIMPLEX) | 04/03/2000 |
| 601134B | 568 | 568290 | A | GA,WATER INJECTION SKID(DUAL SIMPLEX) | 08/02/2000 |
| 601134B | 568 | 568600 | - | GA, MAIN UNIT - RH | 10/11/2000 |
| 601134B | 568 | 568601 | - | GA, MAIN UNIT-LH | 10/10/2000 |
| 601134B | 568 | 568960 | - | GENERATOR PROTECTIVE RELAY SETTINGS | 04/04/2000 |
| 601134B | 568 | 568960 | A | GENERATOR PROTECTIVE RELAY SETTINGS | 07/26/2000 |
| 601134B | 568 | 568961 | - | AUTOMATIC VOLTAGE REGULATOR SETTINGS | 04/04/2000 |
| 601134B | 568 | L1049-02-210 | 9 | VEN,ALTAIR,DUAL ASPECT INTAKE FOR - | 10/09/2000 |

  - 601134C Units 9, 10, 11, 12, 19, 20, 23 & 24

LM6000, 60Hz, Gas Fuel, Brush Generator, Shell/Tube Oil Cooler

| Dwg Series | DWG NO | REV | TITLE | TRANSMITTED |
| --- | --- | --- | --- | --- |
| 601134C | 535005 | - | ELECTRICAL SYMBOLS,ABBR,AND REF DATA | 08/03/2000 |
| 601134C | 535025 | - | P&E, LINESIDE CUB,TOP ENTRY BUS DUCT | 08/03/2000 |
| 601134C | 535051 | - | LOGIC FLOW DIAGRAM,FIRE & GAS PROT SYS | 08/03/2000 |
| 601134C | 535077 | - | WIRING DIAGRAM,FIRE & GAS PROT SYS | 08/03/2000 |
| 601134C | 535931 | A | SYS SCHEMATIC,FIRE & GAS PROTECTION |  |
| 601134C | 535932 | C | SYSTEM SCHEMATIC,VIBRATION |  |
| 601134C | 535961 | A | AUTOMATIC VOLTAGE REGULATOR SETTINGS | 08/03/2000 |
| 601134C | 535962 | - | DIGITAL MULTI FUNCTION METER SETTINGS | 08/03/2000 |
| 601134C | 559013 | B | NPL,ENGRAVING SCHEDULE & SWITCH DEV | 08/03/2000 |
| 601134C | 559018 | C | PLAN & ELEVATION,24VDC BATTERY SYSTEM | 08/03/2000 |
| 601134C | 559023 | B | PLAN & ELEVATION,NEUTRAL CUBICLE |  |
| 601134C | 559023 | C | PLAN & ELEVATION,NEUTRAL CUBICLE | 08/03/2000 |
| 601134C | 559032 | - | THREE LINE DIAGRAM,GENERATOR METERING |  |
| 601134C | 559091 | - | WIRING DIAGRAM TURBINE SKID |  |
| 601134C | 559091 | A | WIRING DIAGRAM TURBINE SKID | 08/03/2000 |
| 601134C | 559930 | B | SYSTEM SCHEMATIC,LIGHTING & DISTRIBUTION |  |
| 601134C | 562032 | - | THREE LINE DIAGRAM,GENERATOR METERING |  |
| 601134C | 568031 | A | ONE LINE DIAGRAM |  |
| 601134C | 568031 | C | ONE LINE DIAGRAM | 08/03/2000 |
| 601134C | 568037 | - | SYSTEM SCHEMATIC,GENERATOR EXCITATION |  |
| 601134C | 568037 | A | SYSTEM SCHEMATIC,GENERATOR EXCITATION | 08/03/2000 |
| 601134C | 568081 | - | WIRING DIAGRAM,NEUTRAL CUBICLE |  |
| 601134C | 568081 | A | WIRING DIAGRAM,NEUTRAL CUBICLE | 08/03/2000 |
| 601134C | 568092 | - | WIRING DIAGRAM GENERATOR SKID |  |
| 601134C | 568092 | A | WIRING DIAGRAM GENERATOR SKID | 08/03/2000 |
| 601134C | 568960 | - | GENERATOR PROTECTIVE RELAY SETTINGS |  |
| 601134C | 568960 | A | GENERATOR PROTECTIVE RELAY SETTINGS | 08/03/2000 |
| 601134C | 581006 | - | INTERCONNECT PLAN,ELECTRICAL | 05/05/2000 |
| 601134C | 581007 | - | INTERCONNECT WIRING DIAGRAM,CUSTOMER | 05/26/2000 |
| 601134C | 581009 | - | INTERCONNECT CABLE SCHEDULE | 05/25/2000 |
| 601134C | 581014 | - | PLAN & ELEVATION,TURB CONT PANEL | 05/05/2000 |
| 601134C | 581035 | - | SCHEDULE,MOTOR CONTROL CENTER | 04/27/2000 |
| 601134C | 581041 | - | SCHEMATIC DIAGRAM,CIRCUIT BREAKER CONT | 05/08/2000 |
| 601134C | 581044 | - | SCHEMATIC DIAGRAM,MOTOR CONTROL CENTER | 05/05/2000 |
| 601134C | 581047 | - | SCHEMATIC DIAGRAM,DISCRETE CONTROL | 05/15/2000 |
| 601134C | 581048 | - | SCHEMATIC DIAGRAM,ANALOG CONTROL | 05/17/2000 |
| 601134C | 581049 | - | SCHEMATIC DIAGRAM,ANALOG CONTROL | 05/17/2000 |
| 601134C | 581058 | - | WIRING DIAGRAM,TURB CONT PNL,TERMN CUB | 08/03/2000 |
| 601134C | 581143 | - | WORKSHEET,FUELCONTROL | 08/03/2000 |
| 601134C | 581145 | - | FUEL CONTROL LAYOUT | 05/15/2000 |
| 601134C | 581146 | - | WORKSHEET,SEQUENCER | 08/03/2000 |
| 601134C | 581147 | - | SEQUENCER LAYOUT | 08/03/2000 |
| 601134C | 581148 | - | WORKSHEET,DISTRIBUTED I/O CONFIGURATION | 08/08/2000 |
| 601134C | 581200 | - | GA,MAIN UNIT-RH | 05/09/2000 |
| 601134C | 581200 | A | GA,MAIN UNIT-RH | 06/17/2000 |
| 601134C | 581200 | B | GA,MAIN UNIT-RH | 07/12/2000 |
| 601134C | 581200 | C | GA,MAIN UNIT-RH | 10/20/2000 |
| 601134C | 581201 | - | GA,MAIN UNIT-LH |  |
| 601134C | 581201 | A | GA,MAIN UNIT-LH | 06/22/2000 |
| 601134C | 581201 | B | GA,MAIN UNIT-LH | 06/29/2000 |
| 601134C | 581201 | C | GA,MAIN UNIT-LH | 10/19/2000 |
| 601134C | 581209 | - | GA,SPRINT SYSTEM SPRINT SKID | 04/28/2000 |
| 601134C | 581218 | - | GA,AUXILIARY SKID | 05/03/2000 |
| 601134C | 581218 | A | GA,AUXILIARY SKID | 05/26/2000 |
| 601134C | 581218 | B | GA,AUXILIARY SKID | 10/26/2000 |
| 601134C | 581222 | - | ANCHOR BOLT & SHEAR LUG DETAIL(M UNIT) | 05/04/2000 |
| 601134C | 581224 | - | INSTALLATION FOOTPRINT(MAIN UNIT) | 05/11/2000 |
| 601134C | 581225 | - | LIFT ARRANGEMENT | 05/18/2000 |
| 601134C | 581226 | - | SHIPPING DATA | 05/18/2000 |
| 601134C | 581226 | A | SHIPPING DATA | 07/05/2000 |
| 601134C | 581226 | B | SHIPPING DATA |  |
| 601134C | 581231 | - | FLOW AND EQUIPMENT SYMBOLS,MECHANICAL | 05/05/2000 |
| 601134C | 581232 | - | F&ID,HYDR START SYSTEM | 05/04/2000 |
| 601134C | 581232 | A | F&ID,HYDR START SYSTEM | 05/22/2000 |
| 601134C | 581232 | B | F&ID,HYDR START SYSTEM | 11/03/2000 |
| 601134C | 581239 | - | F&ID,VENT & COMB AIR SYS | 05/18/2000 |
| 601134C | 581239 | A | F&ID,VENT & COMB AIR SYS | 07/20/2000 |
| 601134C | 581239 | B | F&ID,VENT & COMB AIR SYS | 09/12/2000 |
| 601134C | 581244 | - | F&ID,TURBINE LUBE OIL SYSTEM | 05/11/2000 |
| 601134C | 581244 | A | F&ID,TURBINE LUBE OIL SYSTEM | 05/22/2000 |
| 601134C | 581248 | - | F&ID,GENERATOR LUBE OIL SYSTEM | 05/05/2000 |
| 601134C | 581248 | A | F&ID,GENERATOR LUBE OIL SYSTEM | 05/22/2000 |
| 601134C | 581248 | B | F&ID,GENERATOR LUBE OIL SYSTEM | 07/05/2000 |
| 601134C | 581248 | C | F&ID,GENERATOR LUBE OIL SYSTEM | 07/25/2000 |
| 601134C | 581254 | - | F&ID,FIRE PROT SYSTEM | 05/04/2000 |
| 601134C | 581254 | A | F&ID,FIRE PROT SYSTEM | 11/03/2000 |
| 601134C | 581260 | - | F&ID,FUEL SYSTEM | 05/04/2000 |
| 601134C | 581262 | - | F&ID,WATER WASH SYSTEM | 05/03/2000 |
| 601134C | 581268 | - | F&ID,SPRINT SYSTEM,MAIN UNIT | 05/05/2000 |
| 601134C | 581269 | - | F&ID,WATER INJECTION SKID(DUAL SIMPLEX) | 05/05/2000 |
| 601134C | 581269 | A | F&ID WATER INJ PUMP (DUAL SIMPLEX) | 09/07/2000 |
| 601134C | 581270 | - | F&ID,SPRINT SYSTEM,SPRINT SKID | 05/04/2000 |
| 601134C | 581270 | A | F&ID,SPRINT SYSTEM,SPRINT SKID | 09/07/2000 |
| 601134C | 581272 | - | INSTRUMENT DIAGRAM,AUXILIARY SYSTEMS | 05/03/2000 |
| 601134C | 581272 | A | INSTRUMENT DIAGRAM,AUXILIARY SYSTEMS | 07/05/2000 |
| 601134C | 581290 | - | GA,WATER INJECTION SKID(SIMPLEX) | 05/03/2000 |
| 601134C | 581290 | A | G. A. WATER INJECTION PUMP SKID SIMPLEX | 09/07/2000 |
| 601134C | 581302 | - | 302 THRU 399 MECHANICAL (RESERVED) |  |
| 601134C | 581600 | - | GA, MAIN UNIT-RH | 06/24/2000 |
| 601134C | 581600 | A | GA, MAIN UNIT-RH | 07/12/2000 |
| 601134C | 581600 | B | GA, MAIN UNIT-RH | 10/11/2000 |
| 601134C | 581601 | - | GA, MAIN UNIT-LH | 06/23/2000 |
| 601134C | 581601 | A | GA, MAIN UNIT-LH | 06/29/2000 |
| 601134C | 581601 | B | GA, MAIN UNIT-LH | 10/11/2000 |
| 601134C | 581900 | - | 900 THRU 999 ELECTRICAL (RESERVED) |  |
| 601134C | 581934 | - | SYSTEM SCHEMATIC,COMMUNICATION | 05/12/2000 |
| 601134C | 701024 | - | LM6000 TURB MODULE UNIV, HYDR START |  |
| 601134C | 701042 | - | LM6000 TURB MODULE,RH HYD START PPG FAB |  |
| 601134C | 701055 | - | LM6000,TURB MODULE,LH HYD START,PPG FAB |  |
| 601134C | 701234 | - | LM6000 AUX SKID TURB LO SHELL & TUBE CLR |  |
| 601134C | 701308 | A | WIRING DIAGRAM, TURB GAUGE PANEL, UNIV. | 08/02/2000 |
| 601134C | 701341 | - | LM6000/60,FAB DTL, LUBE OIL PIPE GEN LH |  |
| 601134C | 701402 | B | WIRING DIAGRAM, GENERATOR MODULE,UNIV | 08/02/2000 |
| 601134C | 701404 | A | WIRING DIAGRAM, NEUTRAL CUBICLE,UNIV | 08/02/2000 |
| 601134C | 701406 | C | WIRING DIAGRAM, AUXILIARY SKID,UNIV | 08/02/2000 |
| 601134C | 701407 | A | WIRING DIAGRAM, SPRINT SKID,UNIV | 08/02/2000 |
| 601134C | 701408 | D | WIRING DIAGRAM,TCP, CONTROL CUBICLE,UNIV | 08/02/2000 |
| 601134C | 701409 | D | WIRING DIAGRAM, TCP, TERMN CUBICLE,UNIV | 08/02/2000 |
| 601134C | 701413 | A | WIRING DIAGRAM, AIR INLET FILTER,UNIV | 08/02/2000 |
| 601134C | 701414 | C | WIRING DIAGRAM, TURBINE MODULE,UNIV. | 08/02/2000 |
| 601134C | 701415 | - | WIRING DIAGRAM, TURBINE MODULE,GAS | 08/02/2000 |
| 601134C | 701419 | - | WIRING DIAGRAM, TURB MODULE,NOX WATER | 08/02/2000 |
| 601134C | 701423 | - | WIRING DIAGRAM,TCP,CONT CUBICLE,GAS | 08/02/2000 |
| 601134C | 701424 | - | WIRING DIAGRAM,TCP,CONT CUB,NOX WATER | 08/02/2000 |
| 601134C | 701604 | A | WIRING DIAGRAM,TURBINE GAUGE PANEL, GAS | 08/02/2000 |
| 601134C | 701615 | A | WIRING DIAGRAM,TURBINE MODULE,ENH SPRINT | 08/02/2000 |
| 601134C | 701616 | - | WIRING DIAGRAM,TCP,TERM CUB, NOX WATER | 08/02/2000 |
| 601134C | 701617 | - | WIRING DIAGRAM,TCP,TERMN CUBICLE,GAS | 08/02/2000 |
| 601134C | 701629 | A | WIRING DIAGRAM,TCP,TERM CUB,ENH. SPRINT | 08/02/2000 |
| 601134C | 701633 | A | WIRING DIAG,GEN MODULE,SPACE HEATER | 08/02/2000 |
| 601134C | 701634 | B | WIRING DIAG,TURB MODULE,SPACE HEATER | 08/02/2000 |
| 601134C | 701635 | - | WIRING DIA, LINESIDE CUBICLE, UNIV | 08/02/2000 |
| 601134C | E9955 | 0 | VEN,BRADEN,BM-6000-X-45 EXT,ERECTION DWG |  |
| 601134C | E9955BOM | 0 | VEN,BRADEN,BM-6000-X-45 EXT,BOM |  |
| 601134C | L1049-02-210 | 9 | VEN,ALTAIR,DUAL ASPECT INTAKE FOR - | 10/09/2000 |