| ENRON Federal Solutions, Inc. |  |  |  | # SIGNIFICANT EVENTS REPORT March 10-16, 2000 TEAM MEMBERS: Bill Votaw, John Carr, Bill Gang, Dean Tarbet, Lex Carroll |
| --- | --- | --- | --- | --- |

### RED FLAGS

None

SIGNIFICANT EVENTS

Item

Ft. Carson - Privatization

Good news!  We just got word that the Colorado Public Utilities Commission has ruled favorably on our petition regarding state jurisdiction.  We have not seen the ruling yet (Bob Frank is getting is), but we understand the basis of the ruling to be largely Federal pre-emption.  Bob is also working on getting a scheduling conference on the Federal lawsuit to wake this case back up.

Item

Ft. Campbell - Privatization

The proposal is still due on 4 Apr 00 in Huntsville.  The schedule is as follows (WD is Walt Daniels):

| Site visits: | Feb 23-25 |
| --- | --- |
| Project/O&M Costs due to WD: | March 14 |
| Tech Response due WD: | March 14 |
| Project/O&M cost due to desk: | March 16 |
| Tech Response due to EFSI: | March 16 |
| Cost due to EFSI: | March 23 |
| Publish: | April 2 |
| RFP due: | April 4 |

Azurix is late with costs to Walt Daniels.  Other than that, we are on schedule.  There may be a further impact on schedule, however, due to COE Huntsville's inability to respond to all the bidder questions they have received.  Only one amendment has been released, which addresses the question from the bidders' conference.  We need to identify a Project (Account) Manager for this job.

Item

Ft. Bragg - Privatization

The due diligence visit on 8-9 Mar 00 went well, in spite of a lack of technical documentation by the Ft. Bragg PWC.  We were supported by Walt Daniels, Tony Vivona, Tom Ginsbach, and Dave Miller.  The RFP response is due 18 Apr 00.  We are working to the following schedule (WD is Walt Daniels):

| Site visits: | March 9-10 |
| --- | --- |
| Project/O&M Costs due to WD: | March 24 |
| Tech Response due WD: | March 24 |
| Project/O&M cost due to desk: | March 28 |
| Tech Response due to EFSI: | March 28 |
| Cost due to EFSI: | April 4 |
| Publish: | April 16 |
| RFP due: | April 18 |

Item

RFI Responses - Privatization

During this reporting period the West responded to one RFI for Ft. Lewis, WA for its water distribution system.